**APPENDIX - IX**

**COMMITMENTS OF THE GOVERNMENT- LIST OF INCOMPLETE CAPITAL WORKS- contd.**

**PUBLIC WORKS DEPARTMENT ( ` in lakh)**

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl. No.** | **Name of the project/works** | **Estimated cost of work /date of sanction** | **Year of commen-cement** | **Target year of completion** | **Physical Progress of work (in percent) as on 31.03.24** | **Expendi-**  **ture during the year** | **Progressive expenditure to the end of the year** | **Pending payment** | **Revised cost, if any/date of revision** | |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** | |
| **BUILDINGS** | | | | | | | | | | |
| 1 | Construction of Building for Establishment of Government Medical College in Jagdalpur | 6,817.84 05.09.2007 | 2007-08 | 2011-12 | **\*** | 0.00 | 22,014.90 | \* | 26,868.82 | 05.01.17 |
| 2 | Construction of Medical College Building at Raigarh | 8,343.00  17.07.2008 | 2008-09 | 2009-10 | **\*** | 926.46 | 26,498.00 | \* | 28,251.00 | 26.09.13 |
| 3 | Construction of Composite Building in Ambikapur | 1,522.61  25.10.2016 | 2012-13 | **\*** | **\*** | 0.00 | 1,322.62 | **\*** | **\*** | **\*** |
| 4 | Construction of Raj- Bhawan, Residence of Chief Minister and Cabinet Minister in Sector 24 and Sr. Officials Residential Building in Sector 18 of Nawa Raipur | 59,175.52  10.11.2018 | **\*** | **\*** | **\*** | 21,277.70 | 61,937.11 | **\*** | **\*** | **\*** |
| 5 | H.V.A.C system in Government Medical College Raigarh | 1,822.00  26.06.2018 | **\*** | **\*** | **\*** | 0.00 | 2,004.20 | **\*** | **\*** | **\*** |
| 6 | Rest House Construction in New Raipur | 2,399.56  28.03.2018 | **\*** | **\*** | **\*** | 182.32 | 1,813.77 | **\*** | **\*** | **\*** |

**APPENDIX - IX**

**COMMITMENTS OF THE GOVERNMENT- LIST OF INCOMPLETE CAPITAL WORKS- contd.**

**PUBLIC WORKS DEPARTMENT - contd. (₹in lakh)**

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl. No.** | **Name of the project/works** | **Estimated cost of work/date of sanction** | **Year of commen-cement** | **Target year of completion** | **Physical Progress of work (in percent) as on 31.03.24** | **Expendi-**  **ture during the year** | **Progressive expenditure to the end of the year** | **Pending payment** | **Revised cost, if any/date of revision** | |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** | |
| **BUILDINGS-contd.** | | | | | | | | | | |
| 7 | Construction of Special Jail Building for Prisoners with 1500 capacity in village Nagoi in Bilaspur District | 12,650.39  28.09.2021 | \* | \* | \* | 0.00 | 214.11 | \* | \* | \* |
| 8 | Construction of High- Level lab for upgradation of Sickle Cell Institute to Centre of Excellence | 4,811.96 | 2021-22 | 2025-26 | 3.34% | 123.26 | 214.28 | \* | \* | \* |
| 9 | Construction of new Vidhan-Sabha building at designated place in New Raipur Atal Nagar Sector-19 | 27,311.60  19.02.2021 | 2020-21 | \* | \* | 6,012.07 | 8,892.05 | \* | \* | \* |
| 10 | Construction of Gallery and flood light in the Hockey Field of the State Sports Training Centre, Bahtrai in Bilaspur | 1,595.86 | 2020-21 | \* | \* | 19.82 | 30.39 | \* | \* | \* |
| 11 | Construction of Auditorium in Divisional Headquarter-Bastar | 1,344.74  24.07.2017 | \* | \* | \* | 166.12 | 588.20 | \* | \* | \* |

**APPENDIX - IX**

**COMMITMENTS OF THE GOVERNMENT- LIST OF INCOMPLETE CAPITAL WORKS- contd.**

**PUBLIC WORKS DEPARTMENT - contd. (₹ in lakh)**

|  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl. No.** | **Name of the project/works** | **Estimated cost of work/ date of sanction** | | **Year of commen-cement** | **Target year of completion** | **Physical Progress of work (in percent) as on 31.03.24** | **Expendi-**  **ture during the year** | **Progressive expenditure to the end of the year** | **Pending payment** | **Revised cost, if any/date of revision** | |
| **1** | **2** | **3** | | **4** | **5** | **6** | **7** | **8** | **9** | **10** | |
| **BUILDINGS-concld.** | | | | | | | | | | | |
| 12 | Construction of Transit Hostel in Divisional Headquarter - Bastar | | 1,041.95  28.03.2018 | \* | \* | \* | 147.51 | 1,037.13 | \* | \* | \* |
| 13 | Construction of 12 Nos New Room and Conference Hall including Interior, Furnishing and Lift for Ministers in CG Vidhan Sabha area in Raipur District | | 1,033.33  08.12.2020 | \* | \* | \* | 186.32 | 1,025.38 | \* | \* | \* |
| 14 | Construction of Composite Building and Upgradation of Collectorate Building in Raipur District | | 2,753.06 | 2023-24 | 2026-27 | \* | 134.45 | 134.45 | \* | \* | \* |
| 15 | Construction of Resident Quarters and Hostels in Government Land awarded by Forest Department at the Government Medical College, Raipur | | 4,263.55  06.01.2020 | 2020-21 | 2023-24 | 47% | 1,133.34 | 1,903.63 | \* | \* | \* |
| **TOTAL – BUILDING** | | | **1,36,886.97** |  |  |  |  |  |  |  |  |

**APPENDIX - IX**

**COMMITMENTS OF THE GOVERNMENT- LIST OF INCOMPLETE CAPITAL WORKS- contd.**

**PUBLIC WORKS DEPARTMENT - contd. (₹ in lakh)**

|  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl. No.** | **Name of the project/works** | **Estimated cost of work/ date of sanction** | | **Year of commen-cement** | **Target year of completion** | **Physical Progress of work (in percent) as on 31.03.24** | **Expendi-**  **ture during the year** | **Progressive expenditure to the end of the year** | **Pending payment** | **Revised cost, if any/date of revision** | |
| **1** | **2** | **3** | | **4** | **5** | **6** | **7** | **8** | **9** | **10** | |
| **BRIDGES** | | | | | | | | | | | |
| 16 | Construction of Bridge on Mand River between Bangarsuta and Maharajganj | | 1,096.52  15.12.2010 | 2011-12 | 2023-24 | 70% | 115.34 | 939.30 | \* | \* | \* |
| 17 | Construction of Bridge on Shabri River of Nagar  Panchayat Konta to  Odisha approaching  Road of Sukma - 1/8 km | | 1,556.67  30.08.2012 | 2015-16 | 2023-24 | 90% | 384.85 | 2,646.91 | \* | 3,336.30 | 16.02.22 |
| 18 | Construction of Bridge from Debdand to Pandri - Magora on Budhra River in Korea | | 1,819.03  19.10.2020 | 2021-22 | 2023-24 | 97% | 143.75 | 1,266.28 | \* | \* | \* |
| 19 | Construction of Bridge on Indravati River near Bedre-Satva-Mangalnar of Satwa Village of Bhairamgadh Development Block in Bijapur District | | 3,792.22  26.03.2020 | 2018-19 | 2024-25 | 25% | 132.09 | 1,021.75 | \* | \* | \* |
| 20 | Construction of Bridge on Iragaon-arra-Bundi Road  in Kanker District | | 1,220.73  04.04.2018 | \* | \* | \* | 50.37 | 480.10 | \* | \* | \* |

**APPENDIX - IX**

**COMMITMENTS OF THE GOVERNMENT- LIST OF INCOMPLETE CAPITAL WORKS- contd.**

**PUBLIC WORKS DEPARTMENT - contd. (₹ in lakh)**

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl. No.** | **Name of the project/works** | **Estimated cost of work/ date of sanction** | **Year of commen-cement** | **Target year of completion** | **Physical Progress of work (in percent) as on 31.03.24** | **Expendi-**  **ture during the year** | **Progressive expenditure to the end of the year** | **Pending payment** | **Revised cost, if any/date of revision** | |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** | |
| **BRIDGES- contd.** | | | | | | | | | | |
| 21 | Construction of High- Level Bridge over Shakti Nala on the Lakhna Champaran Road at Raipur 5/6 Km | 1,099.44  10.02.2015 | 2021-22 | 2023-24 | **\*** | 324.72 | 343.92 | **\*** | \* | \* |
| 22 | Construction of Bridge on Howrah Mumbai Rail line in Durg District (839/23-25) (L.C. No. 429) | 2,108.50  12.07.2018 | 2019-20 | 2024-25 | **\*** | 0.00 | 0.42 | **\*** | **\*** | **\*** |
| 23 | Construction of Railway Over-Bridge near Howrah Mumbai Railway level crossing 313 Kharsia yard (km 605/13-15/) in Raigarh District | 5,936.27  06.01.2022 | \* | **\*** | **\*** | 0.00 | 661.53 | **\*** | **\*** | **\*** |
| 24 | Construction of High-Level Bridge on Bokraveda River in Kondagaon District | 1,429.69  08.11.2019 | \* | **\*** | **\*** | 2.77 | 122.83 | **\*** | **\*** | **\*** |

**APPENDIX - IX**

**COMMITMENTS OF THE GOVERNMENT- LIST OF INCOMPLETE CAPITAL WORKS- contd.**

**PUBLIC WORKS DEPARTMENT - contd. (₹ in lakh)**

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl. No.** | **Name of the project/works** | **Estimated cost of work/ date of sanction** | **Year of commen-cement** | **Target year of completion** | **Physical Progress of work (in percent) as on 31.03.24** | **Expendi-**  **ture during the year** | **Progressive expenditure to the end of the year** | **Pending payment** | **Revised cost, if any/date of revision** | |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** | |
| **BRIDGES- contd.** | | | | | | | | | | |
| 25 | Construction of Bridge on Semarghat River at Banskot (Keshkal Vikaskhand-Baderajpur) in Kondagaon District | 1,103.31  05.05.2020 | 2018-19 | **\*** | **\*** | 258.68 | 316.23 | **\*** | **\*** | **\*** |
| 26 | Construction of 120.00 Meter High-Level Bridge on Kernar Nala at Bhanupratappur-Pakhanjur-Bande PV109 Km 106/10 in Kanker District | 1,322.48  19.10.2020 | 2019-20 | **\*** | **\*** | 519.26 | 804.34 | **\*** | **\*** | **\*** |
| 27 | Construction of Causeway on Borkanala at Badedongar-Urdabeda-Kongud Road in Kondagaon District | 1,570.18  01.08.2018 | 2017-18 | \* | \* | 121.42 | 389.27 | \* | \* | **\*** |
| 28 | Construction of Railway Under Bridge on the LC No. 373 of Howrah-Mumbai Rail Route (734/25-27 km) near Bilha in Bilaspur District | 2,000.00 | \* | **\*** | **\*** | 991.14 | 991.14 | **\*** | **\*** | **\*** |

**APPENDIX - IX**

**COMMITMENTS OF THE GOVERNMENT- LIST OF INCOMPLETE CAPITAL WORKS- contd.**

**PUBLIC WORKS DEPARTMENT - contd. (₹ in lakh)**

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl. No.** | **Name of the project/works** | **Estimated cost of work/ date of sanction** | **Year of commen-cement** | **Target year of completion** | **Physical Progress of work (in percent) as on 31.03.24** | **Expendi-**  **ture during the year** | **Progressive expenditure to the end of the year** | **Pending payment** | **Revised cost, if any/date of revision** | |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** | |
| **BRIDGES- contd.** | | | | | | | | | | |
| 29 | Construction of Railway Under Bridge on Level Crossing No. BK-3 of Bilaspur-Katni Rail Route (724/9-11 km) near Ameri in Bilaspur District | 1,200.00 | \* | \* | \* | 576.03 | 576.03 | \* | \* | \* |
| 30 | Construction of High- Level Bridge on Indravati River from Bhairamgadh- Bodli to Bangoli Road - 8/8 km to 9/6 km | 3,169.64  31.03.2018 | 2018-19 | 2024-25 | 70% | 208.12 | 2,827.14 | \* | 4,096.98 | 12.07.22 |
| 31 | Construction Foot Over Bridge (Skywalk) on Main Roads of Raipur City in District Raipur | 4,908.89  08.03.2017 | \* | \* | \* | 0.00 | 3,658.10 | \* | \* | \* |
| 32 | Construction of Railway Over Bridge on Kachna-Khamhardih Road | 2,514.38 | \* | \* | \* | 454.98 | 454.98 | \* | \* | \* |
| 33 | Bridge construction on Kodki River from Gagoli to Kakni Road in Balrampur-Ramanujganj District | 1,011.92  19.07.2022 | \* | \* | \* | 489.31 | 489.31 | \* | \* | \* |

**APPENDIX - IX**

**COMMITMENTS OF THE GOVERNMENT- LIST OF INCOMPLETE CAPITAL WORKS- contd.**

**PUBLIC WORKS DEPARTMENT - contd. (₹ in lakh)**

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl. No.** | **Name of the project/works** | **Estimated cost of work/ date of sanction** | **Year of commen-cement** | **Target year of completion** | **Physical Progress of work (in percent) as on 31.03.24** | **Expendi-**  **ture during the year** | **Progressive expenditure to the end of the year** | **Pending payment** | **Revised cost, if any/date of revision** | |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** | |
| **BRIDGES- contd.** | | | | | | | | | | |
| 34 | Bridge Construction on Kanhar River from Ramchandrapur, Aniruddhpur Gaighat Road in Balrampur-Ramanujganj District | 1,520.10  30.09.2022 | 2023-24 | 2024-25 | 30% | 413.79 | 413.79 | \* | \* | \* |
| 35 | Construction of High- Level Bridge from Kumdoba to Argoti Road on Rehand River in Sarguja District | 1,440.18  10.06.2022 | 2022-23 | 2024-25 | 80% | 711.17 | 711.17 | \* | \* | \* |
| 36 | Bridge Construction on Rehand River from Bilaspur to Odgi accessed Road in Surajpur District | 1,046.58  28.09.2022 | 2023-24 | 2024-25 | 35% | 147.99 | 147.99 | \* | \* | \* |
| 37 | Construction of High- Level Bridge on -Tandula River from Kharra to Rouna Road in Balod District | 1,068.05  31.03.2023 | 2023-24 | 2024-25 | 5% | 75.78 | 75.78 | \* | \* | \* |

**APPENDIX - IX**

**COMMITMENTS OF THE GOVERNMENT- LIST OF INCOMPLETE CAPITAL WORKS- contd.**

**PUBLIC WORKS DEPARTMENT - contd. (₹ in lakh)**

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl. No.** | **Name of the project/works** | **Estimated cost of work/ date of sanction** | **Year of commen-cement** | **Target year of completion** | **Physical Progress of work (in percent) as on 31.03.24** | **Expendi-**  **ture during the year** | **Progressive expenditure to the end of the year** | **Pending payment** | **Revised cost, if any/date of revision** | |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** | |
| **BRIDGES- concld.** | | | | | | | | | | |
| 38 | Construction of High- Level Bridge across Shivnath River on Nagpura-Karela Road in Durg District | 1,902.94  05.11.2020 | 2022-23 | 2024-25 | 65% | 932.87 | 936.34 | \* | \* | \* |
| 39 | Construction of High-  Level Bridge across  Shivnath River on  Anjora -Changori-Bharda  Road in Durg District | 1,871.54  25.03.2021 | 2021-22 | 2024-25 | 90% | 556.70 | 1,466.27 | \* | \* | \* |
| 40 | Construction of High- Level Bridge across Shivnath River on Sagni Ghat to Silli Road in Durg District | 1,640.62  26.03.2020 | 2020-21 | 2024-25 | 85% | 67.22 | 786.65 | \* | \* | \* |
| 41 | Construction of High- Level Bridge across Shivnath River on Khelidih-Arasnara-Pathriya-Doma Road in Durg District | 1,581.71  26.03.2020 | 2020-21 | 2024-25 | 50% | 115.72 | 543.80 | \* | \* | \* |
| 42 | Construction of High- Level Bridge across Shivnath River on 1/4 km of Rudra-Dhiri Road in Durg District | 1,394.70  06.02.2020 | 2020-21 | 2024-25 | 65% | 0.00 | 649.96 | \* | \* | \* |
|  | **TOTAL – BRIDGES** | **52,326.29** |  |  |  |  |  |  |  |  |

**APPENDIX - IX**

**COMMITMENTS OF THE GOVERNMENT- LIST OF INCOMPLETE CAPITAL WORKS- contd.**

**PUBLIC WORKS DEPARTMENT - contd. (₹ in lakh)**

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl. No.** | **Name of the project/works** | **Estimated cost of work/ date of sanction** | **Year of commen-cement** | **Target year of completion** | **Physical Progress of work (in percent) as on 31.03.24** | **Expendi-**  **ture during the year** | **Progressive expenditure to the end of the year** | **Pending payment** | **Revised cost, if any/date of**  **revision** | |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** | |
| **ROAD WORKS** | | | | | | | | | | |
| 43 | Construction of Chand-khuri-Maro-Sambalpur-Nawagardh-Chirha-Umariya Road | 8,964.00  14.09.2012 | **\*** | **\*** | **\*** | 0.00 | 7,967.30 | **\*** | 12,854.00 | 09.03.17 |
| 44 | Construction of Ratanpur –Kota-Lormi-Pandariya-Mungeli Road | 17,207.00  06.10.2012 | **\*** | **\*** | **\*** | 0.00 | 12,513.32 | **\*** | 26,623.00 | 25.04.17 |
| 45 | Construction of Jayram-nagar-Masturi-Malhar-Jodhara -Lavan Road | 11,205.00  06.10.2012 | **\*** | **\*** | **\*** | 0.00 | 10,715.99 | **\*** | 16,888.00 | 29.12.16 |
| 46 | Construction of Nandghat- Bhatapara-Baloda Bazar-Kasdol-Gidhori Road | 22,300.00  17.08.2012 | **\*** | **\*** | **\*** | 0.00 | 24,368.25 | **\*** | 39,707.00 | 31.03.17 |
| 47 | Construction of Shivrinarayan-Birra-Champa Road | 10,409.00  06.10.2012 | **\*** | **\*** | **\*** | 0.00 | 10,445.38 | **\*** | 14,612.00 | 29.12.16 |
| 48 | Construction of Khairagarh-Dongargarh-Tumdibod Road | 10,917.00 14.09.2012 | **\*** | **\*** | **\*** | 0.00 | 7,887.36 | **\*** | 13,990.00 | 29.12.16 |
| 49 | Construction of Ring Road at Premnagar in Surajpur District | 4,356.88  20.09.2012 | 2013-14 | **\*** | **\*** | 0.00 | 3,924.20 | **\*** | 6,251.85 | 20.09.22 |

**APPENDIX – IX**

**COMMITMENTS OF THE GOVERNMENT- LIST OF INCOMPLETE CAPITAL WORKS- contd.**

**PUBLIC WORKS DEPARTMENT - contd. (₹ in lakh)**

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl. No.** | **Name of the project/works** | **Estimated cost of work/ date of sanction** | **Year of commen-cement** | **Target year of completion** | **Physical Progress of work (in percent) as on 31.03.24** | **Expendi-**  **ture during the year** | **Progressive expenditure to the end of the year** | **Pending payment** | **Revised cost, if any/date of revision** | |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** | |
| **ROAD WORKS- contd.** | | | | | | | | | | |
| 50 | Widening and Asphalting of Jashpur-Sanna Road | 1,765.76  24.08.2011 | **\*** | **\*** | **\*** | 0.00 | 1,702.19 | **\*** | **\*** | **\*** |
| 51 | Construction of Helipad at Balrampur | 1,362.32  24.09.2010 | **\*** | **\*** | **\*** | 0.00 | 1,496.39 | **\*** | **\*** | **\*** |
| 52 | Construction of Bijapur Bypass Road | 4,766.50  04.03.2014 | 2014-15 | \* | **\*** | 0.00 | 615.01 | \* | \* | \* |
| 53 | Construction of Katghora Bypass Road in District Korba - 15.00 km | 3,306.00  23.05.2014 | 2014-15 | \* | **\*** | 0.00 | 3,346.48 | **\*** | \* | \* |
| 54 | Widening/Strengthening of Gaurella-Karangra Road | 3,436.00  10.02.2015 | 2015-16 | \* | **\*** | 0.00 | 1,368.82 | \* | \* | \* |
| 55 | Widening and Strengthening of Chanti-Janakpur Road in District Korea – 8.00 km | 4,026.20  29.09.2015 | 2015-16 | \* | **\*** | 0.00 | 2,204.34 | **\*** | **\*** | **\*** |
| 56 | Construction of Beltukri-Putpura-Bundeli-Gidhwa Road of Nawagardh | 1,492.97  09.03.2015 | 2015-16 | \* | **\*** | 0.00 | 909.68 | **\*** | \* | \* |
| 57 | Construction of Kathakoni-Mudhpar Road - 15.00 km | 2,306.42  11.02.2014 | 2014-15 | \* | **\*** | 5.00 | 2,121.83 | **\*** | \* | \* |

**APPENDIX - IX**

**COMMITMENTS OF THE GOVERNMENT- LIST OF INCOMPLETE CAPITAL WORKS- contd.**

**PUBLIC WORKS DEPARTMENT - contd. (₹ in lakh)**

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl. No.** | **Name of the project/works** | **Estimated cost of work/ date of sanction** | **Year of commen-cement** | **Target year of completion** | **Physical Progress of work (in percent) as on 31.03.24** | **Expendi-**  **ture during the year** | **Progressive expenditure to the end of the year** | **Pending payment** | **Revised cost, if any/date of revision** | |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** | |
| **ROAD WORKS- contd.** | | | | | | | | | | |
| 58 | Construction of Road from Balod to Taraud Dehan Route (Balod  Bypass) - 10.80 km | 4,007.29  08.02.2016 | \* | \* | **\*** | 0.00 | 217.51 | **\*** | **\*** | **\*** |
| 59 | Upgradation of Saja-Somaikala-Chilfi- Bendarchi-Ranbirpur Route - 18 km | 2,409.28  30.03.2016 | \* | \* | **\*** | 44.41 | 1,409.83 | **\*** | **\*** | **\*** |
| 60 | Widening and  Upgradation of  Sondh- Rewe-Dewarbija Route in District Bemetara - 9 km | 4,315.25  14.06.2016 | \* | \* | **\*** | 128.58 | 2,899.25 | **\*** | **\*** | **\*** |
| 61 | Construction of Road of Pendra Bypass Route Bilaspur District – 14 km | 5,425.53  30.03.2016 | \* | \* | **\*** | 0.00 | 129.76 | \* | \* | \* |
| 62 | Construction of Darri to Geruwaghat Road at Katghora - 4.50 km | 1,899.49  06.04.2016 | 2017-18 | \* | **\*** | 1.99 | 1,430.69 | **\*** | **\*** | **\*** |
| 63 | Construction of Nangur- Netanar-Koleng Road  in District Bastar –  25.50 km | 4,321.64  25.05.2016 | \* | \* | **\*** | 225.00 | 4,483.78 | **\*** | **\*** | **\*** |

**APPENDIX - IX**

**COMMITMENTS OF THE GOVERNMENT- LIST OF INCOMPLETE CAPITAL WORKS- contd.**

**PUBLIC WORKS DEPARTMENT-contd. (₹ in lakh)**

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl. No.** | **Name of the project/works** | **Estimated cost of work/ date of sanction** | **Year of commen-cement** | **Target year of completion** | **Physical Progress of work (in percent) as on 31.03.24** | **Expendi-**  **ture during the year** | **Progressive expenditure to the end of the year** | **Pending payment** | **Revised cost, if any/date of revision** | |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** | |
| **ROAD WORKS- contd.** | | | | | | | | | | |
| 64 | Construction of Road from Jarahadand to Mundardand (Bakoi) in Sarguja District – 13 km | 2,736.76  10.05.2016 | \* | \* | \* | 42.14 | 2,754.84 | \* | \* | \* |
| 65 | Upgradation of Gharghora By-pass Road in Raigarh District - 6.50 km | 2,474.00  28.03.2018 | \* | \* | \* | 0.00 | 1,715.93 | \* | \* | \* |
| 66 | Upgradation of Pathalgaon Kapu Road in Raigarh District -10.50 km | 2,248.00  28.03.2018 | \* | \* | \* | 0.00 | 1,559.27 | \* | \* | \* |
| 67 | Upgradation and  Reconstruction work of Thelkadih- Durg Road -31.00 km | 11,639.00 06.08.2018 | 2019-20 | 2024-25 | 77% | 2,439.26 | 8,736.17 | \* | \* | \* |
| 68 | Upgradation and Reconstruction work of  Anda-Ranchirai-Jamgaon Road-33.60 km | 10,255.48  07.08.2018 | 2019-20 | 2024-25 | 79% | 1,270.15 | 6,196.08 | \* | \* | \* |
| 69 | Upgradation and Reconstruction work of  Chuikhdan-Udaipur-Bundeli Road -27.00 km | 11,073.00  07.08.2018 | 2019-20 | 2024-25 | 96% | 1,918.04 | 9,131.77 | \* | \* | \* |

**APPENDIX - IX**

**COMMITMENTS OF THE GOVERNMENT- LIST OF INCOMPLETE CAPITAL WORKS- contd.**

**PUBLIC WORKS DEPARTMENT - contd. (₹ in lakh)**

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl. No.** | **Name of the project/works** | **Estimated cost of work/ date of sanction** | **Year of commen-cement** | **Target year of completion** | **Physical Progress of work (in percent) as on 31.03.24** | **Expendi-**  **ture during the year** | **Progressive expenditure to the end of the year** | **Pending payment** | **Revised cost, if any/date of revision** | |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** | |
| **ROAD WORKS- contd.** | | | | | | | | | | |
| 70 | Upgradation and Reconstruction work of Ghotia-Palari-Batgan-Ghirpuri- Chikhli-Samoda- Acholi-Tumgaon Road – 40 km | 14,947.00  07.08.2018 | 2019-20 | 2021-22 | 89.84% | 2,383.22 | 15,795.03 | \* | \* | \* |
| 71 | Upgradation and Reconstruction work of Budeni-Nayapara-Paraswani-Magarlod-Mohandi- Borsi-Bhoyena Road | 28,239.00  07.08.2018 | 2019-20 | 2024-25 | 96.46% | 2,994.02 | 20,521.62 | \* | \* | \* |
| 72 | Upgradation and Reconstruction work of Rajim-Chura-Tarrighat Road - 45 km | 16,592.00  07.08.2018 | \* | \* | \* | 0.00 | 164.37 | \* | \* | \* |
| 73 | Upgradation and Reconstruction work of Panduka-Jamtai-Ghataarani- Gaidabri-Mandeli-Mudagaon Road – 40 km | 14,876.00  06.08.2018 | 2019-20 | 2021-22 | 59.09% | 1,503.32 | 8,127.39 | \* | \* | \* |

**APPENDIX – IX**

**COMMITMENTS OF THE GOVERNMENT- LIST OF INCOMPLETE CAPITAL WORKS- contd.**

**PUBLIC WORKS DEPARTMENT - contd. (₹ in lakh)**

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl. No.** | **Name of the project/works** | **Estimated cost of work /date of sanction** | **Year of commen-cement** | **Target year of completion** | **Physical Progress of work (in percent) as on 31.03.24** | **Expendi-**  **ture during the year** | **Progressive expenditure to the end of the year** | **Pending payment** | **Revised cost, if any/date of revision** | |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** | |
| **ROAD WORKS- contd.** | | | | | | | | | | |
| 74 | Upgradation and Reconstruction work of Mangala to Bhesarjaar Road – 26 km | 11,196.00  06.08.2018 | \* | \* | \* | 0.00 | 3,211.47 | \* | \* | \* |
| 75 | Upgradation and Reconstruction work of Purur-Phagunda-Palari-Arkaar-Jamgon  Road -35 km | 14,257.00 | 2019-20 | 2024-25 | 82% | 2,938.44 | 8,562.05 | \* | \* | \* |
| 76 | Widening and Strengthening of Road from Gadiraas Main Road to Nagaraas Sonakukanar Gorli in District Sukma - 16 km. | 1,437.96  13.11.2019 | 2020-21 | 2021-22 | \* | 7.98 | 1,249.98 | \* | \* | \* |
| 77 | Upgradation work of Shivrinarayan Road of Mulmula – Pamgarh in  Janjgir-Champa District - 26.70 km | 8,581.00 | \* | \* | \* | 0.00 | 10.59 | \* | \* | \* |
| 78 | Widening and Strengthening of Chandkhuri-Pacheda- Nardaha Four Lane Road in Raipur District – 10 km | 4,979.55  23.12.2021 | 2021-22 | \* | \* | 1,493.69 | 1,867.36 | \* | \* | \* |

**APPENDIX – IX**

**COMMITMENTS OF THE GOVERNMENT- LIST OF INCOMPLETE CAPITAL WORKS- contd.**

**PUBLIC WORKS DEPARTMENT - contd. (₹ in lakh)**

|  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl. No.** | **Name of the project/works** | **Estimated cost of work /date of sanction** | **Year of commen-cement** | | **Target year of completion** | **Physical Progress of work (in percent) as on 31.03.24** | **Expendi-**  **ture during the year** | **Progressive expenditure to the end of the year** | **Pending payment** | **Revised cost, if any/date of revision** | |
| **1** | **2** | **3** | **4** | | **5** | **6** | **7** | **8** | **9** | **10** | |
| **ROAD WORKS- contd.** | | | | | | | | | | | |
| 79 | Upgradation of Kunia to Narmadapur (Mainpat) Road in Sarguja  District – 7 km | 1,282.60  26.03.2020 | | **\*** | **\*** | **\*** | 100.12 | 459.16 | **\*** | **\*** | **\*** |
| 80 | Upgradation of Darhi Semriya Bansapur Karchuwa Road in Bemetara District – 5 km | 1,022.99  23.01.2023 | | **\*** | **\*** | **\*** | 144.33 | 1,002.21 | **\*** | **\*** | **\*** |
| 81 | Construction of Salhe to Bhotha Road with 18 pool-puliya and 4 Medium pools work in Kanker District – 16.50 km | 2,173.87  01.08.2018 | | **\*** | **\*** | **\*** | 0.00 | 830.45 | **\*** | **\*** | **\*** |
| 82 | Widening and Strengthening of 8.10 km Road from Nehru Nagar Chowk to Rajendra Nagar Park Ganjpara Minimata Chowk in Durg Town | 6,818.94  29.01.2020 | | 2020-21 | **\*** | **\*** | 217.93 | 638.13 | **\*** | **\*** | **\*** |
| 83 | Widening and Strengthening of 34 km Basantpur village to Basti- Bagra-Amgaon Road in Bilaspur District | 4,116.10  05.09.2020 | | 2020-21 | \* | \* | 1,742.77 | 4,248.49 | \* | \* | \* |

**APPENDIX – IX**

**COMMITMENTS OF THE GOVERNMENT- LIST OF INCOMPLETE CAPITAL WORKS- contd.**

**PUBLIC WORKS DEPARTMENT - contd. (₹ in lakh)**

|  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl. No.** | **Name of the project/works** | **Estimated cost of work /date of sanction** | **Year of commen-cement** | | **Target year of completion** | **Physical Progress of work (in percent) as on 31.03.24** | **Expendi-**  **ture during the year** | **Progressive expenditure to the end of the year** | **Pending payment** | **Revised cost, if any/date of revision** | |
| **1** | **2** | **3** | **4** | | **5** | **6** | **7** | **8** | **9** | **10** | |
| **ROAD WORKS- contd.** | | | | | | | | | | | |
| 84 | Widening and Strengthening of 5 km Basantpur-Navagaon- Bhadi Road with Pool Puliya in Bilaspur District | 1,136.46  05.09.2020 | | 2020-21 | \* | \* | 0.00 | 1,016.81 | \* | \* | \* |
| 85 | Chherkapur Chamari Road in Bemetara District - 5 km out of 13 km | 2,872.07  29.08.2018 | | \* | \* | \* | 778.63 | 1,689.65 | \* | \* | \* |
| 86 | Construction of Utai  By-pass Road in Durg District | 1,791.39  13.10.2020 | | 2020-21 | \* | \* | 1,143.15 | 1,188.92 | \* | \* | \* |
| 87 | Widening of National Highway passing through Kanker Town | 2,400.00 | | \* | \* | \* | 1,567.70 | 1,928.15 | \* | \* | \* |
| 88 | Construction of 10 Km Four-Lane Road from Khandoba Temple to Mahamaya Chawk, Ratanpur, Khuntaghat in Gaurela Pendra Marwahi District | 2,208.87  28.01.2022 | | 2022-23 | 2024-25 | 80% | 1,182.50 | 1,434.14 | \* | \* | \* |
| 89 | Upgradation of Durg Gunderdehi Road in Balod km 27 to 29 and  46 to 49 | 1,536.90 | | \* | \* | \* | 999.27 | 1,001.44 | \* | 1,550.48 | \* |

**APPENDIX – IX**

**COMMITMENTS OF THE GOVERNMENT- LIST OF INCOMPLETE CAPITAL WORKS- contd.**

**PUBLIC WORKS DEPARTMENT - contd. (₹ in lakh)**

|  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl. No.** | **Name of the project/works** | **Estimated cost of work /date of sanction** | **Year of commen-cement** | | **Target year of completion** | **Physical Progress of work (in percent) as on 31.03.24** | **Expendi-**  **ture during the year** | **Progressive expenditure to the end of the year** | **Pending payment** | **Revised cost, if any/date of revision** | |
| **1** | **2** | **3** | **4** | | **5** | **6** | **7** | **8** | **9** | **10** | |
| **ROAD WORKS- contd.** | | | | | | | | | | | |
| 90 | Upgradation and widening of 31 km Road from Jungera to Ajunda in Balod District | 4,989.70  27.04.2017 | | \* | \* | \* | 0.00 | 3,904.88 | \* | \* | \* |
| 91 | Strengthening and Widening of Manth-Tildadih Bithia Asounda Road - 11 km | 2,106.48 | | 2021-22 | \* | \* | 548.40 | 1,459.35 | \* | \* | \* |
| 92 | Upgradation of 10 km Pahanda-Bargaon-Khadmuda Road in Bemetera | 2,405.20 | | 03/2017 | \* | \* | 168.29 | 314.05 | \* | \* | \* |
| 93 | Construction of 40.52 km Selud-Jamgaon-Ranitarai-Patan Road in Raipur | 13,007.71 | | \* | \* | \* | 2,084.00 | 3,584.00 | \* | \* | \* |
| 94 | Construction of 39 Km Karsera-Khamhariya-Silhati Road in Raipur | 9,980.57 | | \* | \* | \* | 0.00 | 80.10 | \* | \* | \* |
| 95 | Construction of 28.07 Km Kawardha-Raipur-Khamhariya Road in Nava Raipur | 8,131.79 | | \* | \* | \* | 0.00 | 200.00 | \* | \* | \* |
| 96 | Construction of 35.50 km Pamgarh-Bhilouni-Sasaha-Sonsari Jodhra Lahod Road in Raipur District | 9,432.06  06.09.2016 | | \* | \* | \* | 0.00 | 1,356.00 | \* | \* | \* |

**APPENDIX – IX**

**COMMITMENTS OF THE GOVERNMENT- LIST OF INCOMPLETE CAPITAL WORKS- contd.**

**PUBLIC WORKS DEPARTMENT - contd. (₹ in lakh)**

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl. No.** | **Name of the project/works** | **Estimated cost of work /date of sanction** | **Year of commen-cement** | **Target year of completion** | **Physical Progress of work (in percent) as on 31.03.24** | **Expendi-**  **ture during the year** | **Progressive expenditure to the end of the year** | **Pending payment** | **Revised cost, if any/date of revision** | |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** | |
| **ROAD WORKS- contd.** | | | | | | | | | | |
| 97 | Construction of Indamara sukuldehan thelakdih Road - 20.02 km | 6,217.56  06.09.2016 | \* | \* | \* | 0.00 | 46.90 | \* | \* | \* |
| 98 | Construction of Shivrinarayan-Sarangarh Varamkela-Sohela  Road - 31.94 km | 10,047.93  06.09.2016 | \* | \* | \* | 0.00 | 900.00 | \* | \* | \* |
| 99 | Construction of Chilfi-Rengakhar-Salhewar Road - 60.81 km | 20,433.00  28.06.2017 | \* | \* | \* | 0.00 | 500.00 | \* | \* | \* |
| 100 | Up-gradation of Kapri Silwa Pathariya Pasia Rampur Lalpur Kharialin Bazar Road | 5,878.65  28.09.2022 | 11/2022 | 07/2024 | \* | 2,139.83 | 3,157.47 | \* | \* | \* |
| 101 | Widening and Strengthening of Road including Pool-puliya from Tundri-Madkadi to Alikud -Girwani via Soniadih in Baloda Bazaar - Bhatapara District - 15 km | 2,000.00 | \* | \* | \* | 51.18 | 143.76 | \* | \* | \* |
| 102 | Construction of Four Lane Road from Pulgaon Naka to Anjora in Durg District – 8 km | 5,639.39  26.03.2020 | 2018-19 | \* | \* | 58.63 | 325.34 | \* | \* | \* |

**APPENDIX – IX**

**COMMITMENTS OF THE GOVERNMENT- LIST OF INCOMPLETE CAPITAL WORKS- contd.**

**PUBLIC WORKS DEPARTMENT - contd. (₹ in lakh)**

|  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl. No.** | **Name of the project/works** | **Estimated cost of work /date of sanction** | **Year of commen-cement** | | **Target year of completion** | **Physical Progress of work (in percent) as on 31.03.24** | **Expendi-**  **ture during the year** | **Progressive expenditure to the end of the year** | **Pending payment** | **Revised cost, if any/date of revision** | |
| **1** | **2** | **3** | **4** | | **5** | **6** | **7** | **8** | **9** | **10** | |
| **ROAD WORKS- contd.** | | | | | | | | | | | |
| 103 | Strengthening and Widening of the NH Road in Bemetara Town of Bemetara District -  8 km | 3,011.49  24.10.2019 | | 2019-20 | \* | \* | 9.92 | 120.90 | \* | \* | \* |
| 104 | Upgradation and renewal of Pratappur Chandramedha Bhaiyathan road (Km 0 to 10 and 15 to 39/4= 34.40 kms) | 3,489.29  11.11.2022 | | 12/2022 | 04/2024 | \* | 1,557.33 | 2,710.58 | \* | 3,853.00 | \* |
| 105 | Construction of Four Lane Road of Mana-Dumartarai in Raipur | 2,453.69  29.04.2017 | | \* | \* | \* | 50.29 | 1,881.60 | \* | \* | **\*** |
| 106 | Construction of Four Lane Road on the canal of Kota-Hirapur Singh Road No. 2 in Raipur | 2,289.58  10.04.2018 | | \* | \* | \* | 82.00 | 1,273.40 | \* | \* | **\*** |
| 107 | Upgradation of 11.2 km Road from Chandkhuri to Khouli in Raipur | 3,283.33  30.03.2020 | | \* | \* | \* | 79.85 | 2912.09 | \* | \* | **\*** |

**APPENDIX – IX**

**COMMITMENTS OF THE GOVERNMENT- LIST OF INCOMPLETE CAPITAL WORKS- contd.**

**PUBLIC WORKS DEPARTMENT - contd. (₹ in lakh)**

|  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl. No.** | **Name of the project/works** | **Estimated cost of work /date of sanction** | **Year of commen-cement** | | **Target year of completion** | **Physical Progress of work (in percent) as on 31.03.24** | **Expendi-**  **ture during the year** | **Progressive expenditure to the end of the year** | **Pending payment** | **Revised cost, if any/date of revision** | |
| **1** | **2** | **3** | **4** | | **5** | **6** | **7** | **8** | **9** | **10** | |
| **ROAD WORKS- contd.** | | | | | | | | | | | |
| 108 | Widening of Road from Nagpura to Jawa Village in Raipur | 1,549.34  16.03.2018 | | \* | \* | \* | 13.18 | 1,152.16 | \* | \* | **\*** |
| 109 | Widening of Rasni-Koira-Farfoud-Fardaha Road in Raipur | 4,624.73  03.01.2018 | | \* | \* | \* | 40.91 | 4,041.73 | \* | \* | **\*** |
| 110 | Widening of Bhansoj-Jaroud-kalai Road in Raipur - 8 km | 1,826.10  01.08.2018 | | \* | \* | \* | 12.96 | 1,372.57 | \* | \* | **\*** |
| 111 | Construction of Road from Dongripali in Mahasamund to Jharmuda - 3 km | 1,078.65  28.03.2018 | | \* | \* | \* | 9.09 | 9.09 | \* | \* | **\*** |
| 112 | Upgradation of Road from Laripur in Mahasamund to Bahadurpur - 9 km | 1,097.20  28.03.2018 | | \* | \* | \* | 6.05 | 819.07 | \* | \* | **\*** |
| 113 | Construction of Road including Pool-puliya from Ghatula Main Road to Bhishampuri-Birnasilli CRPF Camp in Dhamtari District - 9.60 km | 1,257.36  25.01.2022 | | 2022-23 | 2024-25 | 70% | 419.74 | 453.74 | \* | \* | **\*** |

**APPENDIX – IX**

**COMMITMENTS OF THE GOVERNMENT- LIST OF INCOMPLETE CAPITAL WORKS- contd.**

**PUBLIC WORKS DEPARTMENT - contd. (₹ in lakh)**

|  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl. No.** | **Name of the project/works** | **Estimated cost of work /date of sanction** | **Year of commen-cement** | | **Target year of completion** | **Physical Progress of work (in percent) as on 31.03.24** | **Expendi-**  **ture during the year** | **Progressive expenditure to the end of the year** | **Pending payment** | **Revised cost, if any/date of revision** | |
| **1** | **2** | **3** | **4** | | **5** | **6** | **7** | **8** | **9** | **10** | |
| **ROAD WORKS- contd.** | | | | | | | | | | | |
| 114 | Widening and Strengthening of Bhakhara-Bagdehi-Dahi-Puri-Limtara-Demar Road in District  Dhamtari - 17.50 km | 3,500.00  15.03.2022 | | 2021-22 | 2024-25 | 45% | 681.25 | 772.88 | \* | \* | **\*** |
| 115 | Construction of Road from Village Khursul to reach Ganiyari Road - 4 km/5.22 km | 1,428.83  02.03.2023 | | 2022-23 | 2024-25 | 46% | 469.22 | 469.22 | \* | \* | **\*** |
| 116 | Construction of Rural Road from Chhata to Achanakpur in Durg District - 3.30 km | 1,107.92  06.04.2023 | | 2023-24 | 2024-25 | 25% | 253.46 | 253.46 | \* | \* | **\*** |
| 117 | Construction of Road from Chicha to Changori in Durg District - 3.60 km | 1,070.70  10.04.2023 | | 2023-24 | 2024-25 | 25% | 184.01 | 184.01 | \* | \* | **\*** |
| 118 | Construction of Parsahi - Sirri Road in Durg District - 4 km | 1,360.72  06.04.2023 | | 2023-24 | 2024-25 | 45% | 394.07 | 394.07 | \* | \* | **\*** |
| 119 | Construction and Upgradation of Road from Village Nikum to Ruda in Durg District - 3 km/ 3.50 km | 1,194.22  02.03.2023 | | 2022-23 | 2024-25 | 21% | 177.67 | 177.67 | \* | \* | **\*** |

**APPENDIX – IX**

**COMMITMENTS OF THE GOVERNMENT- LIST OF INCOMPLETE CAPITAL WORKS- contd.**

**PUBLIC WORKS DEPARTMENT - contd. (₹ in lakh)**

|  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl. No.** | **Name of the project/works** | **Estimated cost of work /date of sanction** | **Year of commen-cement** | | **Target year of completion** | **Physical Progress of work (in percent) as on 31.03.24** | **Expendi-**  **ture during the year** | **Progressive expenditure to the end of the year** | **Pending payment** | **Revised cost, if any/date of revision** | |
| **1** | **2** | **3** | **4** | | **5** | **6** | **7** | **8** | **9** | **10** | |
| **ROAD WORKS- contd.** | | | | | | | | | | | |
| 120 | Widening of Four Lane Road from Atmanand Chowk, Patan to Khorpa Marg - 1.80 km/ 1.90 km | 1,636.44  05.10.2021 | | 2021-22 | 2024-25 | 39% | 173.89 | 419.47 | \* | \* | **\*** |
| 121 | Widening and Upgradation of Anda-Chingri-Ulbaras Road in Durg District - 4 km | 1,206.88  29.09.2021 | | 2021-22 | 2024-25 | 59% | 485.06 | 570.46 | \* | \* | **\*** |
| 122 | Strengthening and Renewal of Rajnandgaon-Arjunda-Gunderdehi Road in Rajnandgaon District - 6/8 to 16/10 = 10.40 km | 1,618.95  06.07.2023 | | 2023-24 | 2024-25 | 10% | 212.36 | 212.36 | \* | \* | **\*** |
| 123 | Upgradation and Widening of Four Lane Road of Dongargaon Basti in Rajnandgaon District - 3.60 km | 1,866.86  19.10.2022 | | 2023-24 | 2024-25 | 40% | 207.37 | 207.37 | \* | \* | **\*** |
| 124 | Widening, Strengthening and upgradation of Road from Bodhghat Thana New Bus Stand - D.J. Court in Bastar - 2.90 km | 1,593.29  27.02.2018 | | \* | \* | \* | 150.69 | 1,435.84 | \* | \* | **\*** |

**APPENDIX – IX**

**COMMITMENTS OF THE GOVERNMENT- LIST OF INCOMPLETE CAPITAL WORKS- contd.**

**PUBLIC WORKS DEPARTMENT - contd. (₹ in lakh)**

|  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl. No.** | **Name of the project/works** | **Estimated cost of work /date of sanction** | **Year of commen-cement** | | **Target year of completion** | **Physical Progress of work (in percent) as on 31.03.24** | **Expendi-**  **ture during the year** | **Progressive expenditure to the end of the year** | **Pending payment** | **Revised cost, if any/date of revision** | |
| **1** | **2** | **3** | **4** | | **5** | **6** | **7** | **8** | **9** | **10** | |
| **ROAD WORKS- contd.** | | | | | | | | | | | |
| 125 | Construction of Road including Pool-puliya from Village Honhed to Matenga in Kondagaon District - 13 km | 2,455.57  13.01.2023 | | 2023 | 2025 | 30% | 488.31 | 488.31 | \* | \* | **\*** |
| 126 | Construction of Road including Pool-puliya from Village Mardapal-Medhpal Main Road to Village Hungwa via Changer in Kondagaon District - 12.90 km | 1,760.75  13.01.2023 | | 2023 | 2024 | 10% | 207.05 | 207.05 | \* | \* | **\*** |
| 127 | Construction of Road and Pool-puliya from Sonpur, Baderajpur to Batrupara, Khajrawand in Kondagaon District - 7.00 km | 1,115.22  13.01.2023 | | 2023 | 2024 | 30% | 278.21 | 278.21 | \* | \* | **\*** |
| 128 | Construction of Bypass Road in Kondagaon in Kondagaon District | 7,008.51  30.03.2016 | | \* | \* | \* | 1,128.42 | 1,734.43 | \* | \* | **\*** |
| 129 | Strengthening and Renovation of Bilaspur Sipat Road (19.40 km) 1/3 to 9/10 and 12/7 to 30/4 =15.30 km in Bilaspur District | 1,972.40  03.11.2022 | | \* | \* | \* | 1,897.97 | 1,977.87 | \* | \* | **\*** |

**APPENDIX – IX**

**COMMITMENTS OF THE GOVERNMENT- LIST OF INCOMPLETE CAPITAL WORKS- contd.**

**PUBLIC WORKS DEPARTMENT - contd. (₹ in lakh)**

|  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl. No.** | **Name of the project/works** | **Estimated cost of work /date of sanction** | **Year of commen-cement** | | **Target year of completion** | **Physical Progress of work (in percent) as on 31.03.24** | **Expendi-**  **ture during the year** | **Progressive expenditure to the end of the year** | **Pending payment** | **Revised cost, if any/date of revision** | |
| **1** | **2** | **3** | **4** | | **5** | **6** | **7** | **8** | **9** | **10** | |
| **ROAD WORKS- contd.** | | | | | | | | | | | |
| 130 | Construction of Road including Pool-puliya from Village Madwa- Tendubhata to Kamradi via Lachhanpur Village Chowk under Balouda Block in Janjgir-Champa District - 2 km | 1,615.36  30.03.2020 | | 2022-23 | \* | \* | 308.39 | 308.39 | \* | \* | **\*** |
| 131 | Strengthening of Janjgir - Kera - Shivrinarayan Road (19/2 km to 36/10 km) in Janjgir-Champa District - 18 km | 1,046.35  20.01.2023 | | \* | \* | \* | 1,006.15 | 1,006.15 | \* | \* | **\*** |
| 132 | Construction of Road including Pool-puliya from Jourela to Dhabadih by passing the Canal  in Janjgir-Champa  District - 9 km | 1,100.00 | | \* | \* | \* | 121.30 | 199.99 | \* | \* | **\*** |
| 133 | Construction of Kunkuri-Kaliba-Ranpur Road in Jashpur District - 18 km | 2,334.30  31.03.2016 | | 2017-18 | 2024-25 | 85% | 0.00 | 1,610.98 | \* | \* | **\*** |

**APPENDIX – IX**

**COMMITMENTS OF THE GOVERNMENT- LIST OF INCOMPLETE CAPITAL WORKS- contd.**

**PUBLIC WORKS DEPARTMENT - contd. (₹ in lakh)**

|  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl. No.** | **Name of the project/works** | **Estimated cost of work /date of sanction** | **Year of commen-cement** | | **Target year of completion** | **Physical Progress of work (in percent) as on 31.03.24** | **Expendi-**  **ture during the year** | **Progressive expenditure to the end of the year** | **Pending payment** | **Revised cost, if any/date of revision** | |
| **1** | **2** | **3** | **4** | | **5** | **6** | **7** | **8** | **9** | **10** | |
| **ROAD WORKS- contd.** | | | | | | | | | | | |
| 134 | Strengthening and Upgradation of Batouli-Bagicha-Charaidand and Kunkuri-Tapkara-Lawakera Road in Jashpur District - 21 km | 3,421.06 | | 2022-23 | 2024-25 | 52% | 1,747.22 | 1,938.02 | \* | \* | **\*** |
| 135 | Construction of Road from Harrapath to Sanna in Jashpur District - 9 km | 1,188.23  31.05.2022 | | 2023-24 | 2024-25 | 95% | 915.81 | 915.81 | \* | \* | **\*** |
| 136 | Construction of Sulesa-Burjudih Road including Pool-puliya in Jashpur District - 13 km | 1,270.75 | | 2023-24 | 2024-25 | 9% | 106.93 | 106.93 | \* | \* | **\*** |
| 137 | Construction of Road from Thakurtola to Lavatra including Pool-puliya in Rajnandgaon District - 9.50 km | 2,398.04  21.04.2022 | | 2023-24 | 2024-25 | 25% | 532.52 | 532.52 | \* | \* | **\*** |
| 138 | Construction of Lolesara-Dholiya-Bilai-Bhoinbhata-Piparbhattha-Chorbhatthi Road in Bemetera District- 10 km | 1,988.75  31.03.2018 | | \* | \* | \* | 2,693.01 | 2,693.01 | \* | \* | **\*** |
| 139 | Construction of Pratapgar-Gersa-Kerju Road in Sarguja District -39.40 km | 4,283.55  21.01.2022 | | \* | \* | \* | 2,857.47 | 2,857.47 | \* | \* | **\*** |

**APPENDIX – IX**

**COMMITMENTS OF THE GOVERNMENT- LIST OF INCOMPLETE CAPITAL WORKS- contd.**

**PUBLIC WORKS DEPARTMENT - contd. (₹ in lakh)**

|  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl. No.** | **Name of the project/works** | **Estimated cost of work /date of sanction** | **Year of commen-cement** | | **Target year of completion** | **Physical Progress of work (in percent) as on 31.03.24** | **Expendi-**  **ture during the year** | **Progressive expenditure to the end of the year** | **Pending payment** | **Revised cost, if any/date of revision** | |
| **1** | **2** | **3** | **4** | | **5** | **6** | **7** | **8** | **9** | **10** | |
| **ROAD WORKS- contd.** | | | | | | | | | | | |
| 140 | Strengthening and Widening of Bandarchua-Dokda-Farsabahar Main District Road in Jashpur District - 21.80 km | 4,906.19  01.10.2018 | | \* | \* | \* | 727.84 | 727.84 | \* | \* | **\*** |
| 141 | Construction of Paved Road and Pool from Matringa accessed Road to Pendrakhi in Sarguja District - 12 km | 1,641.74  31.05.2019 | | \* | \* | \* | 4.13 | 37.98 | \* | \* | **\*** |
| 142 | Strengthening of Ramanujganj Ring Road in District Balrampur-Ramanujganj - 6.60 km | 1,065.94 | | \* | 2024-25 | 16% | 135.74 | 135.74 | \* | \* | **\*** |
| 143 | Widening and Strengthening of Rajpur-Pratappur Road in District Balrampur-Ramanujganj - 29.60 km | 8,909.00 | | \* | 2024-25 | 38.27% | 2,702.20 | 2,702.20 | \* | \* | **\*** |
| 144 | Strengthening of Kusmi-Asta-Jashpur Road in District Balrampur-Ramanujganj - 16.60 km | 5,215.00 | | \* | 2024-25 | 89.75% | 3,035.99 | 3,035.99 | \* | \* | **\*** |

**APPENDIX – IX**

**COMMITMENTS OF THE GOVERNMENT- LIST OF INCOMPLETE CAPITAL WORKS- contd.**

**PUBLIC WORKS DEPARTMENT - contd. (₹ in lakh)**

|  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl. No.** | **Name of the project/works** | **Estimated cost of work /date of sanction** | **Year of commen-cement** | **Target year of completion** | **Physical Progress of work (in percent) as on 31.03.24** | **Expendi-**  **ture during the year** | **Progressive expenditure to the end of the year** | **Pending payment** | **Revised cost, if any/date of revision** | |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** | |
| **ROAD WORKS- contd.** | | | | | | | | | | |
| 145 | Construction of Road from Village Kamalpur to Chapeta in Balrampur-Ramanujganj  District - 9.31 km | 2,960.68 | \* | 2024-25 | 35% | 675.00 | 675.00 | \* | \* | **\*** |
| 146 | Construction of Bypass Road including Pool-puliya at Wadrafnagar in District Balrampur - 7 km | 2,080.95  31.03.2016 | \* | 2024-25 | 35% | 45.55 | 5,95.99 | \* | \* | **\*** |
| 147 | Construction of Fulidumar-Chera-Salwahi Road in Balrampur-Ramanujganj District - 20.60 km | 2,703.30  31.05.2022 | \* | 2024-25 | 40% | 888.53 | 888.53 | \* | \* | **\*** |
| 148 | Construction of Balrampur-Chando-Samri-Road (43 km to 49 km) in Balrampur-Ramanujganj District - 6 km | 3,045.25  22.09.2022 | \* | \* | \* | 4.80 | 4.80 | \* | \* | **\*** |
| 149 | Strengthening and Widening of Rohra-Ringni-Kesda-Biladi Road in Baloda Bazaar - Bhatapara District -26 km | 7,261.00 | \* | \* | \* | 1,260.57 | 1,260.57 | \* | \* | **\*** |

**APPENDIX – IX**

**COMMITMENTS OF THE GOVERNMENT- LIST OF INCOMPLETE CAPITAL WORKS- contd.**

**PUBLIC WORKS DEPARTMENT - contd. (₹ in lakh)**

|  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl. No.** | **Name of the project/works** | **Estimated cost of work /date of sanction** | **Year of commen-cement** | | **Target year of completion** | **Physical Progress of work (in percent) as on 31.03.24** | **Expendi-**  **ture during the year** | **Progressive expenditure to the end of the year** | **Pending payment** | **Revised cost, if any/date of revision** | |
| **1** | **2** | **3** | **4** | | **5** | **6** | **7** | **8** | **9** | **10** | |
| **ROAD WORKS- contd.** | | | | | | | | | | | |
| 150 | Construction of Road including Pool-puliya from Bodtara to Kukrachunda in Baloda Bazaar - Bhatapara District - 8 km | 2,139.17  31.05.2022 | | \* | \* | \* | 656.88 | 656.88 | \* | \* | **\*** |
| 151 | Widening of Road from Kudargadh Temple Chowk to the Gate of the Temple in Kudarhadh in Surajpur District | 3,129.50  05.01.2023 | | \* | \* | \* | 215.87 | 215.87 | \* | \* | **\*** |
| 152 | Construction of Road from Podi to Telaimuda via Tejpur (Urawnpara) in Surajpur District - 8 km | 1,245.31  16.12.2022 | | \* | \* | \* | 140.97 | 140.97 | \* | \* | **\*** |
| 153 | Upgradation and Widening of Salka-Ketka-Rajapur-Parshurampur-Ramanujnagar-Manja-Kudeli Road in Surajpur District - 36 km | 5,644.32  31.03.2022 | | \* | \* | \* | 198.27 | 198.27 | \* | \* | **\*** |

**APPENDIX – IX**

**COMMITMENTS OF THE GOVERNMENT- LIST OF INCOMPLETE CAPITAL WORKS- contd.**

**PUBLIC WORKS DEPARTMENT - contd. (₹ in lakh)**

|  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl. No.** | **Name of the project/works** | **Estimated cost of work /date of sanction** | **Year of commen-cement** | | **Target year of completion** | **Physical Progress of work (in percent) as on 31.03.24** | **Expendi-**  **ture during the year** | **Progressive expenditure to the end of the year** | **Pending payment** | **Revised cost, if any/date of revision** | |
| **1** | **2** | **3** | **4** | | **5** | **6** | **7** | **8** | **9** | **10** | |
| **ROAD WORKS- contd.** | | | | | | | | | | | |
| 154 | Widening and Renovating of Kamalpur to Podi-Devnagar approaching Road in Ramanujnagar Development Block  of Surajpur District -  14.10 km | 2,508.76  02.05.2022 | | \* | \* | \* | 152.90 | 152.90 | \* | \* | **\*** |
| 155 | Strengthening and BT Renovation work of Jhilmili (Bhaiyathan)-Surajpur-Udaipur Road in Surajpur District - 36 km | 3,182.37  29.09.2022 | | \* | \* | \* | 2,478.21 | 2,478.21 | \* | \* | **\*** |
| 156 | Strengthening and BT Renovation work of Tara-Premnagar-Ramanujnagar -Krishnapur Road in Surajpur  District - 12.60 km | 1,010.79  29.09.2022 | | \* | \* | \* | 755.99 | 755.99 | \* | \* | **\*** |
| 157 | Construction of 3/7 km of Pawra-Randhna Road to access Bridge on Borda River (Pawra River) in Kondagaon District | 1,280.62  07.04.2018 | | \* | \* | \* | 185.37 | 185.37 | \* | \* | **\*** |

**APPENDIX – IX**

**COMMITMENTS OF THE GOVERNMENT- LIST OF INCOMPLETE CAPITAL WORKS- concld.**

**PUBLIC WORKS DEPARTMENT - concld. (₹ in lakh)**

|  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl. No.** | **Name of the project/works** | **Estimated cost of work /date of sanction** | **Year of commen-cement** | | **Target year of completion** | **Physical Progress of work (in percent) as on 31.03.24** | **Expendi-**  **ture during the year** | **Progressive expenditure to the end of the year** | **Pending payment** | **Revised cost, if any/date of revision** | |
| **1** | **2** | **3** | **4** | | **5** | **6** | **7** | **8** | **9** | **10** | |
| **ROAD WORKS- concld.** | | | | | | | | | | | |
| 158 | Construction of High- Level Bridge along with Nala and Road Divider from Bakhrupara to Khadibahar in Narayanpur District | 1,347.93  29.09.2022 | | \* | \* | \* | 129.42 | 129.42 | \* | \* | **\*** |
| **TOTAL - ROAD WORKS** | | **5,53,170.75** | |  |  |  |  |  |  |  |  |