APPENDIX- IX

COMMITMENTS OF THE GOVERNMENT- LIST OF INCOMPLETE CAPITAL WORKS

Details of incomplete capital works costing ` 10 Crore and above

| Period | Irrigation |  | Building |  | Roads |  | Bridges |  | Other |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | No. of Works | Amount | No. of Works | Amount | No. of Works | Amount | No. of Works | Amount | No. of Works | Amount |
| Prior to 1995 | 03 | 8,964.23 | NIL | 0.00 | NIL | 0.00 | NIL | 0.00 | NIL | 0.00 |
| 1995 to 2000 | NIL | 0.00 | NIL | 0.00 | NIL | 0.00 | NIL | 0.00 | NIL | 0.00 |
| 2000 to 2005 | 05 | 33,923.23 | NIL | 0.00 | NIL | 0.00 | NIL | 0.00 | NIL | 0.00 |
| 2005 to 2010 | 30 | 1,39,447.93 | 02 | 15,160.84 | NIL | 0.00 | NIL | 0.00 | NIL | 0.00 |
| 2010 to 2015 | 58 | 3,09,301.98 | NIL | 0.00 | 14 | 1,03,794.85 | 02 | 2,653.19 | NIL | 0.00 |
| 2015 to 2020 | 31 | 82,437.60 | 07 | 71,569.93 | 51 | 2,97,066.50 | 10 | 22,816.88 | NIL | 0.00 |
| 2020 to 2024 | 19 | 68,123.22 | 06 | 50,156.20 | 51 | 1,52,309.40 | 15 | 26,856.22 | NIL | 0.00 |
| Total | 146 | 6,42,198.19 | 15 | 1,36,886.97 | 116 | 5,53,170.75 | 27 | 52,326.29 | NIL | 0.00 |

APPENDIX-IX

COMMITMENTS OF THE GOVERNMENT- LIST OF INCOMPLETE CAPITAL WORKS- contd.

WATER RESOURCES DEPARTMENT 												     (₹ in lakh)

| Sl. No. | Name of the project/works | Estimated cost of work / date of sanction | Year of commen-cement | Target year of completion | Physical Progress of work (in percent) as on 31.03.24 | Expendi- ture during the year | Progressive expenditure to the end of the year | Pending payment | Revised cost, if any/date of revision |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |
| 1 | Bhatapara Branch Canal - Sondur Project | 3,445.00 | 1982 | 2011-12 | * | 0.00 | 24,982.08 | * | 56,569.00 | * |
| 2 | Dudhawa Project (Dam Safety) | 1,122.59 | 2006 | 06/2011 | * | 0.00 | 1,961.65 | * | * | * |
| 3 | Dulna Anicut | 7,668.74 | 03/2008 | 03/2023 | * | 0.00 | 9,497.40 | * | 13,665.52 | * |
| 4 | Malanjhar Diversion | 1,118.96 | 2006 | 03/2023 | * | 0.00 | 4,214.96 | * | 4,965.10 | * |
| 5 | Lining work under the Pairy Project RBC - I | 5,308.78 07.07.2008 | 2010 | 03/2019 | * | 625.89 | 6,338.06 | * | * | * |
| 6 | Ghumariya Barrage | 4,778.86 | 2005 | 01/2021 | * | 0.00 | 5,337.92 | * | * | * |
| 7 | Khatutola Barrage | 4,765.33 23.10.2004 | 10/2006 | 08/2022 | * | 42.29 | 6,235.17 | * | 5,845.18 | * |
| 8 | Godhee Distributary | 250.00 | 2009 | 07/2016 | * | 0.00 | 2,105.41 | * | 2,391.00 | * |
| 9 | Lining of Right Bank Canal Kharkhara Nahar | 1,289.39 | 2008 | 06/2016 | * | 0.00 | 1,410.03 | * | 1,695.11 | * |
| 10 | Pairee Ghumar d/s | 1,527.00 | 2003 | 06/2023 | * | 14.71 | 3,544.97 | * | 2,958.20 4,617.87 | 31.03.1031.03.16 |
| 11 | Urmal Jalplawan Project | 4,268.23 | 1977 | 06/2023 | * | 0.00 | 6698.42 | * | 7,738.31 |  |
| 12 | Khutpali Diversion | 2,952.88 25.08.2007 | 08/2007 | 03/2022 | * | 0.00 | 9,922.29 | * | 8,646.85 15,738.09 | 20.03.14 |
| 13 | Katghora Diversion | 1,519.94 29.03.2007 | 02/2008 | 06/2024 | * | 27.98 | 5,498.70 | * | 5,607.66 | 30.11.14 |
| 14 | Champajhariya Diversion | 2,713.65 01.09.2007 | 02/2009 | 06/2023 | * | 0.00 | 919.86 | * | * | * |

* indicates information not available.

APPENDIX-IX

COMMITMENTS OF THE GOVERNMENT- LIST OF INCOMPLETE CAPITAL WORKS- contd.

WATER RESOURCES DEPARTMENT - contd.											     (₹ in lakh)

| Sl. No. | Name of the project/works | Estimated cost of work / date of sanction | Year of commen-cement | Target year of completion | Physical Progress of work (in percent) as on 31.03.24 | Expendi- ture during the year | Progressive expenditure to the end of the year | Pending payment | Revised cost, if any/date of revision |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |
| 15 | Rampur Tank | 1,800.82 28.04.2005 | 07/2008 | 03/2023 | * | 24.66 | 4274.14 | * | 8,340.45 | 29.03.16 |
| 16 | Salka Diversion | 4,723.22 16.03.2007 | 12/2007 | 03/2023 | * | 2.41 | 6,933.70 | * | 5,950.30 6,611.56 | * |
| 17 | Lachhanpur Diversion | 1,782.00 20.11.2007 | 01/2009 | 03/2023 | * | 0.00 | 4,093.54 | * | 4,933.22 | * |
| 18 | Lathnalla Diversion | 1,505.00 22.01.2007 | 2009 | 03/2017 | * | 0.00 | 4,318.86 | * | 3,858.43 | * |
| 19 | Lilagar Diversion | 3,620.24 14.08.2008 | 08/2008 | 08/2020 | * | 0.00 | 4,886.88 | * | 4,730.42 | * |
| 20 | Mand Anicut Ambetikara | 1,332.52 01.12.2005 | 05/2006 | 06/2018 | * | 0.00 | 704.29 | * | * | * |
| 21 | Remodeling and Lining work of Maniyari Canal | 10,666.00 29.08.2008 | 01/2009 | 06/2022 | * | 0.72 | 14,237.93 | * | 15,995.00 | 20.07.10 |
| 22 | Lining work of Maniyari Tank | 1,064.08 09.11.2016 | 06/2017 | 04/2023 | * | 0.00 | 703.80 | * | * | * |
| 23 | Maniyari Barrage | 1,921.00 13.07.2007 | 03/2008 | 03/2023 | * | 5.41 | 5,355.07 | * | 4,375.31 | 15.04.11 |
| 24 | Kenda Diversion | 835.00 29.08.2008 | 08/2008 | 03/2023 | * | 26.10 | 2,675.22 | * | 2,073.06 2,979.90 | * |
| 25 | Amamuda Diversion | 3,155.00 13.11.2009 | 11/2009 | 06/2023 | * | 84.82 | 4,008.17 | * | 3,841.79 | * |
| 26 | Rehar Diversion | 1,687.00 12.12.2007 | 02/2009 | 06/2018 | * | 0.00 | 4,848.96 | * | 2,706.09 | 16.07.09 |
| 27 | Kharun Diversion | 2,217.00 08.08.2009 | 08/2009 | 03/2017 | * | 0.00 | 3,003.55 | * | 3,499.65 | 13.07.17 |

APPENDIX-IX

COMMITMENTS OF THE GOVERNMENT- LIST OF INCOMPLETE CAPITAL WORKS- contd.

WATER RESOURCES DEPARTMENT - contd.											     (₹ in lakh)

| Sl.No. | Name of the project/works | Estimated cost of work / date of sanction | Year of commen-cement | Target year of completion | Physical Progress of work (in percent) as on 31.03.24 | Expendi- ture during the year | Progressive expenditure to the end of the year | Pending payment | Revised cost, if any/date of revision |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |
| 28 | Maini Anicut | 1,237.18 22.10.2007 | 01/2009 | 06/2021 | * | 0.00 | 3,340.22 | * | 2,750.61 | * |
| 29 | Mahadevghat Anicut | 1,175.44 | 08/2012 | 03/2022 | * | 0.00 | 809.84 | * | 1,276.50 | * |
| 30 | Loker Tank | 3,043.23 | 03/2014 | 06/2023 | * | 47.29 | 3,252.71 | * | * | * |
| 31 | Sheorinarayan Barrage | 11,644.64 08.10.2009 | 07/2011 | 04/2024 | * | 534.98 | 14,517.35 | * | 16,242.75 | 18.03.16 |
| 32 | Kelo Project Dam Safety | 9,850.00 | 07/2003 | 03/2013 | * | 0.00 | 28,607.60 | * | 59,891.00 | 25.07.09 |
| 33 | Saradih Barrage | 37,284.57 | 07/2012 | 06/2023 | * | 434.79 | 62,950.93 | * | 52,752.06 64,020.71 | * |
| 34 | Paraghat Diversion | 2,773.97 22.06.2011 | * | 03/2022 | * | 41.61 | 4,733.43 | * | 5,436.68 | 22.06.11 |
| 35 | Samoda Phase – I | 9,771.00 | 10/2002 | 06/2020 | * | 104.70 | 11,719.74 | * | * | * |
| 36 | Rengabod (kund) d/s | 1,690.10 | 12/2011 | 12/2022 | * | 0.00 | 2,247.99 | * | * | * |
| 37 | Arpa Bhaisajhar Project | 60,643.00 | 09/2013 | 03/2023 | * | 389.75 | 1,02,466.32 | * | 1,14,190.00 | 19.07.16 |
| 38 | Bagod Anicut | 2,100.00 | 05/2013 | 12/2017 | * | 0.00 | 3,787.36 | * | * | * |
| 39 | Sondur Project Dam Safety | 1,405.00 30.03.2013 | 03/2013 | 06/2021 | * | 0.00 | 1,620.39 | * | 1,411.31 | * |
| 40 | Geranala Tank | 1,481.05 31.03.2006 | 03/2006 | 06/2023 | * | 0.00 | 463.17 | * | * | * |
| 41 | Ratiza Anicut | 1,013.71 | 10/2011 | 03/2016 | * | 0.00 | 1,026.77 | * | 1,208.28 | * |
| 42 | Bharari Diversion | 3,998.17 | 03/2010 | 06/2022 | * | 2.51 | 6,973.84 | * | 7,212.17 | 03/2010 |
| 43 | Sahaspur Diversion | 1,265.59 23.12.2011 | 12/2012 | 06/2023 | * | 0.00 | 2,600.57 | * | 2,909.61 | * |
| 44 | Pathariya Barrage | 3,586.20 12.03.2012 | * | 03/2023 | * | 0.00 | 4,481.86 | * | * | * |
| 45 | Chhelanalla Diversion | 1,058.21 | 03/2013 | 06/2023 | * | 66.22 | 3,559.45 | * | 4,070.10 | * |

APPENDIX-IX

COMMITMENTS OF THE GOVERNMENT- LIST OF INCOMPLETE CAPITAL WORKS- contd.

WATER RESOURCES DEPARTMENT – contd.											     (₹ in lakh)

| Sl.No. | Name of the project/works | Estimated cost of work / date of sanction | Year of commen-cement | Target year of completion | Physical Progress of work (in percent) as on 31.03.24 | Expendi- ture during the year | Progressive expenditure to the end of the year | Pending payment | Revised cost, if any/date of revision |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |
| 46 | Mohra Anicut | 1,079.77 | 02/2012 | 12/2023 | * | 0.00 | 5,043.04 | * | 1,519.06 | * |
| 47 | Samoda Barrage | 15,920.00 | 02/2012 | 03/2020 | * | 0.00 | 11,657.79 | * | * | * |
| 48 | Sakalo Tank | 1,917.81 | 08/2011 | 06/2023 | * | 0.00 | 1,815.87 | * | * | * |
| 49 | Gagar feeder | 3,662.79 | 03/2012 | 06/2022 | * | 25.50 | 6,254.49 | * | 8,732.99 | * |
| 50 | Sapnai barrage Phase 1 | 4,974.37 31.03.2012 | * | 03/2020 | * | 174.53 | 3,940.09 | * | * | * |
| 51 | Chirmiri Tank | 1,377.81 30.03.2013 | 03/2013 | 03/2023 | * | 0.00 | 1,637.46 | * | 3,259.51 | * |
| 52 | Anjani Tank | 1,084.00 | 05/2013 | 6/2018 | * | 0.00 | 2,572.13 | * | 2,216.00 | * |
| 53 | Mohalai Diversion | 2,023.73 25.08.2011 | 09/2011 | 06/2023 | * | 0.00 | 45.59 | * | * | * |
| 54 | Kasahi Distributary | 2,483.11 07.01.2013 | 01/2013 | 03/2022 | * | 0.00 | 3,433.63 | * | 2,467.72 | * |
| 55 | Jonk Barrage | 3,512.59 | 2012 | * | * | 0.00 | 1,232.55 | * | * | * |
| 56 | Minimata Hasdeo Bango (E.R.M) | 49,231.00 | 04/2012 | * | * | 2,283.11 | 44,758.48 | * | * | * |
| 57 | Lawan Branch Canal | 9,000.00 | 03/2012 | 12/2020 | * | 0.00 | 6,955.24 | * | 7,235.44 | 2015-16 |
| 58 | Sapna Diversion | 1,204.42 | 02/2015 | 03/2021 | * | 0.00 | 1,575.60 | * | * | * |
| 59 | Shyam Ghunghutta Tank | 9,787.00 | 06/2019 | 06/2026 | * | 0.00 | 2,833.12 | * | * | * |
| 60 | Karoli Diversion | 1,314.70 | 10/2014 | 06/2021 | * | 0.00 | 1,544.55 |  | * | * |
| 61 | Lining work of Mahanadi canal of Dy. No. 5, 16 | 1,141.42 | 06/2016 | 06/2017 | * | 0.00 | 270.71 | * | * | * |
| 62 | Lining work of Mandhar Branch Canal 32-55 km | 3,355.16 13.03.2013 | * | 03/2023 | * | 0.00 | 2,442.44 | * | * | * |
| 63 | Lining works 49.20 – 99 km of Mahanadi Main Canal | 4,742.87 | 06/2016 | 06/2020 | * | 9.64 | 4,745.14 | * | * | * |

APPENDIX-IX

COMMITMENTS OF THE GOVERNMENT- LIST OF INCOMPLETE CAPITAL WORKS- contd.

WATER RESOURCES DEPARTMENT – contd.											     (₹ in lakh)

| Sl.No. | Name of the project/works | Estimated cost of work / date of sanction | Year of commen-cement | Target year of completion | Physical Progress of work (in percent) as on 31.03.24 | Expendi- ture during the year | Progressive expenditure to the end of the year | Pending payment | Revised cost, if any/date of revision |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |
| 64 | Lining and Structural works of Mahanadi Main Canal Distributary Branch No.17 | 1,348.13 | 06/2017 | 03/2023 | * | 112.22 | 1,482.47 | * | * | * |
| 65 | Renovation, Lining and Structural works of Mandhar Branch Canal, Distributary Branch No. 1,1A, 2A,3, 4 and 6 | 1,383.71 | 07/2016 | 03/2023 | * | 27.52 | 1,208.35 | * | * | * |
| 66 | Lining works of Mahanadi Main Canal Distributary Branch No. 21, 24, 25 | 2,418.62 | 06/2016 | 06/2019 | * | 0.00 | 1,863.98 | * | * | * |
| 67 | Remodeling of 22 Nos of Canal structure of Baloda Bazar Branch Canal | 1,013.74 | 10/2016 | 032021 | * | 29.36 | 906.60 | * | * | * |
| 68 | Lining and Remodeling works of Baloda Bazar Branch Canal | 7,887.65 | 12/2013 | 03/2020 | * | 36.69 | 8,993.64 | * | * | * |
| 69 | Baihamuda Barrage | 243.00 20.10.2014 | 10/2014 | 03/2023 | * | 10.65 | 4,041.74 | * | 2,876.22 | * |
| 70 | Renovation and Lining work of Distributary branch 19 of Mahanadi Main Canal | 1,154.97 | 10/2013 | 03/2023 | * | 0.00 | 678.65 | * | * | * |
| 71 | Renovation work of Railway Bridge No 64 at 83.35 km of Mahanadi Main Canal | 2,633.75 11.02.2015 | 02/2015 | 03/2021 | * | 0.00 | 3,260.25 | * | * | * |

APPENDIX-IX

COMMITMENTS OF THE GOVERNMENT- LIST OF INCOMPLETE CAPITAL WORKS- contd.

WATER RESOURCES DEPARTMENT – contd.											     (₹ in lakh)

| Sl.No. | Name of the project/works | Estimated cost of work / date of sanction | Year of commen-cement | Target year of completion | Physical Progress of work (in percent) as on 31.03.24 | Expendi- ture during the year | Progressive expenditure to the end of the year | Pending payment | Revised cost, if any/date of revision |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |
| 72 | Lining work of Distributary Canal No. 23 of Mahanadi Project | 2,851.10 19.09.2013 | * | 12/2020 | * | 0.00 | 1,600.96 | * | * | * |
| 73 | Lining works of Distributary-0-16 of Mandhar Branch Canal | 1,532.08 | 06/2016 | 06/2017 | * | 0.00 | 1,154.72 | * | * | * |
| 74 | Lining works of Distributary no. 10 of Mandhar Branch Canal | 1,227.53 19.09.2013 | 09/2013 | 03/2023 | * | 0.00 | 1,201.51 | * | * | * |
| 75 | Singbhal Tank | 2,231.78 | 2008 | 03/2023 | * | 0.00 | 3,778.40 | * | 3,668.25 | * |
| 76 | Koma Tank | 1,251.00 | 06/1980 | 06/2019 | * | 0.00 | 60.49 | * | 2,475.00 | * |
| 77 | Ratakhand Diversion | 1,500.00 19.02.2015 | 02/2015 | 06/2024 | * | 0.00 | 1,994.48 | * | 1,512.84 | * |
| 78 | Bhejipadar Diversion | 2,977.74 | 09/2014 | 03/2024 | * | 173.93 | 4,009.45 | * | * | * |
| 79 | Pairy Dam Safety (Sikasar) | 1,515.36 | 04/2013 | 06/2024 | * | 259.58 | 5,356.47 | * | 4,474.25 | * |
| 80 | Atem Diversion | 1,262.54 | 02/2015 | 06/2022 | * | 0.00 | 1,482.47 | * | * | * |
| 81 | Lengu Diversion | 1,325.00 | 09/2015 | 06/2021 | * | 0.00 | 2,265.65 | * | 1,802.74 | * |
| 82 | Belnalla Tank | 1,162.44 | 09/2015 | 06/2019 | * | 5.00 | 1,121.63 | * | 1,662.73 | * |
| 83 | Binganga Tank | 1,142.37 | 12/2012 | 06/2020 | * | 5.75 | 238.92 | * | * | * |
| 84 | Hudika Bandh Tank | 1,588.26 13.05.2014 | 6/2017 | 12/2018 | * | 0.00 | 1,744.43 | * | * | * |
| 85 | Chendra Tank | 1,063.14 | 01/2006 | 06/2023 | * | 0.00 | 3,941.95 | * | 1,150.01 | * |
| 86 | Murumsilly Dam | 1,110.80 | 02/2008 | 06/2020 | * | 0.00 | 660.05 | * | * | * |
| 87 | Sondur work | 6,357.40 08.12.2015 | 12/2015 | 06/2020 | * | 0.00 | 3,397.60 | * | * | * |

APPENDIX-IX

COMMITMENTS OF THE GOVERNMENT- LIST OF INCOMPLETE CAPITAL WORKS- contd.

WATER RESOURCES DEPARTMENT – contd.											     (₹ in lakh)

| Sl.No. | Name of the project/works | Estimated cost of work / date of sanction | Year of commen-cement | Target year of completion | Physical Progress of work (in percent) as on 31.03.24 | Expendi- ture during the year | Progressive expenditure to the end of the year | Pending payment | Revised cost, if any/date of revision |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |
| 88 | Sondur Project- Cement Concrete Lining work of Bhatapara Branch Canal and Distributary Canal | 63,574.00 | 2007 | 03/2023 | * | 0.00 | 1,189.03 | * | 29,725.00 | * |
| 89 | Balar Dam Project | 2,491.61 | 06/2015 | 06/2018 | * | 0.00 | 3,098.98 | * | 2,597.23 | * |
| 90 | Balamdehi Diversion | 1,326.67 | 05/2007 | 03/2023 | * | 248.21 | 411.72 | * | * | * |
| 91 | Mudiyadiha Anicut | 2,607.89 | 11/2014 | 06/2022 | * | 0.00 | 3,061.29 | * | * | * |
| 92 | Billa Nalla Tank | 2,000.00 | 06/2015 | 06/2019 | * | 28.07 | 2,272.25 | * | 2,441.39 | * |
| 93 | Mongra LBC Lining Work | 6,029.05 22.06.2015 | 06/2015 | 03/2019 | * | 0.00 | 5,657.15 | * | 4,600.68 5,592.21 | * |
| 94 | Dhudhichhua Tank | 1,353.94 | 12/2012 | 06/2020 | * | 0.00 | 552.78 | * | * | * |
| 95 | Rakeli Diversion | 1,163.26 | 12/2014 | 06/2020 | * | 0.00 | 1,355.41 | * | * | * |
| 96 | Dudhawa Sarona Canal Lining Works | 1,310.50 05.01.2013 | 01/2014 | 06/2021 | * | 127.56 | 6,745.04 | * | * | * |
| 97 | Naharnar Tank | 1,188.69 03.11.2011 | 03/2012 | 03/2023 | * | 18.01 | 1,159.26 | * | * | * |
| 98 | Renovation, Lining and Structure work between KM 10 to 45 of Bhatapara Branch Canal | 4,614.87 23.11.2015 | 11/2015 | 12/2022 | * | 66.70 | 4,084.36 | * | * | * |
| 99 | Sondur Project-Construction of remaining works of Bhatapara Canal | 4,053.00 27.02.2015 | 02/2015 | 03/2023 | * | 0.00 | 2,066.72 | * | * | * |

APPENDIX-IX

COMMITMENTS OF THE GOVERNMENT- LIST OF INCOMPLETE CAPITAL WORKS- contd.

WATER RESOURCES DEPARTMENT – contd.											     (₹ in lakh)

| Sl.No. | Name of the project/works | Estimated cost of work / date of sanction | Year of commen-cement | Target year of completion | Physical Progress of work (in percent) as on 31.03.24 | Expendi- ture during the year | Progressive expenditure to the end of the year | Pending payment | Revised cost, if any/date of revision |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |
| 100 | Sondur Project-Construction of concrete structure including Distributary system of 45-85 km of Bhatapara branch canal | 4,180.33 22.05.2014 | 05/2014 | 03/2023 | * | 0.00 | 3,003.75 | * | * | * |
| 101 | Singhor Diversion | 1,193.68 | 05/2013 | 10/2022 | * | 0.00 | 490.66 | * | * | * |
| 102 | Lower Jonk Barrage | 9,183.14 | 04/2014 | 03/2024 | * | 384.17 | 8,917.44 | * | * | * |
| 103 | Hemp Diversion Half Branch Canal Lining | 1,408.05 | 01/2016 | 12/2022 | * | 0.00 | 971.61 | * | * | * |
| 104 | Phonk Diversion Canal system Lining work | 2,000.73 | 01/2016 | 12/2023 | * | 0.00 | 1,404.71 | * | * | * |
| 105 | Remodeling and Lining work (0-36 km) of Jonk Diversion | 4,907.20 | 06/2015 | 06/2018 | * | 0.00 | 4,855.96 | * | * | * |
| 106 | Aturbeda Reservoir (Ravghat Project) | 4,634.07 | 02/2014 | 06/2023 | * | 0.00 | 825.28 | * | * | * |
| 107 | Remodeling and Lining work 54-69 km of Lawan Branch Canal of Mahanadi Project | 1,142.73 | 02/2015 | 03/2017 | * | 0.00 | 1,225.30 | * | * | * |
| 108 | Thuva (kuba) Diversion | 1,684.45 | 10/2014 | 12/2023 | * | 0.10 | 584.27 | * | * | * |
| 109 | Sildaha Diversion | 2,266.16 | 08/2010 | 03/2022 | * | 4.11 | 1,433.12 | * | * | * |
| 110 | Lining and Concrete work at Distributary and Minor Canal of Kosarteda Project | 1,454.53 25.03.2015 | 03/2015 | 06/2023 | * | 6.76 | 896.04 | * | * | * |

APPENDIX-IX

COMMITMENTS OF THE GOVERNMENT- LIST OF INCOMPLETE CAPITAL WORKS- contd.

WATER RESOURCES DEPARTMENT – contd.											     (₹ in lakh)

| Sl.No. | Name of the project/works | Estimated cost of work / date of sanction | Year of commen-cement | Target year of completion | Physical Progress of work (in percent) as on 31.03.24 | Expendi- ture during the year | Progressive expenditure to the end of the year | Pending payment | Revised cost, if any/date of revision |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |
| 111 | Remodeling & Lining -Kharkhara Mohandipat Canal Project 0-17 km | 4,975.00 05.12.2019 | 12/2019 | 06/2023 | * | 0.00 | 3,339.01 | * | * | * |
| 112 | Chhatreber Diversion | 1,748.56 | 03/2018 | 06/2021 | * | 1,309.22 | 2,818.01 | * | * | * |
| 113 | 29 Nos. Minors under Kharkhara Mohandipat Canal Project 0 - 17 km | 4,962.92 | 2021 | * | * | 547.65 | 1,522.20 | * | * | * |
| 114 | Rajiv Samoda Nisda Vyapwartan Dwitiya Charan Project | 11,445.00 18.08.2003 | 08/2003 | 03/2023 | * | 843.07 | 1,216.79 | * | * | * |
| 115 | Mahanadi Main Canal work of Lawan branch Remodeling cement concrete lining of Dy No. 3,4,5 and Kowadih Lawan Branch Canal | 2,985.02 07.03.2020 | 03/2020 | 06/2022 | * | 0.00 | 1,281.19 | * | * | * |
| 116 | Surhi LBC and RBC Remodeling and Lining | 1,826.23 23.12.2019 | 12/2019 | 03/2023 | * | 274.34 | 1,149.56 | * | * | * |
| 117 | Hemp Vyapwartan yojana LBC RD 16.50 -33.00 km Remodeling and Lining Work | 1,750.46 09.02.2015 | 02/2015 | 03/2023 | * | 147.38 | 1,479.47 | * | * | * |
| 118 | Canal extension of Hemp River d/s Dullipar (Kumardha) up to Bhalapur Tempri in Mungeli district | 1,619.20 17.05.2018 | 05/2018 | 03/2023 | * | 1.31 | 3.39 | * | * | * |

APPENDIX-IX

COMMITMENTS OF THE GOVERNMENT- LIST OF INCOMPLETE CAPITAL WORKS- contd.

WATER RESOURCES DEPARTMENT – contd.											     (₹ in lakh)

| Sl.No. | Name of the project/works | Estimated cost of work / date of sanction | Year of commen-cement | Target year of completion | Physical Progress of work (in percent) as on 31.03.24 | Expendi- ture during the year | Progressive expenditure to the end of the year | Pending payment | Revised cost, if any/date of revision |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |
| 119 | Chaple Anicut | 2,401.36 12.01.2023 | 2023 | 2025 | * | 999.99 | 1,017.48 | * | * | * |
| 120 | Susdega Diversion | 3,884.99 28.08.2015 | 08/2015 | 06/2023 | * | 198.51 | 379.28 | * | * | * |
| 121 | Darbekera Diversion | 7,313.97 10.02.2015 | 02/2015 | 03/2023 | * | 153.50 | 419.47 | * | * | * |
| 122 | Bermal Diversion | 1,156.57 12.05.2014 | 05/2014 | 06/2024 | * | 50.06 | 263.15 | * | 2,500.00 | * |
| 123 | Dharampur dam | 1,330.23 30.10.2002 | 10/2002 | 06/2019 | * | 0.00 | 5.00 | * | * | * |
| 124 | Lining work of Kodar canal Chingrod branch | 1,668.74 10.11.2017 | 11/2017 | 06/2022 | * | 0.00 | 29.99 | * | * | * |
| 125 | Kalipur d/s (18) | 1,007.87 19.02.2018 | 02/2018 | 06/2026 | * | 9.99 | 61.19 | * | * | * |
| 126 | Alga d/s (18) | 1,838.62 26.02.2018 | 02/2018 | 06/2026 | * | 0.00 | 296.09 | * | * | * |
| 127 | Sailapatpar d/s (21) | 1,134.90 | 05/2013 | 08/2022 | * | 19.76 | 29.51 | * | * | * |
| 128 | Salhe Anicut | 1,906.82 15.10.2018 | 10/2018 | 10/2020 | * | 13.73 | 1,245.58 | * | * | * |
| 129 | Kumhari Tank Augmentation | 2,044.45 03.10.2018 | 10/2018 | 12/2022 | * | 1,885.24 | 1,885.24 | * | * | * |
| 130 | Surhi Karra Diversion Phase – II (Dewargaon) | 1,174.92 27.07.2022 | 07/2022 | 01/2024 | * | 349.38 | 349.38 | * | * | * |
| 131 | Dotu Diversion | 3,718.56 12.11.2021 | 11/2021 | 12/2023 | * | 1,262.26 | 1,262.26 | * | * | * |
| 132 | Karuwa Diversion | 1,784.53 | 04/2022 | 07/2023 | * | 841.28 | 841.28 | * | * | * |

APPENDIX-IX

COMMITMENTS OF THE GOVERNMENT- LIST OF INCOMPLETE CAPITAL WORKS- contd.

WATER RESOURCES DEPARTMENT – concld.											     (₹ in lakh)

| Sl.No. | Name of the project/works | Estimated cost of work / date of sanction | Year of commen-cement | Target year of completion | Physical Progress of work (in percent) as on 31.03.24 | Expendi- ture during the year | Progressive expenditure to the end of the year | Pending payment | Revised cost, if any/date of revision |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |
| 133 | Siddhababa Tank | 22,007.19 09.03.2022 | 03/2022 | * | * | 2,175.07 | 2,175.07 | * | * | * |
| 134 | Pipariya Tank | 1,774.45 03.08.2022 | 08/2022 | * | * | 999.99 | 999.99 | * | * | * |
| 135 | Barbaspur Diversion | 1,292.15 27.07.2023 | 07/2023 | * | * | 394.09 | 394.09 | * | * | * |
| 136 | Amner Moti Nalla Diversion | 4,721.04 17.06.2020 | 06/2020 | 07/2024 | * | 99.94 | 99.94 | * | * | * |
| 137 | Ruse Reservoir | 1,432.45 22.03.2023 | 03/2023 | * | * | 484.82 | 484.82 | * | * | * |
| 138 | Karrekote Anicut | 2,040.88 | 2022 | 2026 | * | 0.09 | 0.09 | * | * | * |
| 139 | Barbadha Barrage | 1,954.74 27.07.2022 | 07/2022 | 2026 | * | 40.17 | 40.17 | * | * | * |
| 140 | Morgaon Tatbandh Nirman Work | 1,600.86 15.02.2018 | 02/2018 | 2025 | * | 1.96 | 1.96 | * | * | * |
| 141 | Remodeling and CC lining Work of RTE Distributary of Bhatapara Branch Canal - Sondur Project | 1,589.73 13.01.2023 | 09/2023 | 03/2025 | * | 548.06 | 548.06 | * | * | * |
| 142 | Re-sectioning and CC Lining Work of Datrengi Distributary and Semariya Minor Canal of Bhatapara Branch Canal of Sondur Project | 1,264.39 21.11.2022 | 08/2023 | 08/2024 | * | 94.54 | 94.54 | * | * | * |

APPENDIX-IX

COMMITMENTS OF THE GOVERNMENT- LIST OF INCOMPLETE CAPITAL WORKS- contd.

WATER RESOURCES DEPARTMENT – concld.											     (₹ in lakh)

| Sl.No. | Name of the project/works | Estimated cost of work / date of sanction | Year of commen-cement | Target year of completion | Physical Progress of work (in percent) as on 31.03.24 | Expendi- ture during the year | Progressive expenditure to the end of the year | Pending payment | Revised cost, if any/date of revision |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |  |
| 143 | Construction of Dhurrabandha Distributary of Bhatapara Branch Canal - Sondur Project | 1,548.28 24.03.2022 | 12/2023 | 03/2026 | * | 6.74 | 6.74 | * | * | * |
| 144 | Kharkhara Mohandipat Canal Project | 4,688.32 04.12.2021 | 12/2021 | 03/2024 | * | 3,109.58 | 3,501.91 | * | * | * |
| 145 | Lata Anicut | 4,316.10 29.03.2022 | 03/2023 | 10/2025 | * | 100.87 | 100.87 | * | * | * |
| 146 | Jonk Project – Chicholi | 2,466.19 25.03.2021 | 08/2023 | 06/2025 | * | 488.62 | 488.62 | * | * | * |
| TOTAL - WATER RESOURCES DEPARTMENT |  | 6,42,198.19 |  |  |  |  |  |  |  |  |