## APP_IX 2023_2024
APPENDIX IX
COMMITMENTS OF THE GOVERNMENT - LIST OF INCOMPLETE CAPITAL WORKS
(Includes Projects/Works the cost of which is ` 1 crore and above)
( ` in lakh)
Sl.No. | Name of Project/Work | Estimated Cost of Work/ Date of sanction |  | Year of commen-cement | Target year of completion | Physical progress of work (in per cent) | Expenditure during the year | Progressive expenditure to the end of the year | Pending payments | Revised cost if any/date of revision
Canals
1 | Construction of Sluice downstream of Chettuva bridge to prevent the entry of salt water through PC canal in Kadappuram Grama Panchayath
|  | 218.61 | 2.11.2018 | 2019 | 2020 | 64 | Nil | 146.96 | Nil | Nil
2 | PyIP Rectification work to damaged UT in Main Canal near Ch 32/500 km in Kuttiattoor Panchayath (!)
|  | 139 | 18.2.2020 | 2020 | 2022 | 95 | Nil | 79.7 | 55.29 | Nil
3 | Canal beautification - Cleaning,
construction of drain and beautification
of canal in Sea View Ward in Alappuzha
| Municipality in Alappuzha LA Constituency | 391.08 | 27.09.2019 | 2020 | 2022 | 70 | Nil | 283.93 | Nil | Nil
4 | Formation of Badagara Mahe Canal from
| Ch.464.210 km to 467.690 Km | 1993 | 06.01.2019 | 2020 | 2022 | 87 | 356.48 | 1128.86 | # | #
5 | IWT- Construction of a road bridge with
footpath across Badagara - Mahe canal
| at vengoli (!) | 2200 | 17.03.2017 | 2020 | 2022 | 98 | 271.08 | 1399.88 | # | #
(#) | Information not furnished by department
(!) | OB revised by the division
6 | Construction of Boat Jetty at Ozhayilbagam
in Dharmadam Grama Panchayath -
| Dharmadam LA constituency | 190 | 28.12.2020 | 2021 | 2023 | 60 | # | # | 81.73 | #
7 | Construction of Boat Jetty near
Mammakkunnu bridge in Kadambur Grama
| Panchayath - Dharmadam LA constituency | 190 | 28.12.2020 | 2021 | 2023 | 69 | 86.95 | 86.95 | 14.21 | #
8 | Construction of Boat Jetty near new bypass
Bridge at Kandikkal in Thalassery
| Municipality Thalassery LA Constitutnecy | 155 | 24.03.2020 | 2021 | 2023 | 76 | 41.77 | 41.77 | # | #
9 | Construction of Boat Jetty near Kaali
Park in Eranholi Gramapanchayath -
| Thalassery LA Constituency | 155 | 28.12.2020 | 2022 | 2023 | 85 | 79.08 | 79.08 | # | #
10 | Construction of Boat jetty Eranholi Bridge
in Thalasserry Muncipality. Thalasserry LA
| Consitituency | 155 | 18.03.2020 | 2021 | 2023 | 95 | 65.6 | 65.6 | # | #
11 | Reconstruction of Boat Jetty at
Valluvankadavu in Chirakkal panchayath
| General civil work | 120 | 23.07.2022 | 2022 | 2023 | 76 | 45.37 | 45.37 | # | #
(#) | Information not furnished by department
Anti Sea Erosion works
1 | Kuttanad Package - FMP -
Modernisation of Thaneermukkom
| Bund to manage salinity | 25533.5 | 22.10.2013 | 2014 | 2018 | 98 | Nil | 14216.19 | Nil | 1822.8
2 | KP Restoring Outer Bund of Kadannakkad
| padasekharam in NedumudyPanchayath | 296.1 | 25.07.2019 | 2019 | 2023 | # | # | 267.59 | # | #
3 | KP- Restoration of damaged outer bunds
Cherukalikayal padasekharam in kainakary
| Grama panchayath in Kuttanand LAC | 199.9 | 30.05.2020 | 2021 | 2022 | # | 18.98 | 191.27 | # | #
4 | Kp- Mitigation of flood in Manimalakkad
padaseharam ward no.5 of Champakulam
| panchayath | 130 | 17.06.2021 | 2021 | 2023 | # | 19.92 | 106.79 | # | #
(#) | Information not furnished by department
Irrigation Projects
1 | CDP- Design, Manufacture, supply
and erection of radial gates and hoisters
| for spillway ($) | 130 | # | 1991 | 1992 | 98 | Nil | 155.78 | Nil | Nil
2 | Construction of Regulator cum bridge
across Venniyode river at Malankara
| Parakkadave in Panamaram Panchayath | 800 | 28.11.2015 | 2018 | 2020 | 15 | Nil | 117.54 | Nil | Nil
3 | CSIND - Construction of Lock Bridge in
Ch.316.728 km of west cost canal at
Veliyamcode in Ponnani taluk in
| Malappuram DT | 2987 | 01.10.2019 | 2022 | 2024 | # | 389.93 | 829.69 | # | #
4 | Construction of Eranhiparambu LI
| scheme in Chathamangalam Panchayat | 160 | 28.06.2027 | 2022 | 2024 | # | # | 108.47 | # | #
5 | Rejuvination of Kachithode dam in
| Madakkathara PT | # | 12.02.2021 | 2022 | 2024 | # | 115.73 | 115.73 | # | #
6 | Rectification Work of RCB at | 3128 | 07.08.2020 | 2021 | 2024 | # | 202.17 | 1053.23 | # | #
Chamravattam across bharathapuzha
7 | Vellayani kayal Restoration Scheme | 9650 | 29.11.2021 | not started | 2025 | # | 150 | 150 | # | #
(#) | Information not furnished by department
($) | Reason for excess expenditure over estimated cost awaited from the Division
8 | MI Class 1, Construction of VCB Cum
Bridge at Pothullichira Vengad Across
Pothullithode in Moorkanad panchayath,
| Malappuram | 200 | 02.08.2021 | 2021 | 2021 | # | 22.59 | 138.71 | # | #
9 | Construction of SWE regulator on Upstream
of OLD Chithari SWE RCB Acrosss Chithari
| River in Kasargod | 3328 | 08.02.2023 | 2023 | 2025 | # | 472.84 | 472.84 | # | #
(#) | Information not furnished by department
($) | Reason for excess expenditure over estimated cost awaited from the Division
Buildings
1 | Construction of Multi storied
building for super specialities
| in Medical college, Kozhikode [@] | 356 | # | 1999 | 2006 | # | Nil | 1363.29 | 359.43 | 1285
2 | Construction of Administrative block
| for DIET, Kuruppampady | 162 | 15.2.2006 | 2006 | 2008 | 58 | Nil | 68.65 | Nil | 111.33
3 | State Central Library construction of
| Heritage Model Reference Block | 308 | 9.9.2010 | 2013 | 2016 | 90 | Nil | 256.98 | 82.31 | 339.29
4 | Government Medical College
Thiruvananthapuram - Renovation
and repair works of PG men's hostel
| and ladies hostel for under Graduate | 100 | 22.8.2014 | 2015 | 2016 | 85 | Nil | 63.17 | Nil | 95.38
5 | Construction of new building for
| PHC Maragnattupally | 450.78 | 1.8.2015 | 2016 | 2017 | 95 | Nil | 272.8 | 28.97 | 498.67
6 | Construction of Headquarters building
in the State Election Commission at
| Vikas Bhavan, Thiruvananthapuram | 1350 | 29.6.2015 | 2016 | 2018 | 100 | Nil | 754.64 | Nil | Nil
(#) | Information not furnished by department
(@) | Final bill not prepared for want of clearance from Vigilance Department
7 | Higher Education RIT Kottayam Construction
| of building for Architectural block | 1103 | 6.12.2013 | 2016 | 2018 | 90 | Nil | 947.36 | 247.75 | 1317.15
8 | Construction of building for GVHSS
| Thattakkuzha | 269.73 | 20.11.2014 | 2018 | 2019 | 95 | Nil | 153.53 | 43.21 | Nil
9 | H&FWD NABARD Assistance under
RIDF XX (2014-15) - Construction of
| Community Health Centre Paika | 1467.19 | 21.03.2015 | 2017 | 2019 | 100 | Nil | 1022.19 | Nil | 1286.82
10 | NABARD - RIDF XXI - Construction
of IP Block Phase II Taluk Head
| quarters Hospital, Thiruvalla | 906.2 | 15.2.2016 | 2018 | 2019 | 87 | Nil | 791.99 | Nil | Nil
11 | Govt. TDMCH Vandanam Alappuzha -
Construction of compound wall and
Development of land for setting up of
| Oncology Institutute (Phase 1) | 320 | 8.1.2019 | 2019 | 2020 | 88 | Nil | 255.1 | 9.6 | Nil
12 | Construction of flat type quarters
Type 1 (2 blocks each of 8 quartes) for
Government employees in NGO
| Quarters compound Kaithavana Alappuzha | 416 | 29.6.2018 | 2018 | 2020 | 95 | Nil | 342.58 | Nil | Nil
13 | Construction of new block for District
| PSC Office - Balance work | 249 | 17.9.2014 | 2019 | 2020 | 97 | Nil | 144.24 | 87.27 | Nil
14 | Modernisation of prisons 2017-18
Open Jail Chenmani construction of
| new Barrack for inmates | 308 | 19.7.2017 | 2018 | 2020 | 90 | Nil | 142.79 | 115 | 338.64
15 | Construction of 1st and 2nd floor to
new block building of Boys Hostel
| at Govt. College, Chittur | 500 | 28.4.2018 | 2019 | 2020 | 95 | Nil | 254 | 19.44 | Nil
16 | Construction of new building for Govt.
| Higher Sec. School, Kallingalpadam | 330 | 14.2.2017 | 2018 | 2020 | 95 | Nil | 166.8 | 52.94 | Nil
17 | DTE - Construction of Library,
Computer Lab and Conference Hall at
| Govt. Polytechnic College, Palakkad | 320 | 12.8.2016 | 2019 | 2020 | 90 | Nil | 164.52 | 36.05 | Nil
18 | NABARD - Infrastructure work for
additional building in Taluk Hospital
| Vythiri - Maternity Unit | 750 | 12.10.2017 | 2018 | 2020 | 40 | 303.53 | 516 | Nil | Nil
19 | NABARD - Infrastructure work for
additional building in Taluk Hospital
Sulthan Bathery - Women &
| Children Hospital | 2500 | 12.01.2017 | 2018 | 2020 | 35 | 1127.6 | 1906.46 | # | #
20 | NABARD - Construction of Multi
purpose Hospital Block at District
| Hospital, Mananthavady | 4500 | 15.2.2016 | 2018 | 2020 | 19 | 1563.38 | 3453 | Nil | 3359
(#) | Information not furnished by department
21 | Modernisation of administrative block
| and medical records library | 150 | 20.7.2018 | 2019 | 2020 | 80 | Nil | 67.36 | Nil | Nil
22 | Budget work 2017-18 - Construction of
| Excise Tower, Thrissur at Olari | 716 | 22.9.2017 | 2019 | 2020 | 80 | Nil | 228.6 | 360 | Nil
23 | Construction of flat type non-gazetted
officers quarters in Govt. Medical
| College Kozhikode | 3000 | 8.7.2015 | 2017 | 2020 | 60 | Nil | 1019.53 | 600 | Nil
24 | Construction of ground floor and 1st
| floor in CHC Palikal Phase II | 247 | 19.2.2019 | 2019 | 2020 | 95 | Nil | 196.94 | 56.23 | Nil
25 | Construction of new building for Coastel
Police headquarters at Kochi
| Willington Island | 330 | 31.3.2017 | 2018 | 2020 | 65 | Nil | 77.76 | Nil | Nil
26 | H&PWD 2018-19 - Major construction
works under DHS - Construction of a
building for Regional Public Health
Laboratory in Puduppariyaram
| Palakkad | 200 | 19.2.2019 | 2020 | 2020 | 95 | Nil | 58.61 | 27.31 | Nil
27 | LAC-ADS - 2015-16 - Construction of
school building for Kallai Govt. Ganapath
| Higher Secondary School in Kozhikode Dist. | 200 | 16.1.2016 | 2021 | 2021 | 30 | Nil | 29.4 | 15.61 | Nil
28 | Construction of additional floor to the
| A Block building, Dist. Court, Alappuzha | 250 | 27.6.2019 | 2019 | 2021 | 65 | Nil | 112.85 | Nil | Nil
29 | Construction of building for Govt. U.P.
| School, Kanakkanthuruthi | 268 | 3.8.2018 | 2020 | 2021 | 70 | Nil | 40.88 | 96.56 | Nil
30 | Construction of compound wall to
| Govt. College, Chittur | 200 | 1.5.2013 | 2020 | 2021 | 85 | Nil | 36.72 | 39.55 | Nil
31 | Annual plan 2019-20 - Construction of
school building for Govt. LP School,
| Maravancheri, Thavanur | 100 | 16.1.2020 | 2020 | 2021 | 90 | Nil | 84.28 | 5.26 | Nil
32 | Construction of retaining wall &
| compound wall in Govt. Polytechnic, Pala | 244.19 | 18.7.2017 | 2019 | 2021 | 85 | Nil | 107.92 | Nil | Nil
33 | Construction of new building, Govt. U.P.
| School, Panoorkara, Thrikkunnappuzha | 160 | 17.8.2020 | 2020 | 2022 | 70 | Nil | 44.12 | 22.87 | Nil
34 | Construction of new building for Sub
| Registra office, Pulincunnu, Alappuzha | 328 | 2.8.2019 | 2020 | 2022 | 44 | Nil | 135.14 | Nil | Nil
35 | NABARD - General Education Dept.
NABARD RIDF XXII - Infrastructure
works under RMSA, SSK - Construction
of new building for Govt. Girls High
| School, Chengannur | 200 | 16.4.2020 | 2021 | 2022 | 80 | Nil | 98.04 | 49.04 | Nil
36 | NABARD RIDF XXIII - Infrastructure
work under RMSA SSK - Construction
| of school building for Govt. LPS Kundayam | 171.26 | 18.2.2020 | 2021 | 2022 | 67 | Nil | 102.76 | 20 | Nil
37 | NABARD - General Education NABARD
\RIDF XXIII RMSASSA - Construction
| of new building for Govt. UPS Elampal | 171.56 | 18.12.2021 | 2021 | 2022 | 95 | NIL | 106.11 | 38.97 | Nil
38 | Construction of Higher Sec. block
building for Govt. SMHSS Thathamangalam
| Chittur | 230 | 23.6.2018 | 2021 | 2022 | 85 | Nil | 85.52 | 84.71 | Nil
39 | Construction of new warehouse for
storage of EVM and VVPT machines
| at Kannur | 596 | 16.5.2022 | 2020 | 2022 | 15 | Nil | 36.31 | Nil | Nil
40 | Construction of Library Block for Govt.
| Engineering College, Kannur | 1275 | 28.6.2018 | 2021 | 2022 | 30 | Nil | 315.48 | Nil | Nil
41 | Annual Plan 2017-18 - Construction of
| Govt. HSS Palayad New Building | 500 | 18.1.2018 | 2019 | 2022 | 60 | Nil | 278.31 | Nil | Nil
42 | Extension of Administrative block at
Govt. Polytechnic College for Women
| Kaimanam, Thiruvananthapuram Phase I | 300 | 2.4.2019 | 2021 | 2022 | 25 | Nil | 41.72 | 69.51 | Nil
43 | Construction of Residents' Quarters at
| Govt. Medical College, Manjeri | 300 | 13.9.2017 | 2020 | 2022 | 45 | Nil | 17.77 | Nil | Nil
44 | Construction of Laboratory Block &
Examination Hall at Govt. Polytechnic
| College, Kottayam | 374.58 | 12.8.2016 | 2021 | 2022 | 95 | Nil | 131.19 | 29.21 | Nil
45 | GED-NABARD RIDF XXIII -
Infrastructure works under RMSA, SSK -
Construction of new building for Govt.
| UP School, Panackachira (Phase I) | 169.53 | 18.2.2020 | 2021 | 2022 | 67 | Nil | 96.46 | 56.36 | Nil
46 | GED-NABARD RIDF XXIII -
Infrastructure works under RMSA, SSK -
Construction of new building for Kanjirappally
| Kunnumbhagam Govt. HS (Phase II) | 158.55 | 18.2.2020 | 2021 | 2022 | 46 | Nil | 102.41 | 5.08 | Nil
47 | General Education LAC ADS - Sri
Oommen Chandy - Puthuppally LAC
Construction of the new building for Govt.
| Vocational HSS THS Pampady | 300 | 28.6.2016 | 2021 | 2022 | 85 | Nil | 195.35 | Nil | Nil
48 | Construction of the new building for
Mechanical and Electrical Dept. in Govt
| Engineering College, Thalappuzha, Wayanad | 700 | 07.10.2015 | 2020 | 2023 | 66 | 319.83 | 471.29 | # | 637.25
49 | Construction of Gazzetted officers Quarters
| at Kalpetta | 321 | 27.11.2018 | 2021 | 2023 | 29 | # | # | # | #
50 | Annual Plan 2019-2020 Construction of
school building of Govt. HSS Meppadi
| Wayanad | 133 | 31.03.2020 | 2021 | 2023 | 99 | 50 | 50 | # | #
51 | Annual Plan 2019-2020 Construction of
chool building of Govt. HSS Edathana
| Manathavadi - Wayanad | 300 | 11.03.2020 | 2021 | 2023 | 98 | 143 | 143 | # | #
52 | Constrcution of Lab and library for GHSS
| Vythiri - Wayanad | 100 | 19.10.2019 | 2021 | 2024 | 99 | 17.69 | 17.69 | # | #
53 | Construction of Coompound wall for
| Govt. Technical HS Sulthan Bathery- Wayanad | 145 | 16.05.2022 | 2023 | 2024 | 99 | Nil | Nil | 64.44 | #
54 | Judicial Officers Quarters Kadavanthra
| I st Phase | 1049 | 22.03.2018 | 2020 | 2022 | 88 | 265.06 | 718.88 | # | #
55 | Construction of new building for Govt.
| LPS Cherai in Vypin LAC | 100 | 28.09.2017 | 2021 | 2022 | 80 | 18.98 | 63.18 | # | #
(#) | Information not furnished by Department
Bridges
1 | Construction of Vadapozhi bridge and
approaches connecting beach road in
Alappuzha town and
| coastal road in Punnapra ($) | 120 | # | 2010 | 2011 | 85 | # | 148.04 | # | #
2 | B/W 2009-10 Construction of
| Peyithuruth bridge across Chalakudy | 350 | 14.7.2009 | 2012 | # | # | # | 391.2 | # | #
river ($)
3 | B/W 2009-10 Old NH Venduruthy to
| BOT bridge | 290 | 6.7.2010 | 2012 | 2012 | # | # | 108.61 | # | #
4 | Champakulam Canal Jetty bridge
| (213/239)(CCII & part) | 1125 | 14.07.2009 | 2010 | 2012 | 95 | Nil | 794.34 | # | #
5 | Construction of Mithramadom Bridge
across Pamba river in Chengannur
| Mannar road in Alappuzha District | 985 | 02.03.2013 | 2014 | 2015 | 70 | # | 501.47 | Nil | Nil
6 | Construction of Eramallikkara Bridge
| across Manimalayar | 1006 | 16.12.2011 | 2013 | 2015 | 85 | # | 715.8 | Nil | Nil
7 | Construction of Mariyil Kalungu
| Bridge | 550 | 14.08.2009 | 2013 | 2014 | 95 | Nil | 356.67 | Nil | Nil
(#) | Information not furnished by Department
8 | Construction of Elookkara Uliyannoor
| bridge across Periyar river | 1250 | 20.11.2012 | 2013 | 2014 | 40 | Nil | 545.14 | Nil | Nil
9 | Reconstruction of Pavumba bridge
in Mannappally - Anayadi road
| Karunagappally constituency | 217 | 13.12.2012 | 2013 | 2014 | 60 | Nil | 107.72 | Nil | Nil
10 | Construction of Perandoor Bridge | 500 | 11.02.2014 | 2016 | 2016 | 15 | Nil | 41.8 | Nil | Nil
11 | Construction of Parallel bridge to
Kodimatha bridge across kodoor river
| in Kottayam district | 984 | 2013-05-03 | 2015 | 2016 | 60 | Nil | 570.15 | Nil | 1549
12 | Thuravoor Pamba road renovation
and construction of Thycattussery
Nerekadavu Bye Pass (Construction
| of bridge) | 9899 | 16.2.2012 | 2016 | 2017 | 60 | Nil | 5048.61 | Nil | Nil
13 | RIDF-XX Construction of Keezhumurykadavu
| bridge across Muvattupuzha river | 1630 | 30.12.2015 | 2017 | 2019 | 65 | Nil | 903.95 | Nil | Nil
14 | NABARD-RIDF - XXII - Construction
of Mambaram Bridge across Anjarakkandy
river at Km 11/350 of Chovva Kuthuparamba
| road in Kannur District | 1340 | 23.11.2016 | 2018 | 2019 | 47 | Nil | 624.59 | Nil | Nil
(#) | Information not furnished by Department
15 | Construction of Irinavu bridge on
Payyattam Irinavu Madakkara road in
| Kannur District | 1645 | 4.3.2016 | 2018 | 2019 | 70 | Nil | 1149.7 | Nil | Nil
16 | Reconstruction of Ponnara Bridge
| across TS Canal in Thiruvananthapuram | 1480 | 5.8.2017 | 2017 | 2019 | 28 | Nil | 409.61 | Nil | Nil
17 | NABARD RIDF XII - Construction of
Alex Nagar Kanhileri Bridge across
| Valapattanam river in Kannur District | 1010 | 23.11.2016 | 2018 | 2020 | 20 | Nil | 192.49 | # | #
18 | Special sanction 2017-18 Construction
of Enathi Bridge across Karimpuzha
| river in Malappuram District | 1093 | 13.4.2018 | 2018 | 2020 | 20 | Nil | 198.58 | # | #
19 | Budget Work 2015-16 - Reconstruction
of Nedungad Nayarambalam Bridge in
| North Paravur Constitutency | 650 | 22.12.2015 | 2016 | 2020 | 55 | Nil | 334.48 | # | #
20 | Reconstruction of Valicode Bridge
| across Killi river in Thiruvananthapuram | 600 | 31.3.2018 | 2018 | 2020 | 43 | Nil | 260.54 | # | #
21 | Construction of Aalam Bridge across
| Biyyam Kayal in Malappuram District | 555 | 22.12.2017 | 2018 | 2020 | 35 | Nil | 169.66 | 97.3 | Nil
22 | Construction of Ullorkkadavu bridge
| across Akalapuzha in Kozhikode Dist. | 1625 | 23.12.2020 | 2021 | 2022 | 20 | 576.63 | 829.34 | Nil | Nil
(#) | Information not furnished by Department
23 | Thycherythodu bridge at Ch 2/400 of AC
road Karumady Vilakkumaram road in
| Alappuzha Dist. | 473 | 26.2.2021 | 2021 | 2022 | 90 | Nil | 178.02 | 171.64 | Nil
24 | Construction of Attakulam bridge in
Thiruvalla Constituency in
| Pathanamthitta Dist | 166.1 | 19.2.2021 | 2021 | 2022 | 95 | Nil | 27.53 | 112.58 | Nil
25 | NABARD RIDF XXI - Construction of
Keezhmurikadavu bridge across
| Muvattupuzha river in Ernakulam District | 1630 | 30.12.2015 | 2017 | 2020 | 20 | Nil | 252.71 | Nil | Nil
26 | Construction of Thottathankandy Bridge
across kuttiadipuzha Connceting chanraoth
| GP and Maruthonkara GP | 920 | 2021-12-13 | 2021 | 2023 | # | 155.62 | 310.98 | # | #
27 | Construction of Parakkadavath Bridge
Connceting velom & Changaroth Across
| Cherupuzha | 770 | 2022-01-28 | 2022 | 2023 | # | 146.66 | 315.23 | # | #
28 | Reconstruction of Chembukavu Bridge
| Across Chalipuzha in Kozhikode District | 785 | 2020-11-06 | 2021 | 2023 | # | 113.63 | 582.17 | # | #
29 | Construction of Pulikkattukadavu Bridge
| Across kabani river of Valadi in Waynad | 1263 | 2019-12-11 | 2021 | 2023 | # | 201.36 | 385.39 | # | #
(#) | Information not furnished by Department
30 | Construction of Cheekkalloor bridge approach
road from CH 0/000 to 1/000 Km at
| kaniyambatta grama panchayath in kalpetta | 675 | 2020-01-13 | 2020 | 2022 | # | 490.02 | 1419.13 | # | #
31 | reconstruction of kalleri Chettikadavu Bridge
| Across Cherupuzzha in Kozhikode | 1100 | 2020-11-06 | 2021 | 2023 | # | 743.01 | 743.01 | # | #
32 | Budget 2017-2018 Reconstruction of kolad
| Bridge in Kannur District balance Work | 1360 | 2019-11-04 | 2022 | 2023 | # | 345.2 | 492.8 | # | #
33 | Construction of keezhathoor Bridge Aacross
| Anjarakkandy River in Kannur | 1210 | 2019-10-10 | 2022 | 2024 | # | 194 | 194 | # | #
34 | Construction of New Bridge at
| Vannathikadavu Across vannathipuzha in Kannur | 849.23 | 2019-11-21 | 2019 | 2022 | # | 268.9 | 789.5 | # | #
35 | Reconstruction of Karuvanchal Bridge in
| KM 20/000 of Taliparamba -Coorg Bordeer road | 680 | 2022-10-24 | 2022 | 2024 | # | 170.7 | 170.7 | # | #
36 | Construction of alexnagar Kanhileri Bridge
| Across valapattanam River in Kannur | 1010 | 2016-11-23 | 2022 | 2023 | # | 548 | 934.8 | # | #
37 | Construction of Aramanappady Bridge
across Payaswini River on Perladukam-
| bavikkaara Road in Kasargod | 643.25 | 2021-01-04 | 2022 | 2024 | # | 108 | 108 | # | #
(#) | Information not furnished by Department
38 | Construction of bund Palam kanam puzha
| in Kannur | 330 | 2019-12-27 | 2020 | 2022 | 60 | 15.1 | 205 | # | #
39 | Reconstruction of kunhithottam bridge
| in Kannur | 300 | 2021-08-13 | 2022 | 2023 | # | 133.5 | 133.5 | 2.1845 | #
40 | Construction of poomangalam Kodiery Bridge
| Across karimbam River in Kannur | 400 | 2021-01-19 | 2022 | 2023 | # | 117.6 | 117.6 | # | #
41 | Improvements to Oduvilathattu Naduvil
Kudiyanmala road from Km 0/000 to 18/000
| in Kannur | 2724.6 | 2016-02-25 | 2017 | 2023 | # | 233.1 | 1737.63 | # | #
42 | Construction of Thannimude bridge in
Nedumkandam-Cumbamettu Road
| Udumbanchola | 220 | 2022-06-30 | 2022 | 2024 | 99 | 140.7993 | 163.94 | # | 220
43 | Improvements to kavumannam -madakkunnu
| bankunnu Road Km 0/000 to 12/000 in Waynad | 1500 | 2022-07-20 | 2023 | 2024 | # | 723.4 | 723.4 | # | #
44 | Improvement to Chennalode -Oottupura Road
| km 0/000 to 12/325 in Waynad | 1500 | 2022-07-20 | 2023 | 2025 | # | 462.3 | 462.3 | # | #
45 | Improvements to Odayanchal -Edathida-
| vellarikkundu-cherupuzha Road in Kasargode | 1000 | 2022-07-20 | 2023 | 2025 | # | 193 | 193 | # | #
(#) | Information not furnished by Department
46 | Improvements to Ponnurkkakiparara
| Madamthattu Road in Kannur | 1990 | 2022-07-20 | 2023 | 2024 | # | 699.9 | 699.9 | # | #
47 | Improvements to 6th Mile-Panunda Artech-
Olayikkara -Pachapoyka -kavalode Kuttichal
madam-Kuzhipidika powerloom-motta-
| Arathikavyu Road in Kannur | 2640 | 2022-07-20 | 2023 | 2025 | # | 691.5 | 691.5 | # | #
48 | Construction of Korankadavu bridge across
| Muvattupuzha river in ernakulam district- work | 1430 | 2019-06-07 | 2020 | 2025 | # | 140.3 | 620.7 | # | #
49 | construction of Convent Beach Bridge
Connecting Convent Junction and Beach road
| at Pallippuram in Ernakulam | 2446.18 | 2018-12-19 | 2019 | 2025 | 78 | 179.9 | 1470.1 | # | #
50 | Reconstruction of nedungad Nayarambalam
| Bridge in North paravoor | 650 | 2015-12-22 | 2016 | 2020 | 95 | 70.42 | 405.09 | 63.45 | #
51 | Construction of keezhmudikadavu Bridge | 1630 | 2015-12-30 | 2017 | 2020 | 92 | 387.35 | 387.35 | # | #
Across Muvattupuzha River in Ernakulam
52 | Improvement and providing BM and BC in
Kuttiady Mullankunne Passukadave Road in
| between Km) /000 and 13/000 | 1670 | 2019-12-21 | 2019 | 2020 | 95 | 16.91 | 1502.53 | # | #
53 | Construction of kattikkunnathuruthel bridge
| Across Murinja puzha River in Kottyam | 860 | 2020-12-31 | 2022 | 2024 | 85 | 10.41 | 583.936 | 624 | #
(#) | Information not furnished by Department
54 | Construction of Company Kadavu bridge
and approach Across Meenachil River in
| Kottyam | 1000 | 2020-01-04 | 2022 | 2024 | 40 | 54.57 | 115.512 | 96 | 1090
55 | Construction of Cheruvally Bridge in
| kanjirappilly Constituency in Kottayam | 961 | 2022-07-10 | 2024 | 2025 | Nil | Nil | Nil | # | #
(#) | Information not furnished by Department
Roads
1 | Improvements to Monkombu
Kavalam vikas marg Pulincunnu
| Market road from ch 08/050 to ch9/440 | 180 | 14.8.2009 | 2010 | 2011 | 67 | Nil | 161.13 | # | #
2 | Improvements to Madayi TB Muttom
Palacode Ettikulam High school road 1st reach
| reach km.0/00 to 5/595 (!) | 552 | 20.6.2010 | # | # | 69.86 | Nil | 1021.88 | # | #
3 | Improvements to Iritty Ulikkal Mattara
road providing BM &BC from km
| 0/000 to 10/250 ($) (!) | 425 | # | 2011 | 2011 | # | Nil | 748.88 | # | #
4 | Improvements to Peppathppara road
Providing BM&BC Construction of drain
| and retaining wall ($) | 168 | 14.7.2009 | 2010 | 2011 | # | Nil | 294.56 | # | #
5 | B/W 2011-12 Widening and
| improvements to Aluva Alangad road | 100 | 9.11.2011 | 2012 | 2013 | # | Nil | 44.44 | # | #
6 | Approach road to Iranavu bridge | 300 | # | 2010 | 2010 | 70 | Nil | 87.9 | # | #
7 | Improvements to Panur town Menapram
| Pookod road (SH38) km 5/100 to 6/00 (!) | 137.5 | # | 2011 | 2013 | # | Nil | 184.02 | # | #
(#) | Information not furnished by Department
($) | Reason for excess expenditure made over Estimated Cost/Revised Cost of the work is awaited from the Division
8 | Construction of 4 lane road from Ulloor
| NH By-pass at Kuzhivila | 1875.79 | 9.4.2010 | 2011 | 2012 | 60 | Nil | 1503.01 | # | #
9 | Improvements to Vithura - Peppara Road | 758.31 | 16.2.2012 | 2012 | 2013 | 90 | Nil | 552.21 | # | #
10 | Improvements to Chingavanam - Kollad
| Kanjikuzhy Bye pass road | 1250 | 23.2.2012 | 2013 | 2014 | 90 | Nil | 1212.89 | # | #
11 | Improvements to Charummoodu
Ayyappankuzhy road from Km 0/000
| to 5/000 | 590 | 27.3.2013 | 2014 | 2015 | 35 | # | 566.71 | # | #
12 | Improvements to Kaduthuruthy -
| Neezhoor road ch 0/000 to 5/000 km | 450 | 11.2.2014 | 2015 | 2016 | 80 | Nil | 306.26 | # | #
13 | Improvements to Podikkalam
Madambam Parakkadavu Chipping
| Carpet road Km 0/000 to 10/200 | 480 | 22.12.2015 | 2016 | 2016 | 84 | Nil | 421.13 | # | #
14 | Improvements and resurfacing to
Panchikkadau - Aruvippuram road in
| Neyyattinkara Municipality | 245 | 8.8.2014 | 2015 | 2016 | 70 | Nil | 144.85 | # | #
15 | Formation of Kalmandapam Bus Stand
| Kalvakkulam road km 0/00-0/750 (1st Phase) | 459 | 3.4.2014 | 2015 | 2017 | 80 | Nil | 299.67 | 79.58 | #
(#) | Information not furnished by Department
16 | Improvements and providing BM & BC to
Vellur - Padiyottuchal - Pulingome Road
| Km 15/000 to 27/200 in Kannur District ($) | 1750 | 18.1.2016 | 2016 | 2017 | 99 | Nil | 1686.29 | 80.31 | #
17 | Stimulus Package - Construction of Nilambur
bypass - Phase 1 from Km 0/000 to 4/387
| in Malappuram District | 2000 | 10.9.2017 | 2017 | 2017 | 40 | Nil | 254.73 | # | #
18 | Improvements to Kunnukara Vaylkara Road | 175.39 | 22.12.2015 | 2016 | 2017 | 100 | Nil | 169.65 | # | #
19 | Budget work 2014-15 - Improvements to
Odakkayam Roobipally (Ruby Palli) road from
| Km 0/000 to 4/250 in Malappuram District | 625 | 28.7.2015 | 2016 | 2017 | 90 | Nil | 405.09 | # | #
20 | Nedumbala - Pallikavala - Ezhamchira -
| Kurusukavala Mukkamkunnu road | 300 | 22.12.2015 | 2016 | 2017 | 95 | Nil | #i | 258.96 | #
21 | Budget work - Improvements to Uliyil
Thillankeri road Km 0/000 to 4/650
| in Kannur (!) | 399.87 | 16.3.2017 | 2017 | 2017 | 22 | Nil | 291.46 | # | #
22 | NABARD RIDF XX - Improvements to
Aythala - Aruvachankuzhy road from
| 0/000 to 30/000 in Ranni LAC | 873.7 | 14.1.2015 | 2017 | 2018 | 100 | Nil | 822.79 | # | #
($) | Reason for expenditure expenditure over estimated cost is awaited from the Division
(!) | OB revised by the division
(#) | Information not furnished by Department
23 | Improvements and providing BM & BC
for approach road to Payyannur Railway
| station Km 1/000 - 3/100 in Kannur (!) | 300 | 22.12.2015 | 2016 | 2018 | 88 | Nil | 328.03 | Nil | Nil
24 | Improvements including to Parakadavu
Kallikandy Parat Cheruvanchery in
| Valiavelicham Airport road (!) | 102 | 25.1.2015 | 2017 | 2018 | 90 | Nil | 105.96 | # | #
25 | Reconstruction of Cherthala Town Roads | 631 | 16.3.2017 | 2017 | 2018 | 65 | Nil | 339.63 | # | #
26 | NABARD RIDF - XIX 2015
Construction of Vellikulam - Kariyad -
Chettupura - Vagamon road
| Ch 0/000 to 5/000 Km | 625 | 14.1.2015 | 2016 | 2018 | 80 | Nil | 446.91 | # | #
27 | Improvements and providing BM & BC
works to Morayur - Ozhukoor -
Ekkaparamba road from Km 1/780 to
| 5/600 in Malappuram Dist | 300 | 14.2.2017 | 2018 | 2018 | 85 | Nil | #i | 227.64 | #
28 | Providing BM & BC works to
Kattungalchola - Pilakkal - Puzhamkavu
| road between Km 0/350 to 3/100 | 128 | 16.3.2017 | 2018 | 2018 | 85 | Nil | #i | 108.9 | #
(!) | OB revised by the division
(#) | Information not furnished by Department
29 | Improvements and BT renewal works to
Valappumkundu - Pullancheri road
| (Km 0/000 to 1/600) in Ernad LAC | 180 | 16.3.2017 | 2017 | 2018 | 80 | Nil | #i | 127.29 | #
30 | Providing BM & BC works between
Km 9/000 to 11/158 of Thachangode -
| Koorad - Kallamoola road | 150 | 15.9.2017 | 2018 | 2018 | 80 | Nil | #i | 122.72 | #
31 | Widening and providing BM & BC
surfacing to Kottakkal - Kottapadi road
(Kovilakam road between Km 0/000
| to 2/100) in Kottakkal LAC Malappuram | 300 | 14.2.2017 | 2018 | 2018 | 45 | Nil | #i | 227.64 | #
32 | NABARD RIDF XXII - Improvements
to Chavakkad - Wadakkanchery road
| Km 15/000 to 19/015 | 500 | 23.11.2016 | 2017 | 2019 | 30 | Nil | 218.86 | # | #
33 | Improvements to Porthissery road
(Mini Civil Station road) Km 2/500
| to 3/220 | 149.5 | 3.6.2018 | 2018 | 2019 | 100 | Nil | 133.65 | # | #
34 | Improvements to Potta Moonnupeedika
| road from 1/000 to 6/000 km | 400 | 24.9.2018 | 2018 | 2019 | 100 | Nil | 356.49 | Nil | #
35 | Providing BC Overlay in Kaipattoor -
Pathanamthitta road Km 0/000 to 6/330
| and Town road 1.90 Km ($) | 400 | 21.8.2018 | 2018 | 2019 | 95 | Nil | 413.73 | Nil | #
(#) | Information not furnished by Department
36 | Improvements - widening and providing
BM & BC works to Parappangadi -
Tippusulthan road between km 0/000
to 5/600 in Tirurangadi LAC
| Malappuram District | 500 | 28.3.2018 | 2018 | 2019 | 60 | Nil | #i | 283.36 | #
37 | Improvements and providing BM & BC
works to Thottasseriyara - Nediyiruppu
harijan colony road between Km 0/000
| to 5/000 in Vengara LAC | 475 | 28.3.2018 | 2018 | 2019 | 85 | Nil | #i | 370.54 | #
38 | Providing BM & BC works to
Angadippuram Pariyapuram Cherukara
road Km 2/000 to 7/300 in
| Perinthalmanna LA | 400 | 28.3.2018 | 2018 | 2019 | 60 | Nil | #i | 149.33 | #
39 | Providing BM & BC work on Thuvoor
Puttamanna road between Km 4/000 to
| 6/150 in Malappuram District | 400 | 14.11.2017 | 2018 | 2019 | 50 | Nil | #i | 157.91 | #
40 | Improvements and providing BM & BC
from 4/500 to 7/800 of Omanoor -
| Kuzhimanna road in Kondotty LAC | 378 | 15.9.2017 | 2018 | 2019 | 40 | Nil | #i | 62.54 | #
41 | 2017/9626 Mulliria - Nattakkal -
| Arlapadavu road Km 4/100 to 8/000 (!) | 400 | 28.3.2018 | 2018 | 2019 | 70 | Nil | 254.54 | # | #
(!) | OB revised by the division
(#) | Information not furnished by Department
42 | 2018/10106 Providing BM & BC to
Kunjathoor - Kedumpady -
Nandarapadavu road Km 0/00 to
| 1/000 (1st Phase) | 100 | 27.11.2018 | 2019 | 2019 | 72 | Nil | 70.31 | # | #
43 | Improvements to Pallathur - Adoor -
Pandi road Km 0/000 to 9/350
| 1st Phase (0/000 to 3/600) | 283 | 16.3.2017 | 2017 | 2018 | 35 | Nil | 72.73 | # | #
44 | 2017/9746 Improvements to Kottikulam
| Thachangad road 03/200 to 4/200 | 120 | 28.3.2018 | 2018 | 2019 | 75 | Nil | 76.11 | # | #
45 | Podikundu - Kannothumchal road
(Renovation to Podikundu thana
Kannothumchal) via Kottali Kunhipally
Kakkad Dhanalakshmi road Km 0/000
| to 5/700 in Kannur (!) | 830 | 18.1.2016 | 2017 | 2018 | 86 | Nil | 714.62 | # | #
46 | Ashramam link road near KSRTC bus
stand to Thoppilkadavu (Phase 3
| extending to Olayilkadavu) | 11400 | 23.1.2016 | 2017 | 2019 | 12 | Nil | 862.81 | 277.18 | #
47 | RIDF XXIV - Improvements to St.
George Junction Pazhukkanam Junction
| in Arakkulam panchayath | 500 | 15.11.2018 | 2019 | 2019 | 45 | 17.41 | 127.34 | # | #
(!) | OB revised by the division
(#) | Information not furnished by Department
48 | FDR - Budget work 2018-19 - Improvements
to Cherthala Arookutty road from Ch 13/000
| to 16/500 in Aroor LAC | 300 | 22.12.2018 | 2019 | 2019 | 40 | Nil | 39.56 | 78.77 | #
49 | FDR 2018019 - Improvements to
Cherthala Arookutty road by providing
DGBM & BC overlay from Ch 2/000
| to 6/600 in Cherthala LAC | 400 | 22.12.2018 | 2019 | 2019 | 80 | Nil | 296.83 | 65.26 | #
50 | Construction of extension of river view
road LA and construction of road up to
| 16th mile in Ettumanoor - Poonjar SH ways | 4750 | 30.9.2015 | 2018 | 2020 | 90 | 1558.11 | 2844.7 | 2804.02 | #
51 | Improvements to Mundakkayam -
Kottikkal - Elamkadu - Valyantha -
Kolahalamedu - Vagamon Road
| Ch 0/000 to 23/850 km. | 3473 | 29.3.2018 | 2019 | 2020 | 90 | Nil | 1904.91 | 920.66 | #
52 | RIDF XXIV - Improvements to
anakkallu - Karivedakam Pookayam
road Km 0/000 to 5/500 in
| Kasaragod Dist | 600 | 2.11.2019 | 2019 | 2020 | 93 | Nil | 589.52 | # | #
(#) | Information not furnished by Department
53 | 2017/9627 Kumbala - Cherikkavu -
Kanjikatta - Churithaduka BM &
| BC Km 0/000 to 4/500 | 350 | 28.3.2018 | 2019 | 2020 | 80 | Nil | 215.39 | 40.43 | #
54 | Improvements to Amsakachery -
| Cherukulam road | 650 | 28.3.2018 | 2020 | 2020 | 50 | Nil | 109.52 | # | #
55 | Improvements to Thachampoyil Erpona
Parappanpoyil road (Thachampoyil
| Vadikkal road) Km 0/00 to 3/500 | 500 | 3.11.2018 | 2019 | 2020 | 95 | Nil | 105.41 | # | #
56 | Improvements to Kuttiady - Mullankunnu
| Pasukkadavu road 0/00 to 13/000 Km | 1670 | 21.2.2019 | 2020 | 2020 | 70 | Nil | 882.1 | # | #
57 | Improvements to Perambra - Chembra-
| Koorachundu road 0/000 to 2/200 | 400 | 5.3.2019 | 2019 | 2020 | 50 | Nil | 84.05 | # | #
58 | Improvements to Muruvassery-Changaramkulam
Kayakkodi road by providing BM & BC
| from Km 0/000 to 2/501 | 350 | 27.11.2018 | 2019 | 2020 | 60 | Nil | 98.45 | # | #
(#) | Information not furnished by Department
59 | Budget work 2018-19 RP to
Vattimthode Karumankayam Manippara
Kunnathur Paissakari road Km 3/900 to
5/900, Construction of retaining wall in
Mandambam parakkadavu Road and
reconstruction of damaged culverts at
| Uadayagiri Arivilinhapoyil road Km 2/300 | 161 | 13.2.2019 | 2019 | 2020 | 65 | Nil | 90.15 | # | #
60 | Construction of Akkamparamba
Chittikkara road Km 0/000 to 2/500 in
| Kuthuparamba LAC in Kannur Dist | 400 | 6.3.2019 | 2019 | 2020 | 80 | Nil | 320.02 | 26.74 | #
61 | Budget work 2018-19 - Improvements to
Vettippuram - Mahanimala Nellikkala -
| Naranganam road | 1000 | 27.11.2018 | 2019 | 2020 | 96 | Nil | 625.11 | 327.71 | #
62 | Budget work 2016-17 - Improvements to
Thodupuzha Pappotty hall Vengalloor
| (river view) road | 646.3 | 16.3.2017 | 2019 | 2020 | 99 | 350.42 | 751.22 | # | #
63 | 2017/9952 Chemmattamvayal -Kalichanadukkam
| road Km 0/000 to 8/001 | 900 | 28.3.2018 | 2019 | 2020 | 75 | Nil | 625.96 | # | #
64 | 2017/4229 - Improvements to Kamballur
Kadumeni - Pavel Chittarikkal road
in Trikkaripur LAC in Kasaragod Dist.
| Km 0/000 to 5/600 & 7/200 to 10/800 | 1900 | 28.3.2018 | 2019 | 2020 | 10 | Nil | 133.52 | # | #
(#) | Information not furnished by Department
65 | Budget work 2019-20 - Improvements
and BM & BC Surfacing to Chirayam
Methanam Panayikulam Road
| Ch 0/500 to 2/000 | 150 | 2.8.2019 | 2020 | 2020 | 70 | Nil | 48.69 | 62.61 | #
66 | Construction of Kandamkary Nedumudi
Umbukkattu Varambinakam - Vellamathara
Venattukadavu - Kayalpuram - Kannady
road from Ch 5/400 to 9/580 km in
| Alappuzha District | 2500 | 16.7.2015 | 2019 | 2020 | 55 | Nil | 449.58 | 245.95 | #
67 | Budget work 2017-18 - Improvements to
| Thankey road | 900 | 6.6.2018 | 2019 | 2020 | 68 | Nil | 1091.43 | 90.24 | #
68 | Improvements to Cherthala Arookutty road
by providing DGBM & BC overlay from
| Ch 0/200 to 2/000 in Cherthala LAC | 150 | 13.2.2019 | 2019 | 2020 | 80 | Nil | 105.82 | # | #
69 | FDR 2018-19 - Improvements to
Cherthala Arookutty road by providing
DGBM & BC overlay from Ch 2/000 to
| 6/600 in Cherthala LAC | 400 | 22.12.2018 | 2019 | 2020 | 80 | Nil | 296.84 | # | #
70 | Improvements to Ambalappuzha
| Chirakkodu - Kanippara - SN Kavala Road | 2412 | 19.12.2017 | 2018 | 2020 | 95 | Nil | 1200.54 | # | #
71 | SF 2020-21 - Improvements to Pandanad
| Budhanoor Road from Ch 0/000 to 7/125 | 600 | 9.9.2020 | 2020 | 2020 | 40 | Nil | 466.76 | # | #
(#) | Information not furnished by Department
72 | Construction of Kandamkary - Nedumudi
Umbukkattu Varambinakam - Vellamthara -
Venattukadavu - Kayalpuram - Kannady road
| from Ch 5/400 to 9/580 km in Alappuzha Dist. | 2500 | 16.7.2015 | 2019 | 2020 | 55 | Nil | 449.57 | # | #
73 | Improvements to Kozhenchery Market
Marottumukku - Melukara Keezhukara
| road 0/000 | 280 | 25.7.2019 | 2019 | 2021 | 94 | Nil | 261.64 | # | #
74 | Raising sub merged portion of Muttar
Central road & providing DBM&BC
| between Ch 3/000 to 6/300 | 350 | 13.2.2019 | 2020 | 2021 | 75 | Nil | 77.93 | # | #
75 | Providing drainage facility to various
| roads in Cherthala LAC | 300 | 26.8.2019 | 2020 | 2021 | 80 | Nil | 138.47 | 86.61 | #
76 | Improvements by providing BM & BC
to various roads under Kandalloor,
| Panchayats in Kayamkulam LAC | 1000 | 12.12.2019 | 2020 | 2021 | 90 | Nil | 178.61 | 46.13 | #
77 | Budget work 2018-19 - Improvements
to Koxukulanji - Thayyilppady - Athalakkadavu
| road from Ch 0/000 to 5/001 | 720 | 24.9.2018 | 2020 | 2021 | 70 | Nil | 153.05 | # | #
78 | Improvements including BM & BC to
Peringathoor - Mukkilpeedika road
| Km 0/000 to 2/512 | 400 | 28.3.2018 | 2019 | 2020 | 70 | Nil | 75.84 | 293.40 | #
(#) | Information not furnished by Department
79 | Improvements including BM & BC to Parat
Kunothparamba Pollur road Km 4/900 to
| 6/500 in Kuthuparamba LAC | 200 | 28.3.2018 | 2019 | 2020 | 75 | Nil | 46.56 | 79.53 | #
80 | Improvements to Muttannur - Edayannur
| Road Km 0/000 to 2/000 | 200 | 27.8.2019 | 2019 | 2020 | 20 | Nil | 36.38 | # | #
81 | Improvements by providing BM & BC to
Pazhayattinkuzhi-Sangha mukku-Kaithari mukku
Palathara Varazhikam road in Kollam
| Corporation - Work General Civil Work | 310 | 12.5.2021 | 2021 | 2021 | 75 | Nil | 121.34 | 66.91 | #
82 | Improvements to Rayarome -
Moonnamkunnu - Kunderi - Parapoyil
| Road Km 0/000 to 8/200 | 1200 | 13.12.2019 | 2021 | 2021 | 32 | Nil | 386.60 | 199.35 | #
83 | Development of Peralassery town with
beautification by providing drainage, fixing
of handrail and footpath between Ch.93/000
| to 96/000 | 500 | 23.8.2020 | 2021 | 2021 | 9 | Nil | 34.11 | # | #
84 | Town improvements works - Development
of town relevant to Chembilode Panchayat
including related roads of Chala -
Mowanchery road encompassing Chala
Town and other with beautification under
PWD Roads section, Kannurby providing
| drainage, fixing of handrails and foot path | 300 | 22.12.2020 | 2021 | 2021 | 65 | Nil | 49.61 | 113.78 | #
(#) | Information not furnished by Department
85 | Improvements to Punnayurkulam -
Changaramkulam road Km 0/000 to 2/200
| Work General Civil work | 222.16 | 12.5.2020 | 2021 | 2021 | 90 | Nil | 94.30 | # | #
86 | S/F 2020-21 BM & BC works in
Chandanappally Konny road Ch 0/00
| to 12/200 | 975.00 | 9.9.2020 | 2021 | 2021 | 90 | Nil | 147.24 | 129.88 | #
87 | NABARD RIDF XXV - Improvements to
Moothedathukavu road ch 0/000 to 4/200 km
| Work General Civil | 441.42 | 24.1.2020 | 2020 | 2021 | 60 | Nil | 407.65 | 49.07 | #
88 | General SF work 2020-21 - Providing
MSS with mechanical means to Manimala -
Pazhayidam - Chenapady - Erumely road
| Ch 0/000 to 15/205 Km work | 300 | 9.9.2020 | 2020 | 2021 | 60 | Nil | 196.44 | # | 299.86
89 | Improvements by providing BM and BC
to Koorachipadi Naduvattom road
| Km 1/000 to 3/440 | 400 | 8.10.2020 | 2021 | 2021 | 84 | Nil | 305.76 | # | #
90 | Providing drainage facilities and
improvements to Koppam Town in
| Pattambi LAC | 200 | 06.11.2020 | 2021 | 2021 | 92 | Nil | 161.53 | # | #
91 | Improvements to Prakash Karikkinmedu
| Upputhodu road Km 0/000 to 6/000 | 500 | 11.02.2019 | 2020 | 2021 | 98 | 109.7 | 497.31 | 8.07 | #
(#) | Information not furnished by Department
92 | Improvements to Murikkassery
| Kambilkandom road Km 0/000 to 3/000 | 400 | 02.08.2019 | 2020 | 2021 | 90 | Nil | 237.98 | # | #
93 | Budget work 2014-15 Improvements to
| Moolamattom Pathippilly Ulupunni road | 696.96 | 02.01.2020 | 2020 | 2021 | 90 | Nil | 280.88 | 122.54 | #
94 | Sabarimala Festival 2020-21 - Improvements
by providing BM & BC to Kanjirathumoodu
| Parappattupady road - Ch 0/000 to 03/081 | 300 | 09.09.2020 | 2021 | 2021 | 80 | Nil | 9.18 | 59.71 | #
95 | Improvements to Ganapathynada
Arkannoor Maniyanmukku Road Ch 0/000
to 4/000 KM by providing BM & BC and
allied works in Chadayamangalam LAC
| work - General Civil work | 400 | 20.10.2021 | 2021 | 2022 | 75 | Nil | 82.51 | 86.17 | #
96 | Budget work 2017-18 Improvements to
Mulavana Kaithakode road 0/000 to 2/700
| Work - General Civil work | 250 | 26.08.2021 | 2021 | 2022 | 75 | Nil | 200.13 | # | 480.68
97 | Budget work 2019-20 - Improvements to
Thulasimukku Pangalukadu road by laying
BM & BC Ch 0/000 to 4/400 in
Chadayamangalam LAC - Work General
| Civil work | 400 | 26.02.2021 | 2021 | 2022 | 85 | Nil | 340.8 | # | #
(#) | Information not furnished by Department
98 | Providing 40MM close graded CC and
Berm protection to Elamad Thevannoor
Road Ch 0/000 to 6/950 - Work General
| Civil work | 170 | 28.05.2021 | 2021 | 2022 | 25 | Nil | 20.87 | # | #
99 | Improvements with BM & BC to approach
road to Mattool - Madakkara road 0/000 -
| to 1/259 | 150 | 05.01.2021 | 2021 | 2022 | 30 | Nil | 42 | 5.93 | #
100 | Improvements with BM & BC to
Mannamangalam Marottichal Vellur
Chimney Dam road 2/000 to 5/700 in Ollur
| constituency-Work-General Civil Work | 305.96 | 06.11.2020 | 2021 | 2022 | 80 | Nil | 78.45 | # | #
101 | Improvements to Althara Panamthrar
road Km 0/000 to 2/140 Work - General
| Civil work | 176.35 | 12.05.2020 | 2020 | 2022 | 30 | Nil | 8.88 | # | #
102 | Improvements with BM & amp, BC to
Kanippayyur Iringapuram road Ch 0/000
| to 2/800 - Work General Civil work | 260.53 | 06.11.2020 | 2021 | 2022 | 50 | Nil | 79.28 | # | #
103 | Sabarimala Festival 2021-22 - Improvements
Improvementswith BM & BC to Inchimala
Palace square Eruveli Vattukunnu
| Road Ch 0/000 to 2/910 | 300 | 30.10.2021 | 2022 | 2022 | 90 | Nil | 73.17 | 211.78 | #
(#) | Information not furnished by Department
104 | NABARD RIDF XXVI - Ameparambu
Road Ch 0 to 1/400, Kshemodayam road
Ch 0 to 1/300, Pullipra Ch 0 to 1/400,
Mullayappilly Ch 0 to 0/900,
Pazhagattuveli Ch 0 to 0/250, SNDP
Cheriyappilly Road Ch 0 to 0/900
| (Total length 6.150 km) 6 nos. road | 489.64 | 29.9.2020 | 2021 | 2022 | 41 | Nil | 49.22 | # | #
105 | General - Combined - Deposit and Budget
work 2020-21 Moulana Azad Road -
Restoration due to road cutting for OFC
cable laying project under NCN for Indian
Navy and Budget work 2020-21 -
Improvements with BC overlay to Moulana
| Azad Road Ch 0/000 to 3/600 | 249.00 | 19.4.2022 | 2022 | 2022 | 50 | Nil | 64.77 | # | #
106 | Budget work 2020-21 - Improvements with
Thoppumpady Jn by providing handrails,
| drainage and footpath | 250.00 | 6.11.2020 | 2022 | 2022 | 45 | Nil | 39.29 | # | #
107 | NABARD RIDF XXIV Improvements
to Kumbanadu - Cherukolpuzha road
Km 0/00 to 5/350, Kuriyannoor - Maramon
road Km 0/00 to 3/380 and Parapuzha
Cross road Km 0/00 to 1/780 Work
| General Civil work | 1000.00 | 11.02.2019 | 2020 | 2022 | 90 | Nil | 699.91 | 22.42 | #
(#) | Information not furnished by Department
108 | Budget work 2018-19 - Improvements to
Ezhamkulam Plantation mukku Theppupara -
| Nedumankavu road in Adoor LAC | 2000.00 | 26.02.2020 | 2021 | 2022 | 85 | Nil | 1544.85 | # | #
109 | Budget work Kozhippalam -
| Karakkadu road by providing BM & BC | 500.00 | 13.08.2021 | 2022 | 2022 | 70 | Nil | 34.11 | 229.05 | #
110 | Sabarimala Festival 2020-21 - Improvements
to Sabarimala Thiruvabharana Kshethram
| Road - General Civil Work | 500.00 | 09.09.2020 | 2022 | 2022 | 75 | Nil | 202 | 128.49 | #
111 | General Budget work 2020-2021 :
Poomkavu Pathanamthitta Road Ch 0/000
| to 5/000 - Work General Civil work | 700.17 | 27.12.2020 | 2021 | 2022 | 90 | Nil | 402.54 | 151.39 | #
112 | Improvements to Bethelppadi - Chumathra by
| providing BM & BC from 0/00 to 02/01 | 200.00 | 13.02.2019 | 2021 | 2022 | 35 | Nil | 60.54 | 28.75 | #
113 | Providing BC overlay & drainage facilities
in Vennikkulam Ranny Road Ch 0/000
| to 4/500 | 200.00 | 09.09.2020 | 2021 | 2022 | 90 | Nil | 30.31 | 151.39 | #
114 | NABARD RIDF XXVI - Improvements
to Kottarathil Kadavu - Manganam -
| Paloorpady road Ch 0/000 to 5/600 | 432.16 | 29.09.2020 | 2021 | 2022 | 90 | Nil | 436.46 | # | 486.06
(#) | Information not furnished by Department
115 | General Budget work 2019-2020 -
| Construcion of Kidangoor bypass | 300 | 12.12.2019 | 2021 | 2022 | 60 | Nil | 78.81 | 149.82 | #
116 | General Plan 2019-20 - Improvements to
Kavungumpalam Naiplavu road Ch 3/000
| to 13/000 Km | 400 | 31.01.2020 | 2021 | 2022 | 60 | Nil | 216.53 | Nil | #
117 | Improvements and widening work to
Karapotta - Choolipadam road Km 0/000
| to 4/000 | 340 | 28.03.2018 | 2019 | 2022 | 45 | Nil | 138.83 | # | #
118 | Improvements to Melechinnar
Kanakakunnu Perumthotty Prakash
| Karikkinmedu Upputhode road | 1000 | 24.09.2020 | 2021 | 2022 | 80 | Nil | 538.05 | 242.62 | #
119 | Imprvements to Cheruthony Town | 500 | 12.12.2019 | 2022 | 2022 | 20 | Nil | 1.77 | 18.01 | #
120 | General 2020-21 - Improvements to BHS
to old Kuttitheruvu road 0/00 to 1/800
| Work General Civil work | 149 | 5.1.2021 | 2021 | 2022 | 92 | Nil | 49.75 | # | #
121 | SLTF 2020-21 - Improvements to by
providing BC overlay to Thottappally -
| Trikkunnappuzha road Ch 0/000 to 7/600 | 260 | 5.1.2021 | 2021 | 2022 | 95 | Nil | 265.56 | # | #
122 | Sabarimala festival 2021-22 - Improvements
of MC Road with BM patch and BC
| overlay from Ch 227/000 to 232/250 | 400 | 30.1.2021 | 2022 | 2022 | 92 | 390.79 | 390.79 | # | #
(#) | Information not furnished by Department
123 | Special sanction 2017-18 - Improvements
to Kothamangalam Perumbakuthu road
from Ch 0/000 to 4/700 (from
| Kothamangalam to Chelad) balance work | 380 | 28.3.2018 | 2021 | 2022 | 50 | 117.08 | 162.13 | # | #
124 | General budget work 2021-22 providing
BM and BC to Thavalakkuzhi-clamattom
kadappor road ch: 1/000 to 4/000 Km-
| general civil work-1 | 400 | 13.08.2021 | 2021 | 2023 | 95 | 393.29 | 393.29 | # | #
125 | Construction of Thankalam -kozhippilly
| New bye Pass Road Ch 0/00 to 1/000 | 450 | 27.12.2019 | 2021 | 2022 | # | 28.79 | 295.91 | # | #
126 | Improvements to Manakkadavu-Morakkala
Perumbikkara-Pinarmunda- Ambalampady
Peringala-Padathikkara- bramapuram road
by providing BM& BC and drainage
| facilities from ch 0/000-2/400 | 450 | 13.08.2021 | 2022 | 2023 | 90 | 74.56 | 74.55 | 279.84 | 401.40
127 | Improvements to keerithodu Aramkopu
| Ezhkoppu Periyavally Road in Idukki | 1000 | 12.02.2021 | 2022 | 2023 | 70 | 263.37 | 263.37 | 178.51 | #
128 | Improvements to Arappamattom
| Karimannoor Road 0/000 to 8/000 | 700 | 13.08.2021 | 2022 | 2023 | 80 | 194.11 | 194.11 | 160.22 | #
129 | Improvements to Parathodu Town-
karshikavipani Pallickamallappady
| Chinaar - Nirappu-Chembakappara Road | 500 | 01.12.2021 | 2022 | 2022 | 80 | 157.67 | 157.67 | # | #
(#) | Information not furnished by Department
130 | Construction of Attakkulam bridge in
| Thiruvalla constituency in Pathanamthitta | 166.1 | 19.02.2021 | 2021 | 2022 | 98 | 77.5 | 169.7 | # | #
131 | Reconstruction of Punnappadam Mambad
| causeway in Alathur LAC Palakkad Dist. | 660 | 08.01.2021 | 2022 | 2024 | 90 | 300.44 | 300.44 | # | #
132 | Construction of Enathi bridge across
| Karimpuzha River in Malappuram | 1093 | 13.04.2018 | 2018 | 2020 | 42 | 27.13 | 225.71 | # | #
133 | Construction of Thrikkekuth bridge across | 1090 | 12.03.2023 | 2021 | 2022 | 82 | 362 | 784.9 | # | #
Kuthirappuzha Malappuram
(#) | Information not furnished by Department
National Highways
1 | IRCP from km 444/000 to 462/000
| on NH 47 new NH 56 in the state | 1372.18 | # | 2012 | 2013 | 100 | # | 1326.05 | # | 1711.03
(#) | Information not furnished by Department
Source - Information furnished by Divisions

## Closed 23_24
APPENDIX IX
COMMITMENTS OF THE GOVERNMENT - LIST OF INCOMPLETE CAPITAL WORKS
(Includes Projects/Works the cost of which is ` 1 crore and above)
( ` in lakh)
Sl. | Name of | Estimated Cost of Work/ Date of sanction |  | Year of commen-cement | Target year of completion | Physical progress of work (in per cent) | Expenditure during the year | Progressive expenditure to the end of the year | Pending payments | Revised cost if any/date of revision
No. | Project/
Work
Canals
1 | Construction of steel foot bridge across
| Badagara - Mahe canal at Karuvayal(!) | 107 | 1.2.2019 | 2020 | 2022 | 100 | 34.18 | 64.5 | Nil | Nil | Completed on 29.8.22
Anti sea Erosion
2 | KP- Restoring outer bund of Arupank | [9 empty] | work completed
| padasekharam in kainakary Panchayath | 374.49 | 25.07.2019 | 2020 | 2022 |  | 67.54 | 406.74 | Nil | Nil
3 | KP Restoring Outer Bund of marthandam
| padasekharam in kainakary Panchayath | 416.81 | 24.07.2019 | 2019 | 2023 |  | 146.49 | 454.31 | NIL | Nil | work completed
4 | Restoring Outer bund of madathil Kayal
thazha, madathil kayal, Padinjar venttukkary
Puthanpura kayal and Vadakke Mathikayal in
| Pulinkunnu Panchayath | 830 | 25.07.2019 | 2020 | 2023 |  | 94.47 | 707.27 |  |  | work completed
Buildings
5 | Construction of building for Form
Store at Meppady Government Press
| in Wayanad | 110 | 21.7.2016 | 2016 | 2017 | 100 | Nil | 78.98 | Nil | Nil | work completed
26 | Construction of Collector's Bungalow
| Pathanamthitta | 135.69 | 27.12.2019 | 2019 | 2020 | Nil | Nil | Nil | Nil | Nil | work completed
27 | GMC - EKM - Modernization of
| administrative block and medical | [9 empty] | work completed
| records library | 150 | 20.7.2018 | 2019 | 2020 | 100 | # | 68.36 | Nil | Nil
30 | Construction of MBBS Ladies Hostel
| Phase II in Govt. Medical College, Thrissur | 236.24 | 8.3.2018 | 2020 | 2021 |  |  |  | Nil | Nil | work completed
31 | Construction of a building for new
academic block, GPTC, Chelad,
| Kothamangalam | 500 | 18.7.2017 | 2019 | 2023 | 100 | 76.78 | 332.68 | Nil | Nil | work completed 13.07.2023
41 | Construction of a new building for
| Govt. ITI Maradu | 540 | 25.1.2019 | 2020 | 2022 | Nil | Nil | Nil | Nil | Nil | work completed
Bridges
17 | Construction of Cherpunkal parallel | [9 empty] | workl completed
Bridge across Meenachil river in
| Cherpunkal Kozhuvanal road | 945 | 31.3.2012 | 2019 | 2020 | 60 | 152.91 | 2555.835 | 109 | Nil
23 | Construction of Cherpunkal parallel | [9 empty] | workl completed
Bridge across Meenachil river in
| Cherpunkal Kozhuvanal road | 945 | 31.3.2012 | 2019 | 2020 |  |  |  | 16.12 | Nil
24 | Construction of Mambillikadavu Bridge in
| Vengappally Grama Panchayat in Waynad | 1164 | 14.01.2015 | 2018 | 2020 | 100 | 0 | 1157.4 | 0 | nil
25 | Construction of Thalipparakkadavu Bridge
| Across Panamaram River in Waynad | 1755 | 30.12.2015 | 2018 | 2020 | 100 | 0 | 1419.13 | 334.83 | nil
27 | Kakkeri single lane bridge across | [9 empty] | workl completed
Cherupuzha, connecting Kunnamangalam
| and Chathamangalam Panchayath | 459 | 2.11.2020 | 2021 | 2022 | 100 | 28.7 | 114.59 | 145.89 | Nil
28 | Pthundy Bridge (Reconstruction) across | [9 empty] | workl completed
Pothundy thodu in Adivaram Nooram
| Thodu road | 300 | 1.1.2021 | 2021 | 2022 | 100 | 178.47 | 214.47 | 38.25 | Nil
29 | Construction of Nadakkal Bridge across | [9 empty] | workl completed
Cherupuzha river on Keezhariyoor -
| Podiyadi - Thurayur road in Kozhikode Dist. | 312 | 22.12.2020 | 2021 | 2022 | 100 | 0 | 100.1 | 106.3 | Nil | work completed
30 | Reconstruction of Urutty bridge on Kallachi
| Vilangadu road in Nadapuram | [9 empty] | work completed
| Constituency at Chinage 11/500 | 320 | 19.1.2021 | 2021 | 2022 | 100 | 48.48 | 217.56 | 26.44 | Nil
33 | New Malamala Santhi Bridge across | [9 empty] | work completed
| Periyar river in Peermedu LAC | 600 | 15.2.2021 | 2021 | 2022 | 60 | 0 | 32816486 | 216.93 | Nil
Roads
13 | Improvements to Karakkunnu - | [9 empty] | Completed on 18.7.2017
Kurumbalakotta - Kallamthodu road
in Kottathara Grama Panchayath
| Km 0/000 to 3/200 in Wayanad ($) | 250 | 11.2.2014 | 2016 | 2016 | 96 | Nil | 197.18 | 86.03 | Nil | closed on 25.03.2020
17 | Improvements to Kodunthirapulli
| Thirunellayi road km 0/00 - 2/600 | 100 | 22.12.2015 | 2017 | 2017 |  |  |  | 44.82 | Nil
24 | Providing BM & BC to Mananthavady
Pakramthalam road from km 10/240
| to Wayanad District | 1000 | 22.12.2015 | 2017 | 2018 | 100 | 127.47 | 127.47 | 178.8 | 1209.32 | closed on 29-11-21
25 | Improvements and providing BM & BC
| Nedumpoyile - Mananthavady road | [9 empty] | Completed
Chainage 38/000 to 81/000 (Portion
| from Ch 50/400 to 81/000 of Thalasseri | [9 empty] | Completed 30.7.20
| Bavali road (Balance work) | 2500 | 9.11.2011 | 2017 | 2018 | 100 | nil | 143.92 | 0 | 1392.72
28 | Improvements to Padiyottuchal -
| Cherupara - Thimiri - Perumbadavu | [9 empty] | Completed 29.4.21
| road Km 4/000 to 9/210 (!) | 447 | 16.3.2017 | 2017 | 2018 |  |  |  | Nil | Nil
46 | 2017/9746 Improvements to Kottikulam
| Thachangad road 3/200 to 4/200 | 120 | 28.3.2018 | 2018 | 2019 |  |  |  | Nil | Nil
47 | Improvements to Kakadavu Badoor - | [9 empty] | Completed
Kambaloor Cheriupzha road - West
| Eleri & East Eleri GP (0/00 to 5/200 | 126 | 16.3.2017 | 2018 | 2019 |  |  |  | Nil | Nil
57 | Special sanction 2017-18 - Improvements | [9 empty] | Completed
and providing BC renewal to Thrissur
Mannuthy road from 0/000 to 5/020
| in Thrissur LAC | 300 | 28.3.2018 | 2018 | 2019 |  |  |  | Nil | Nil | Completed
58 | Budget work 2017-18 - Providing BM &
BC to Koratty - Pullikkakadavu road
| from Ch 1/100 to 4/250 | 289.4 | 17.3.2018 | 2018 | 2019 |  |  |  | Nil | Nil
59 | Budget work 2018-19 - Improvements | [9 empty] | Completed
to Ezhunallathpatha road in Chalakudy
| from 0/00 to 2/200 | 180 | 28.3.2019 | 2019 | 2019 |  |  |  | Nil | Nil
60 | Special sanction - Improvements and
| providing BM & BC & Drainage works | [9 empty] | completed on 29-02-24
to Pattikkad Bazar road at Km 0/000
| to 2/000 in Ollur LAC | 225 | 6.6.2018 | 2019 | 2019 |  |  |  | Nil | Nil
99
27 | RIDF XXIV - Improvements to | [9 empty] | work completed
Punnacity 300 acre Kurangupara road
| Km 0/000 to 4/500 | 600 | 15.11.2018 | 2019 | 2020 | 100 | 76.81 | 455.24 | 119.8 | Nil
135 | Sabarimala Festival 2021-22 Providing BC | [9 empty] | work completed
overlay to Koothattukulam Ramapuram
| road Ch 1/600 to 3/600 | 200 | 30.10.2021 | 2022 | 2022 | 100 | 147.69 | 191.27 | 0 | 193.44
136 | Budget work 2020-21 - Improvements to | [9 empty] | work completed
Arakuzha - Thottakara (Marika) BM &
| BC specification from 0/00 to 3/400 | 225 | 6.11.2020 | 2022 | 2022 | 100 | 214.45 | 214.45 | 0 | 216.44 | Completed 28.02.2023
137 | Budget work 2020-21 - Improvements to
Mannoor - Valakam road from 6/400 to
| 7/00 and 7/400 to 8/600 | 250 | 6.11.2020 | 2021 | 2022 | 100 | 153.38 | 153.38 | 67.89 | 228.69 | Completed 30.06.2023
Improvement works to Mutholapuram -
| ponkutty Road | 300 | 12.05.2020 | 2021 | 2021 | 100 | 54.41 | 238.18 | 24.60 | 258.04
improvements from Chelad to punnekkadu in
| Kothamangalam perumbankuth Road | [9 empty] | Completed
| Ch4/700to 8/700 | 400 | 06.11.2020 | 2022 | 2023 | 100 | 230.52 | 238.18 | 124.49 | Nil
budget work2019-2020 improvements to
| Peringala Puthencruz road Ch0/000 to 3/600 | [9 empty] | Completed 24.12.2022
and construction of Cuvert at Ch 3/850 and
| 4/600 Phase I | 300 | 02.08.2019 | 2021 | 2022 | 100 | 12.89 | 159.89 | 106.86 | 255.10
| B\W 2020-21 Improvements to Pulluvazhy | [9 empty] | Completed 30.05.2023
Kallil Road providing BM &BC from Ch
| 3/000 to 4/000 & amp ch6/000 to 6/750 | 224 | 01.12.2021 | 2022 | 2022 | 100 | 124.95 | 207.73 | Nil | 189.10
Sabarimala festival 2021-22 providing BC
Overley to Aluva Munnar road from
| Ch.28/000 to 35/226 | 460 | 30.10.2021 | 2022 | 2023 | 100 | 433.41 | 433.41 | 29.56 | 399.50