## Sheet1
Appendix-IX
Commitment of the Government-list of Incomplete capital works
(` in lakh)
SL. No. | Name of the Project/ Works | Estimated cost of work/ date of Sanction | Year of commen-cement | Target year of completion | Physical progress of work (in per cent) | Expen-diture during the year | Progressive expenditure to the end of the year | Pending Payments | Revised cost if any/date of revision
1. PHE Department
1 | Pfutsero town (State Plan) | 424.81 | 2011-12 | 2013-14 | 1 | 0 | 43.7 | 0 | 424.81
2 | Prov. Water Supply to new Peren District HQ (NLCPR) | 930.94 | 2012-13 | 2014-15 | 77 | 0 | 900.54 | 0 | 930.94
3 | Construction of SE, PHED office complex at Dimapur | 216.24 | 2012-13 | 2014-15 | 99 | 0 | 214.49 | 63.3 | 216.24
4 | Urban water metering system at Dimapur | 1654.58 | 2011-12 | 2019-20 | 19 | 17.79 | 262.35 | 1392.23 | 1654.58
|  | 3226.57 |  |  |  | 17.79 | 1421.08 | 1455.53 | 3226.57
2. P.W.D. (R&B)
1 | Improvement of road from Chozuba to Ghatashi (NABARD) | 800 | 2010-11 | 2012-13 | 0.39318 | 0 | 314.54 | 485.46 | 800
2 | Construction of Road from Akukchampang to Tizit via New Akuk | 530.68 | 2007-08 | 2009-10 | 0.90211 | 0 | 478.73 | 51.95 | 530.68
3 | Improvement of roads in Mon district (under PM’s package) | 2374.78 | 2005-06 | 2014-15 | 0.73333 | 0 | 1741.49 | 633.29 | 2374.78
4 | Construction of 2 lane RCC Bridge over Dhansiri river | 645.19 | 2007-08 | Work Suspended | 0.99933 | 0 | 644.76 | 0.43 | 645.19
5 | Construction of road from NH-150 to Chokriba via Thipuzu. (10 Km) | 1167.91 | 2011-12 | 2014-15 | 0.71819 | 0 | 838.78 | 329.13 | 1167.91
6 | Construction of road from Kohima-Leikie road Jn To Barak Ph-III | 1911.48 | 2012-13 | 2014-15 | 0.76 | 0 | 1452.72 | 458.76 | 1911.48
7 | Construction of road from Jumuzyu to Tronger Jn. | 71.1 | 2013-14 | 2014-15 | 0.05007 | 0 | 3.56 | 67.54 | 71.1
Appendix-IX
Commitment of the Government-list of Incomplete capital works -Contd.
(` in lakh)
SL. No. | Name of the Project/ Works | Estimated cost of work/ date of Sanction | Year of commen-cement | Target year of completion | Physical progress of work (in per cent) | Expen-diture during the year | Progressive expenditure to the end of the year | Pending Payments | Revised cost if any/date of revision
8 | Construction of road from Chen Hq to Wangti | 2451 | 2013-14 | 2017-18 | 35.9853 | 0 | 882 | 1569 | 2451
|  | 9952.14 |  |  |  | 0 | 6356.58 | 3595.56 | 9952.14
3. Geology and Mining
1 | Construction of Guest House and Chowkidar Quarter at Kobulong (Mokokchung) and Tobu (Mon) | 100 | 2017-18 | 2018-19 | 21.98 | 0 | 21.98 | 78.02 | 100
2 | Construction of Link Roads to Mineral Deposit area. | 2653.91 | 2007-08 | 2010-11 | 98.0406 | 0 | 2601.91 | 52 | 5394.52
3 | Mineral Industry Growth Centre of Kirupe, Kohima | 500 | 2010-11 | 2013-14 | 60 | 0 | 300 | 200 | 500
4 | Construction of bridges in Nimi-Laluri Mineral Link Road | 2053.93 | 2010-11 | 2013-14 | 95.9799 | 0 | 1971.36 | 82.57 | 2053.93
|  | 5307.84 |  |  |  | 0 | 4895.25 | 412.59 | 8048.45
4. Department of Under Developed Area
1 | Construction of DUDA Students Hostel at Jotsoma (Phase-I) | 490 | 2013-14 | 2016-17 | 40.8163 | 0 | 200 | 290 | 490
2 | Construction of DUDA Directorate | 829 | 2012-13 | 2016-17 | 50.6634 | 0 | 420 | 409 | 829
3 | Completion of DUDA Guest House at Sovima | 450 | 2012-13 | 2016-17 | 44.4444 | 0 | 200 | 250 | 450
|  | 1769 |  |  |  | 0 | 820 | 949 | 1769
5. Tribal Affairs Department
1 | Construction of tribal complex at Tuensang town | 180 | 2013-14 | 2014-15 | 5 | 0 | 9 | 171 | 180
Appendix-IX
Commitment of the Government-list of Incomplete capital works -Contd.
(` in lakh)
SL. No. | Name of the Project/ Works | Estimated cost of work/ date of Sanction | Year of commen-cement | Target year of completion | Physical progress of work (in per cent) | Expen-diture during the year | Progressive expenditure to the end of the year | Pending Payments | Revised cost if any/date of revision
2 | Construction of tribal complex at Mon town | 180 | 2013-14 | 2014-15 | 5 | 0 | 9 | 171 | 180
3 | Construction of tribal complex at Kiphire town | 180 | 2013-14 | 2014-15 | 5 | 0 | 9 | 171 | 180
4 | Construction of tribal complex at Longleng town | 180 | 2013-14 | 2014-15 | 5 | 0 | 9 | 171 | 180
5 | Construction of tribal complex at Shamatore town | 180 | 2013-14 | 2014-15 | 5 | 0 | 9 | 171 | 180
6 | Construction of tribal complex at Noklak town | 180 | 2013-14 | 2014-15 | 5 | 0 | 9 | 171 | 180
|  | 1080 |  |  |  | 0 | 54 | 1026 | 1080
6. Various Works under Eastern Nagaland
1 | Construction of Town Committee Office Complex at Tizit | 90 | 2013-14 | 2014-15 | 95.5556 | 0 | 86 | 4 | 90
2 | Augmentation of water supply at Naginimora town | 90 | 2013-14 | 2014-15 | 95.5556 | 0 | 86 | 4 | 90
3 | Construction of Agri-link road from Langtang to Talit river | 90 | 2013-14 | 2014-15 | 95.5556 | 0 | 86 | 4 | 90
4 | Construction of culvert, soiling & blacktopping from Phomching main town to football ground | 90 | 2013-14 | 2014-15 | 95.5556 | 0 | 86 | 4 | 90
5 | Soiling & metaling of circular road at Chen Town | 90 | 2013-14 | 2014-15 | 95.5556 | 0 | 86 | 4 | 90
Appendix-IX
Commitment of the Government-list of Incomplete capital works -Contd.
(` in lakh)
SL. No. | Name of the Project/ Works | Estimated cost of work/ date of Sanction | Year of commen-cement | Target year of completion | Physical progress of work (in per cent) | Expen-diture during the year | Progressive expenditure to the end of the year | Pending Payments | Revised cost if any/date of revision
6 | Construction of road from Leangha village and Chi village | 90 | 2013-14 | 2014-15 | 95.5556 | 0 | 86 | 4 | 90
7 | Construction of Community Hall at Aboi | 90 | 2013-14 | 2014-15 | 95.5556 | 0 | 86 | 4 | 90
8 | Construction of 10 Nos of retaining walls at Angjangyang HQ. | 90 | 2013-14 | 2014-15 | 95.5556 | 0 | 86 | 4 | 90
9 | Construction of Guest House at Tobu HQ. | 90 | 2013-14 | 2014-15 | 95.5556 | 0 | 86 | 4 | 90
10 | Construction of Agri-link road from Kangching Rest House to Shingha river | 90 | 2013-14 | 2014-15 | 95.5556 | 0 | 86 | 4 | 90
11 | Construction of RCC drainage within Longleng Town | 90 | 2013-14 | 2014-15 | 95.5556 | 0 | 86 | 4 | 90
12 | Diversion of Noksen Town road | 90 | 2013-14 | 2014-15 | 95.5556 | 0 | 86 | 4 | 90
13 | Extension/soiling/metalling at 155 NH bypass road via Angangba village to Longkhim | 90 | 2013-14 | 2014-15 | 95.5556 | 0 | 86 | 4 | 90
14 | Construction of road from Nongshang colony to State highway | 90 | 2013-14 | 2014-15 | 95.5556 | 0 | 86 | 4 | 90
15 | Construction of road between Hakchang to Maksha Phase-II | 90 | 2013-14 | 2014-15 | 95.5556 | 0 | 86 | 4 | 90
16 | Construction of approach road to new Pangsha | 90 | 2013-14 | 2014-15 | 95.5556 | 0 | 86 | 4 | 90
Appendix-IX
Commitment of the Government-list of Incomplete capital works -Contd.
(` in lakh)
SL. No. | Name of the Project/ Works | Estimated cost of work/ date of Sanction | Year of commen-cement | Target year of completion | Physical progress of work (in per cent) | Expen-diture during the year | Progressive expenditure to the end of the year | Pending Payments | Revised cost if any/date of revision
17 | Tourist rest house between Sanglao | 90 | 2013-14 | 2014-15 | 95.5556 | 0 | 86 | 4 | 90
18 | Improvement and black topping of church road at Shamator | 90 | 2013-14 | 2014-15 | 95.5556 | 0 | 86 | 4 | 90
19 | Construction of 4 staff quarters type-III at Amahator EAC HQ. | 90 | 2013-14 | 2014-15 | 95.5556 | 0 | 86 | 4 | 90
20 | Black topping of road from NH 155 Jn. to Kiphire village | 90 | 2013-14 | 2014-15 | 95.5556 | 0 | 86 | 4 | 90
|  | 1800 |  |  |  | 0 | 1720 | 80 | 1800
1 | District Institute for Education and Training (DIET), Mokokchung | 469.56 | 2012-13 | 2020-21 | 72.3145 | 0 | 339.56 | 130 | 469.56
2 | District Institute for Education and Training (DIET), Tuensang | 937.56 | 2012-13 | 2020-21 | 0 | 0 | 0 | 937.56 | 937.56
3 | Block Institute of Teacher Education (BITE) Aboi | 485.72 | 2015-16 | 2021-22 | 72.48 | 0 | 352.05 | 133.67 | 485.72
4 | Block Institute of Teacher Education (BITE) Medziphema | 421.1 | 2015-16 | 2021-22 | 72.4863 | 0 | 305.24 | 115.86 | 421.1
5 | Block Institute of Teacher Education (BITE) Bhandari | 485.72 | 2015-16 | 2021-22 | 78.1644 | 0 | 379.66 | 106.06 | 523.87
6 | Block Institute of Teacher Education (BITE) Chuchuyimlang | 485.72 | 2012-13 | 2021-22 | 56.7487 | 0 | 275.64 | 210.08 | 485.72
7 | Block Institute of Teacher Education (BITE) Longkhim | 596.05 | 2012-13 | 2021-22 | 52.8328 | 0 | 314.91 | 281.14 | 596.05
8 | Construction of SCERT Directorate Building | 427.7 | 2006-07 | 2011-12 | 93.1665 | 0 | 463 | 33.96 | 496.96
|  | 4309.13 |  |  |  | 0 | 2430.06 | 1948.33 | 4416.54
Appendix-IX
Commitment of the Government-list of Incomplete capital works -Contd.
(` in lakh)
SL. No. | Name of the Project/ Works | Estimated cost of work/ date of Sanction | Year of commen-cement | Target year of completion | Physical progress of work (in per cent) | Expen-diture during the year | Progressive expenditure to the end of the year | Pending Payments | Revised cost if any/date of revision
8. Transport Commissioner
1 | Construction of Inspection & Certification Centre, Dimapur | 1440 | 2017-18 | 2018-19 | 41.6667 | 0 | 600 | 840 | 1440
2 | Infrastracture Development for Helicopter Services at Phek, Zunhebhoto, Wokha, and Satoi | 492.38 | 2014-15 | 2016-17 | 65.0676 | 0 | 320.38 | 172 | 492.38
3 | Construction of Special Pool Workshop cum Garrage, Kohima | 475 | 2012-13 | 2016-17 | 73.6842 | 0 | 350 | 125 | 475
4 | Construction of Sub-station cum retiring, Imphal | 138.79 | 2008-09 | 2016-17 | 90.0641 | 0 | 125 | 13.79 | 172.58
5 | Construction of bus and truck Terminus, Peren | 873.86 | 2013-14 | 2016-17 | 62.7824 | 0 | 548.63 | 325.23 | 873.86
6 | Construction of ISBT, Kohima | 912.27 | 2008-09 | 2016-17 | 97.8011 | 0 | 892.21 | 20.06 | 912.27
7 | Construction of Helipad at Chumukedima Phase I | 497.96 | 2019-20 | 2021-22 | 0 | 0 | 0 | 497.96 | 497.96
|  | 4830.26 |  |  |  | 0 | 2836.22 | 1994.04 | 4864.05
9. Public Works Department (P.W.D) (Housing)
1 | Construction of Nagaland Cricket Stadium, Sovima | 1031 | 2009-10 | 2011-12 | 72.7449 | 0 | 750 | 281 | 1031
2 | Construction of Cricketer’s Hostel at Sovima | 807 | 2009-10 | 2011-12 | 80.5452 | 0 | 650 | 157 | 807
3 | Development of Playground at Pfutsero | 350 | 2009-10 | 2011-12 | 42.8571 | 0 | 150 | 200 | 350
4 | Construction of Multipurpose Hall at Longleng | 1170.42 | 2009-10 | 2011-12 | 35.2933 | 0 | 413.08 | 757.34 | 1170.42
Appendix-IX
Commitment of the Government-list of Incomplete capital works -Contd.
(` in lakh)
SL. No. | Name of the Project/ Works | Estimated cost of work/ date of Sanction | Year of commen-cement | Target year of completion | Physical progress of work (in per cent) | Expen-diture during the year | Progressive expenditure to the end of the year | Pending Payments | Revised cost if any/date of revision
5 | Construction of 11 (eleven ) Minister's bangalow | 3482.16 | 2012-13 | 2014-15 | 90.473 | 0 | 3673.06 | 386.78 | 4059.84
6 | Construction of EE (R&B) Office at Baghty | 74.81 | 2006-07 | 2020-21 | 32.7496 | 0 | 24.5 | 50.31 | 74.81
7 | Construction of Addl. Floor Civil Secretariat, Kohima | 1236.82 | 2013-14 | 2015-16 | 89.7705 | 0 | 1110.3 | 126.52 | 1236.82
8 | Construction of ME office building & workshop at Tuensang | 67.82 | 2007-08 | 2018-19 | 41.2858 | 0 | 28 | 39.82 | 138.07
9 | Construction of EE (R&B) office, Pughoboto | 99.06 | 2017-18 | 2019-20 | 33.3131 | 0 | 33 | 66.06 | 99.06
10 | Construction of SE quarter at Zunheboto | 75.11 | 2013-14 | 2019-20 | 52.9224 | 0 | 39.75 | 35.36 | 75.11
11 | Construction of SDO (R&B) quarter, Satakha | 53.07 | 2009-10 | 2019-20 | 88.5623 | 0 | 47 | 6.07 | 53.07
12 | Construction of EE, PWD (R&B) office Bldg Noklak | 132.54 | 2016-17 | 2018-19 | 19.9638 | 0 | 26.46 | 106.08 | 338.04
13 | Construction of external security fencing and internal boundary wall (ancillary works Ph I a) (construction of internal boundery wal,l compound drainage, retaining wall and portion of external fancing) for 11 ministers qrts Thizama | 478.88 | 2017-18 | 2019-20 | 20.8821 | 0 | 100 | 378.88 | 478.88
14 | Construction of parking area, internal approch road and compound side developmnt (anillary works Ph I) | 287 | 2017-18 | 2019-20 | 59.2334 | 0 | 170 | 117 | 287
Appendix-IX
Commitment of the Government-list of Incomplete capital works -Contd.
(` in lakh)
SL. No. | Name of the Project/ Works | Estimated cost of work/ date of Sanction | Year of commen-cement | Target year of completion | Physical progress of work (in per cent) | Expen-diture during the year | Progressive expenditure to the end of the year | Pending Payments | Revised cost if any/date of revision
15 | Construction of RCC triple storied rental housing building (Ty. B) Ph III (3 blocks) Near Stadium near PWD colony, Dimapur | 474.3 | 2014-15 | 2016-17 | 96.4158 | 0 | 457.3 | 17 | 474.3
16 | Construction of PWD Office Complex at Mokokchung | 773.81 | 2010-11 | 2016-17 | 92.2707 | 0 | 714 | 59.81 | 773.81
17 | Construction of Rental Housing Phase-IV at Dimapur (incomplete due to land dispute) | 742 | 2014-15 | 2016-17 | 61.434 | 0 | 455.84 | 286.16 | 742
18 | Construction of Staff Housing Flat Type at Kohima | 204.17 | 2014-15 | 2016-17 | 73.4682 | 0 | 150 | 54.17 | 204.17
19 | Construction of Rental Housing Phase-III at Dimapur | 631 | 2014-15 | 2016-17 | 91.4422 | 0 | 577 | 54 | 631
20 | Contruction of SP office Building for DEF wokha | 350 | 2020-21 | 2022-23 | 26.6971 | 93.44 | 93.44 | 256.56 | 0
21 | Contruction of culvert/protection wall for Officer Colony junction, Quarter Guard junction and Office Building junction at 7th NAP Bn Bhandari | 80 | 2022-23 | 2022-23 | 9.875 | 7.9 | 7.9 | 72.1 | 0
|  | 12600.97 |  |  |  | 101.34 | 9670.63 | 3508.02 | 13024.4
10. Medical Engineering Division
1 | Upgradation of District Hospital, Phek | 1282 | 2009-10 | 2011-12 | 15.6006 | 0 | 200 | 1082 | 1282
2 | Upgradation of District Hospital, Kiphire | 1400 | 2009-10 | 2011-12 | 1.4286 | 0 | 20 | 1380 | 1400
|  | 2682 |  |  |  | 0 | 220 | 2462 | 2682
Appendix-IX
Commitment of the Government-list of Incomplete capital works -Contd.
(` in lakh)
SL. No. | Name of the Project/ Works | Estimated cost of work/ date of Sanction | Year of commen-cement | Target year of completion | Physical progress of work (in per cent) | Expen-diture during the year | Progressive expenditure to the end of the year | Pending Payments | Revised cost if any/date of revision
11. Veterinary and Animal Husbandry
1 | Reno of DVO office building at Dimapur | 30 | 2012-13 | 2013-14 | 80 | 0 | 24 | 6 | 30
2 | Construction of Veterinary Health Centre at Dihoma | 15 | 2012-13 | 2014-15 | 76.6667 | 0 | 11.5 | 3.5 | 15
3 | Construction of Main Gate S/Fencing half brick wall and barbed wire around DOV quarter & Main Gate at Bayavu Kohima | 13.64 | 2013-14 | 2014-15 | 100 | 0 | 13.64 | 0 | 13.64
4 | Construction of VOP Building at Athibong | 16 | 2011-12 | 2012-13 | 68.75 | 0 | 11 | 5 | 16
5 | Construction of Veterinary Hospital at Jalukie Peren | 43 | 2012-13 | 2015-16 | 60.4651 | 0 | 26 | 17 | 43
6 | Construction Piggery Farm, Repair of Piggery Building at Poilwa Piggery Farm | 50 | 2012-13 | 2015-16 | 86 | 0 | 43 | 7 | 50
7 | Construction of VFA Quarter at Englan | 15.38 | 2013-14 | 2015-16 | 90.2471 | 0 | 13.88 | 1.5 | 15.38
8 | Construction of Veterinary Health Centre at Seyochang | 18.3 | 2012-13 | 2015-16 | 67.2131 | 0 | 12.3 | 6 | 18.3
9 | R/R of SM Building & Providing S/Fencing at Kashiram, Dimapur | 12 | 2011-12 | 2012-13 | 50 | 0 | 6 | 6 | 12
10 | Construction of Gate, App/Road, Ring Well with Jet Pump & Brick S/fencing at Girl Hostel Medziphema | 43.75 | 2013-14 | 2015-16 | 93.1429 | 0 | 40.75 | 3 | 43.75
Appendix-IX
Commitment of the Government-list of Incomplete capital works -Contd.
(` in lakh)
SL. No. | Name of the Project/ Works | Estimated cost of work/ date of Sanction | Year of commen-cement | Target year of completion | Physical progress of work (in per cent) | Expen-diture during the year | Progressive expenditure to the end of the year | Pending Payments | Revised cost if any/date of revision
11 | Construction of SDVO Office Building at Mongkolemba | 18.78 | 2013-14 | 2015-16 | 92.0128 | 0 | 17.28 | 1.5 | 18.78
12 | Construction of Type – I Quarter at Molungkimong | 8.47 | 2013-14 | 2015-16 | 88.1936 | 0 | 7.47 | 1 | 8.47
13 | Construction of SMC building at Tamlu | 17 | 2012-13 | 2014-15 | 58.8235 | 0 | 10 | 7 | 17
14 | Construction of S/Fencing around Veterinary Complex at Longleng | 24.25 | 2013-14 | 2015-16 | 93.8144 | 0 | 22.75 | 1.5 | 24.25
15 | Construction of Veterinary Health Centre at Pathso, Nokeng | 17.3 | 2013-14 | 2015-16 | 59.5376 | 0 | 10.3 | 7 | 17.3
16 | Construction of VHC building at Noksen | 22.25 | 2013-14 | 2015-16 | 93.2584 | 0 | 20.75 | 1.5 | 22.25
17 | Construction of VHC building at Noklak | 22.25 | 2013-14 | 2015-16 | 100 | 0 | 22.25 | 0 | 22.25
18 | Construction of QCP at Pansha | 15.8 | 2013-14 | 2015-16 | 90.5063 | 0 | 14.3 | 1.5 | 15.8
19 | R/Renovation of VHC at Satakha | 5 | 2013-14 | 2014-15 | 70 | 0 | 3.5 | 1.5 | 5
20 | Construction of Deputy Director Quarter at Phghoboto | 23.3 | 2013-14 | 2015-16 | 93.5622 | 0 | 21.8 | 1.5 | 23.3
21 | Construction of Veterinary Health Centre at Sanyu | 18.3 | 2012-13 | 2014-15 | 50.8197 | 0 | 9.3 | 9 | 18.3
22 | Construction of QCP Building at Naginimora | 14.53 | 2013-14 | 2015-16 | 89.6765 | 0 | 13.03 | 1.5 | 14.53
23 | Construction of QCP Building at Chen | 14.53 | 2013-14 | 2015-16 | 89.6765 | 0 | 13.03 | 1.5 | 14.53
Appendix-IX
Commitment of the Government-list of Incomplete capital works -Contd.
(` in lakh)
SL. No. | Name of the Project/ Works | Estimated cost of work/ date of Sanction | Year of commen-cement | Target year of completion | Physical progress of work (in per cent) | Expen-diture during the year | Progressive expenditure to the end of the year | Pending Payments | Revised cost if any/date of revision
24 | Providing S/Fencing at Pig Breeding Farm Suthazu | 11.76 | 2013-14 | 2014-15 | 87.2449 | 0 | 10.26 | 1.5 | 11.76
25 | Construction security fencing (B/W) around SMC at Chunlikha, Tseminyu | 8 | 2011-12 | 2013-14 | 68.75 | 0 | 5.5 | 2.5 | 8
26 | Construction of Dispensary Building at Chizami | 22.16 | 2013-14 | 2015-16 | 93.231 | 0 | 20.66 | 1.5 | 22.16
27 | Construction of VOP Building at Monyakshu, Mon | 113.98 | 2010-11 | 2011-12 | 1.7547 | 0 | 2 | 111.98 | 113.98
28 | Construction of QCP Building at Bhandari, Wokha | 8.67 | 2010-11 | 2011-12 | 51.9031 | 0 | 4.5 | 4.17 | 8.67
29 | Construction of QCP Building and Staff quarter at Khezakeno | 30 | 2008-09 | 2011-12 | 100 | 0 | 30 | 0 | 43.65
30 | Construction of New Directorate building, Main Gate & Boundary wall at New Secretariat complex, Kohima, Nagaland | 3646.79 | 2011-12 | 2016-17 | 56.1258 | 0 | 2046.79 | 1600 | 3646.79
31 | Construction of Security Fencing & Reno of Office Building and Staff Quarters at Jakhama, Kohima | 25 | 2011-12 | 2012-13 | 52 | 0 | 13 | 12 | 25
32 | Construction of security fencing at Dispy Building Chiephobozou | 15 | 2011-12 | 2013-14 | 80 | 0 | 12 | 3 | 15
33 | Construction of main Gate, security fencing with Half bricks wall and Barbed wire around DOV Quarter R/Reno of Building at Bayavu | 20.54 | 2014-15 | 2016-17 | 92.6972 | 0 | 19.04 | 1.5 | 20.54
Appendix-IX
Commitment of the Government-list of Incomplete capital works -Contd.
(` in lakh)
SL. No. | Name of the Project/ Works | Estimated cost of work/ date of Sanction | Year of commen-cement | Target year of completion | Physical progress of work (in per cent) | Expen-diture during the year | Progressive expenditure to the end of the year | Pending Payments | Revised cost if any/date of revision
34 | Construction of Vety Health Centre at Chedema | 18 | 2014-15 | 2015-16 | 91.6667 | 0 | 16.5 | 1.5 | 18
35 | Renovation of DOV quarter at upper Bayavu, Kohima | 6.9 | 2013-14 | 2015-16 | 78.2609 | 0 | 5.4 | 1.5 | 6.9
36 | Renovation Dispensary building & security fencing , Botsa | 7.4 | 2013-14 | 2014-15 | 79.7297 | 0 | 5.9 | 1.5 | 7.4
37 | Construction of VOP Yaogyimsen | 14.85 | 2013-14 | 2016-17 | 52.862 | 0 | 7.85 | 7 | 14.85
38 | Construction of SMC Building at Tamlu | 17 | 2013-14 | 2016-17 | 58.8235 | 0 | 10 | 7 | 17
39 | Construction of Veterinary Health Centre, Panthso Nokeng | 17.3 | 2013-14 | 2016-17 | 59.5376 | 0 | 10.3 | 7 | 17.3
40 | Renovation of staff quarter at Sakhabama | 5 | 2012-13 | 2013-14 | 60 | 0 | 3 | 2 | 5
41 | Construction of security fencing DOV office Building, Kohima | 25 | 2011-12 | 2012-13 | 72 | 0 | 18 | 7 | 25
42 | Construction of VAS Qtr (Type-V at Tobu, Mon District | 25.08 | 2014-15 | 2016-17 | 94.0191 | 0 | 23.58 | 1.5 | 25.08
43 | Construction of Staff Quarter Type-I,II and III at Phusachodu Village, Phek | 10 | 2013-14 | 2016-17 | 50 | 0 | 5 | 5 | 10
44 | Providing Security fencing at Pig Breeding Farm, Suthazu | 11.76 | 2014-15 | 2016-17 | 87.2449 | 0 | 10.26 | 1.5 | 11.76
45 | Construction of Dispensary Building at Khezakenoma | 43.65 | 2008-09 | 2016-17 | 72.1649 | 0 | 31.5 | 12.15 | 43.65
46 | Construction of QCP Building at Avankhu (ITC) | 15 | 2014-15 | 2016-17 | 90 | 0 | 13.5 | 1.5 | 15
Appendix-IX
Commitment of the Government-list of Incomplete capital works -Contd.
(` in lakh)
SL. No. | Name of the Project/ Works | Estimated cost of work/ date of Sanction | Year of commen-cement | Target year of completion | Physical progress of work (in per cent) | Expen-diture during the year | Progressive expenditure to the end of the year | Pending Payments | Revised cost if any/date of revision
47 | Repair & Renovation of Type-III (2 Nos) and Goatery Shed (2 Nos) at Goatery Farm, Sanis | 11.5 | 2012-13 | 2013-14 | 65.2174 | 0 | 7.5 | 4 | 11.5
48 | Construction of New building Type-V DVO quarter at Kiphirie | 27 | 2011-12 | 2013-14 | 77.7778 | 0 | 21 | 6 | 27
49 | Repair & Renovation of Dispensary building at Pungro | 5 | 2012-13 | 2013-14 | 60 | 0 | 3 | 2 | 5
50 | Construction of security fencing around Chilling unit Dairy at Chuchuyimlang | 14 | 2011-12 | 2012-13 | 85.7143 | 0 | 12 | 2 | 14
51 | Construction of QCP at Zhamai | 10.24 | 2012-13 | 2014-15 | 51.1719 | 0 | 5.24 | 5 | 10.24
52 | Construction of water tank , Pultry farm & Vety Hospital at Longleng | 12 | 2011-12 | 2012-13 | 66.6667 | 0 | 8 | 4 | 12
|  | 4677.41 |  |  |  | 0 | 2769.11 | 1908.3 | 4691.06
12. Urban Development
1 | Storm Water Management of Kohima City | 1113.01 | 2017-18 | 2018-19 | 73.3569 | 0 | 816.47 | 296.54 | 1358.01
2 | Construction of Footpath in Dimapur Town | 768.58 | 2017-18 | 43392 | 87.071 | 0 | 669.21 | 99.37 | 899.57
3 | Construction of Cultural Hall at Kohima, Nagaland | 1760.47 | 2009-10 | 2011-12 | 83.4908 | 0 | 1469.83 | 290.64 | 1760.47
4 | Construction of Amenity Centre at Golaghat road, Dimapur | 76.4 | 2009-10 | 2011-12 | 49.9869 | 0 | 38.19 | 38.21 | 76.4
Appendix-IX
Commitment of the Government-list of Incomplete capital works -Contd.
(` in lakh)
SL. No. | Name of the Project/ Works | Estimated cost of work/ date of Sanction | Year of commen-cement | Target year of completion | Physical progress of work (in per cent) | Expen-diture during the year | Progressive expenditure to the end of the year | Pending Payments | Revised cost if any/date of revision
5 | Construction of Shopping Complex cum car parking at Tamlu | 932 | 2008-09 | 2011-12 | 65.882 | 0 | 614.02 | 317.98 | 932
6 | Roads & Transportation Project in Kohima | 2525.6 | 2008-09 | 2011-12 | 46.3973 | 0 | 1171.81 | 1353.79 | 2525.6
7 | Integrated Roads & Multilevel Parking Project in Kohima | 5042.23 | 2009-10 | 2011-12 | 20.2192 | 0 | 1019.5 | 4022.73 | 5042.23
8 | Housing for Urban poor in Dimapur under IHSDP | 8774.04 | 2007-08 | 2011-12 | 41.7492 | 0 | 3663.09 | 5110.95 | 8774.04
|  | 20992.33 |  |  |  | 0 | 9462.12 | 11530.21 | 21368.32
13. C.A.W.D.
1 | Construction of Flat Type Building for ADC’s Staff at Shamator (Type B4 units 1 No) | 135.23 | 2014-15 | 2019-20 | 66.7381 | 0 | 90.25 | 44.98 | 135.23
2 | Construction of Guest House at Noklak | 72 | 2013-14 | 2014-15 | 95.5556 | 0 | 68.8 | 3.2 | 72
3 | Construction of Guest House at Longkhim | 72 | 2013-14 | 2014-15 | 95.5556 | 0 | 68.8 | 3.2 | 72
4 | Construction of Guest House at Noksen | 72 | 2013-14 | 2014-15 | 95.5556 | 0 | 68.8 | 3.2 | 72
5 | Construction of Guest House at Chare | 51.3 | 2013-14 | 2014-15 | 95.5556 | 0 | 49.02 | 2.28 | 51.3
6 | Construction of Guest House at Sangsangyu | 51.3 | 2013-14 | 2014-15 | 95.5556 | 0 | 49.02 | 2.28 | 51.3
Appendix-IX
Commitment of the Government-list of Incomplete capital works -Contd.
(` in lakh)
SL. No. | Name of the Project/ Works | Estimated cost of work/ date of Sanction | Year of commen-cement | Target year of completion | Physical progress of work (in per cent) | Expen-diture during the year | Progressive expenditure to the end of the year | Pending Payments | Revised cost if any/date of revision
7 | Construction of Guest House at Sotokur | 51.3 | 2013-14 | 2014-15 | 95.5556 | 0 | 49.02 | 2.28 | 51.3
8 | Construction of Guest House at Tizit | 55.8 | 2013-14 | 2014-15 | 95.5556 | 0 | 53.32 | 2.48 | 55.8
9 | Construction of Guest House at Angjangyang | 55.8 | 2013-14 | 2014-15 | 95.5556 | 0 | 53.32 | 2.48 | 55.8
10 | Construction of Guest House at Chen | 55.8 | 2013-14 | 2014-15 | 95.5556 | 0 | 53.32 | 2.48 | 55.8
11 | Construction of Guest House at Monyakshu | 46.8 | 2013-14 | 2014-15 | 95.5556 | 0 | 44.72 | 2.08 | 46.8
12 | Construction of Guest House at Yachem | 51.3 | 2013-14 | 2014-15 | 95.5556 | 0 | 49.02 | 2.28 | 51.3
13 | Construction of GA Quarter at Panso | 27 | 2013-14 | 2014-15 | 95.5556 | 0 | 25.8 | 1.2 | 27
14 | Construction of GA Quarter at Mangko | 27 | 2013-14 | 2014-15 | 95.5556 | 0 | 25.8 | 1.2 | 27
15 | Construction of GA Quarter at Phomching | 27 | 2013-14 | 2014-15 | 95.5556 | 0 | 25.8 | 1.2 | 27
16 | Construction of GA Quarter at Wakching HQ | 27 | 2013-14 | 2014-15 | 95.5556 | 0 | 25.8 | 1.2 | 27
17 | Construction of GA Quarter at Aboi | 27 | 2013-14 | 2014-15 | 95.5556 | 0 | 25.8 | 1.2 | 27
18 | Construction of GA Quarter at Shangnyu | 27 | 2013-14 | 2014-15 | 95.5556 | 0 | 25.8 | 1.2 | 27
19 | Construction of GA Quarter at Sitimi | 27 | 2013-14 | 2014-15 | 95.5556 | 0 | 25.8 | 1.2 | 27
20 | Construction of GA Quarter at Khonsa | 27 | 2013-14 | 2014-15 | 95.5556 | 0 | 25.8 | 1.2 | 27
21 | Construction of GA Quarter at Kiusium | 27 | 2013-14 | 2014-15 | 95.5556 | 0 | 25.8 | 1.2 | 27
Appendix-IX
Commitment of the Government-list of Incomplete capital works -Contd.
(` in lakh)
SL. No. | Name of the Project/ Works | Estimated cost of work/ date of Sanction | Year of commen-cement | Target year of completion | Physical progress of work (in per cent) | Expen-diture during the year | Progressive expenditure to the end of the year | Pending Payments | Revised cost if any/date of revision
22 | Construction of GA Quarter atTamlu | 27 | 2013-14 | 2014-15 | 95.5556 | 0 | 25.8 | 1.2 | 27
23 | Construction of Girls Hostel at Wangkhao College, Mon | 54 | 2013-14 | 2014-15 | 95.5556 | 0 | 51.6 | 2.4 | 54
24 | Construction of Girls Hostel at GHS Noksen | 58.5 | 2013-14 | 2014-15 | 95.5556 | 0 | 55.9 | 2.6 | 58.5
25 | Construction of Library Hall at Tuensang town | 45 | 2013-14 | 2014-15 | 95.5556 | 0 | 43 | 2 | 45
26 | Construction of Library Hall at Mon town | 45 | 2013-14 | 2014-15 | 95.5556 | 0 | 43 | 2 | 45
27 | Construction of Library Hall at Kiphire town | 45 | 2013-14 | 2014-15 | 95.5556 | 0 | 43 | 2 | 45
28 | Construction of Library Hall at Longleng town | 45 | 2013-14 | 2014-15 | 95.5556 | 0 | 43 | 2 | 45
29 | Construction of Library Hall at Shamatore town | 45 | 2013-14 | 2014-15 | 95.5556 | 0 | 43 | 2 | 45
30 | Construction of Library Hall at Noklak town | 45 | 2013-14 | 2014-15 | 95.5556 | 0 | 43 | 2 | 45
|  | 1423.13 |  |  |  | 0 | 1320.91 | 102.22 | 1423.13
14. Power Department
1 | Development of 220kv downstream connectivity from 400kv sub-station at Zakhama to the State owned 220kv Station at Zhadima | 1387 | 2020-21 | 2021-22 | 81.5941 | 0 | 1131.71 | 255.29 | 1387
2 | Construction of 220kv D/C T/L from Dimapur to Zhadima | 10815.89 | 2016-17 | 2020-21 | 81.206 | 0 | 8783.15 | 2032.74 | 10815.89
|  | 12202.89 |  |  |  | 0 | 9914.86 | 2288.03 | 12202.89
Appendix-IX
Commitment of the Government-list of Incomplete capital works -Contd.
(` in lakh)
SL. No. | Name of the Project/ Works | Estimated cost of work/ date of Sanction | Year of commen-cement | Target year of completion | Physical progress of work (in per cent) | Expen-diture during the year | Progressive expenditure to the end of the year | Pending Payments | Revised cost if any/date of revision
15. Police Engineering Project
1 | Construction of permanent Headquarters for 10th NAP(IR) Bn at Zhadima under HUDCO | 6863.12 | 2004-05 | 2009-10 | 56.4796 | 0 | 3876.26 | 2986.86 | 6863.12
2 | Construction of permanent Headquarters for 11th NAP (IR) Bn at Aboi under HUDCO | 9387.91 | 2009-10 | 2014-15 | 8.5216 | 0 | 800 | 8587.91 | 9387.91
3 | Construction of permanent Headquarters for 12th NAP (IR) Bn at Chingtok under HUDCO | 9787.62 | 2009-10 | 2014-15 | 8.1736 | 0 | 800 | 8987.62 | 9787.62
4 | Construction of permanent Headquarters for 13th NAP (IR) Bn at Yachang under HUDCO | 9842.74 | 2009-10 | 2014-15 | 14.2237 | 0 | 1400 | 8442.74 | 9842.74
5 | Construction of permanent Headquarters for 14th NAP (IR) Bn at Okhezong under HUDCO | 12118.95 | 2009-10 | 2014-15 | 6.6012 | 0 | 800 | 11318.95 | 12118.95
6 | Construction of Type-1 Quarters for PS Bhandari (Type-1 Semi-Permanent, Type 1 flat-4 unit, 1 no of Barrack (48*22), protection wall) | 153.97 | 2014-15 | 2015-16 | 0 | 0 | 0 | 153.97 | 153.97
7 | Construction of Type-1 Quarters at Doyang (1 no of Barrack) | 30 | 2014-15 | 2015-16 | 0 | 0 | 0 | 30 | 30
Appendix-IX
Commitment of the Government-list of Incomplete capital works -Contd.
(` in lakh)
SL. No. | Name of the Project/ Works | Estimated cost of work/ date of Sanction | Year of commen-cement | Target year of completion | Physical progress of work (in per cent) | Expen-diture during the year | Progressive expenditure to the end of the year | Pending Payments | Revised cost if any/date of revision
8 | Construction of Type-1 Quarters for PS Ralan (Type 1 flat-2 units, 1 no of Barrack (34*22) | 66.03 | 2014-15 | 2015-16 | 0 | 0 | 0 | 66.03 | 66.03
9 | Construction of Type-1 Quarters at Check Gate Lanye Barrack (34*22) | 24.3 | 2014-15 | 2015-16 | 0 | 0 | 0 | 24.3 | 24.3
10 | Construction of Type-1 Quarters at PS Chizami Barrack (48*22) | 40 | 2014-15 | 2015-16 | 0 | 0 | 0 | 40 | 40
11 | Construction of Type-1 Quarters at OP Cheteba Barrack (34*22) | 25.99 | 2014-15 | 2015-16 | 0 | 0 | 0 | 25.99 | 25.99
12 | Construction of Type-1 Quarters at PS Athibung (Type-1 flat units, Barrack (24*15) | 50 | 2014-15 | 2015-16 | 0 | 0 | 0 | 50 | 50
13 | Construction of Type-1 Quarters at PS Tenning Barrack (34*22) | 21.5 | 2014-15 | 2015-16 | 0 | 0 | 0 | 21.5 | 21.5
14 | Construction of Type-1 Quarters at OP Heningkunglwa Barrack (34*22) | 22.96 | 2014-15 | 2015-16 | 0 | 0 | 0 | 22.96 | 22.96
15 | Construction of Type-1 Quarters at PS Mangkolemba (Type 1 flat 2 units) | 50 | 2014-15 | 2015-16 | 0 | 0 | 0 | 50 | 50
16 | Construction of Type-1 Quarters at PS Dhansaripar (Type 1 flat 4 units) | 75 | 2014-15 | 2015-16 | 0 | 0 | 0 | 75 | 75
17 | Construction of Type-1 Quarters at OP Niuland (Type-1 flat 4 units) | 75 | 2014-15 | 2015-16 | 0 | 0 | 0 | 75 | 75
18 | Construction of Type-1 Quarters at Dimapur | 45 | 2014-15 | 2015-16 | 0 | 0 | 0 | 45 | 45
Appendix-IX
Commitment of the Government-list of Incomplete capital works -Contd.
(` in lakh)
SL. No. | Name of the Project/ Works | Estimated cost of work/ date of Sanction | Year of commen-cement | Target year of completion | Physical progress of work (in per cent) | Expen-diture during the year | Progressive expenditure to the end of the year | Pending Payments | Revised cost if any/date of revision
19 | Construction of Type-1 Quarters at Bhandari (7th NAP CO Quarter) | 55 | 2014-15 | 2015-16 | 0 | 0 | 0 | 55 | 55
|  | 48735.09 |  |  |  | 0 | 7676.26 | 41058.83 | 48735.09
16. Directorate of Evaluation
1 | Construction of flat type staff quarter at Kohima | 111 | 2015-16 | 2016-17 | 90.0901 | 0 | 100 | 11 | 111
|  | 111 |  |  |  | 0 | 100 | 11 | 111
17. Youth Resources and Sports
1 | Dev. of Playground at Pfutsero | 349.88 | 2009-10 | 2011-12 | 70.1066 | 0 | 350 | 149.24 | 499.24
2 | Construction of Multi-Disciplinary Sports Complex, Dimapur | 13499.41 | 2007-08 | 2011-12 | 60.739 | 0 | 8199.41 | 5300 | 13499.41
3 | Construction of Multi-Disciplinary Sports Complex, Dimapur ( Site Grading ) | 1830 | 2006-07 | 2007-08 | 51.4208 | 0 | 941 | 889 | 1830
4 | Construction of Music Academy and Performing Arts at Kohima | 1780.2 | 2007-08 | 2011-12 | 50.7491 | 0 | 1437.5 | 1395.06 | 2832.56
|  | 17459.49 |  |  |  | 0 | 10927.91 | 7733.3 | 18661.21
18. Directorate of School Education
1 | Construction of GHSS Mon, Mon district | 251 | 2010-11 | 2011-12 | 66.1355 | 0 | 166 | 85 | 251
|  | 251 |  |  |  | 0 | 166 | 85 | 251
19. Economics and Statistic
1 | 3 (three) story building, Staff Quarters at Chumukedema | 172 | 2012-13 | 2014-15 | 100 | 0 | 172 | 0 | 172
|  | 172 |  |  |  | 0 | 172 | 0 | 172
Appendix-IX
Commitment of the Government-list of Incomplete capital works -Contd.
(` in lakh)
SL. No. | Name of the Project/ Works | Estimated cost of work/ date of Sanction | Year of commen-cement | Target year of completion | Physical progress of work (in per cent) | Expen-diture during the year | Progressive expenditure to the end of the year | Pending Payments | Revised cost if any/date of revision
20. Social Welfare
1 | Construction of Directorate office building | 792.03 | 2010-11 | 2012-13 | 53.873 | 0 | 925 | 792 | 1717
2 | Construction of Blind School and VTC | 3000 | 2011-12 | 2014-15 | 75 | 0 | 2250 | 750 | 3000
|  | 3792.03 |  |  |  | 0 | 3175 | 1542 | 4717
21. Principal Chief Conservator of Forest
1 | Construction of Shopping Complex and Parking plaza at Forest Colony Dimapur | 1855.65 | 2009-10 | 2012-13 | 68.2969 | 0 | 2955.65 | 1372 | 4327.65
|  | 1855.65 |  |  |  | 0 | 2955.65 | 1372 | 4327.65
22. Water Resources Department
1 | Kiphire Office Building | 170.15 | 2009-10 | 2011-12 | 52.9592 | 0 | 90.11 | 80.04 | 170.15
2 | Longleng Office Building | 168.37 | 2009-10 | 2011-12 | 52.8598 | 0 | 89 | 79.37 | 168.37
3 | 270 Nos of Surface Minor Irrigation Project under PMKSY-Har Khet Ko Pani (CSS) | 20685.21 | 2018-19 | 2021-22 | 0 | 0 | 0 | 20685.21 | 20685.21
|  | 21023.73 |  |  |  | 0 | 179.11 | 20844.62 | 21023.73
23. Employment and Skill Development & Entrepreneurship
1 | MCC Kohima | 37.37 | 2015-16 | 2019-20 | 59.9946 | 0 | 22.42 | 14.95 | 37.37
2 | Construction of Principal and Staff Qtrs. at ITI, TGS, Mon, Dimapur and Kohima | 200 | 2013-14 | 2014-15 | 0 | 0 | 0 | 200 | 200
|  | 237.37 |  |  |  | 0 | 22.42 | 214.95 | 237.37
Appendix-IX
Commitment of the Government-list of Incomplete capital works -Contd.
(` in lakh)
SL. No. | Name of the Project/ Works | Estimated cost of work/ date of Sanction | Year of commen-cement | Target year of completion | Physical progress of work (in per cent) | Expen-diture during the year | Progressive expenditure to the end of the year | Pending Payments | Revised cost if any/date of revision
24. Land Record and Survey
1 | Conference Hall at Directorate | 88.93 | 2015-16 | 2016-17 | 66.2656 | 0 | 58.93 | 30 | 88.93
|  | 88.93 |  |  |  | 0 | 58.93 | 30 | 88.93
25. Department of Prison
1 | Construction of District Jail, Longleng | 720 | 2008-09 | 2009-10 | 73.6111 | 0 | 530 | 190 | 720
|  | 720 |  |  |  | 0 | 530 | 190 | 720
26. Director of Agriculture
1 | New Directorate Building | 15.9 | 2011-12 | 2016-17 | 93.2519 | 0 | 16.03 | 1.16 | 17.19
|  | 15.9 |  |  |  | 0 | 16.03 | 1.16 | 17.19
28. Women Resource Development
1 | Multi-purpose Training and Marketing Complex | 825 | 2010-11 | 2015-16 | 55.6364 | 0 | 459 | 366 | 825
2 | Women Resource Centre, Peren | 300 | 2013-14 | 2015-16 | 46.6667 | 0 | 140 | 160 | 300
3 | Women Resource Centre, Wokha | 300 | 2013-14 | 2015-16 | 46.6667 | 0 | 140 | 160 | 300
4 | Women Resource Centre, Zunheboto | 300 | 2013-14 | 2015-16 | 46.6667 | 0 | 140 | 160 | 300
|  | 1725 |  |  |  | 0 | 879 | 846 | 1725
29. Printing and Stationery Department
1 | Major Repair and Renovation of Government Press Office Building Phase-I, Chandmari, Kohima | 150 | 2016-10-01 | 2018-10-01 | 52.7933 | 0 | 79.19 | 70.81 | 150
|  | 150 |  |  |  | 0 | 79.19 | 70.81 | 150
Appendix-IX
Commitment of the Government-list of Incomplete capital works -Contd.
(` in lakh)
SL. No. | Name of the Project/ Works | Estimated cost of work/ date of Sanction | Year of commen-cement | Target year of completion | Physical progress of work (in per cent) | Expen-diture during the year | Progressive expenditure to the end of the year | Pending Payments | Revised cost if any/date of revision
30. Sericulture Department
1 | Implementation of Farmars Development Programme (FDP) | 559 | 2017-18 | 2019-20 | 66.5116 | 0 | 353.21 | 177.84 | 531.05
2 | Integrated Eri Silk Development Project (IESDP) | 1200.83 | 2016-17 | 2018-19 | 16.6776 | 0 | 200.27 | 1000.56 | 1200.83
3 | State Sericulture Farmers Training Centre | 424 | 2012-13 | 2013-14 | 80.1887 | 0 | 340 | 84 | 424
|  | 2183.83 |  |  |  | 0 | 893.48 | 1262.4 | 2155.88
31. General Administration
1 | Construction of VG Barrack at Nyinyen | 30 | 2013-14 | 2016-17 | 93.3333 | 0 | 28 | 2 | 30
2 | Construction of VG Barrack at Hakchang | 30 | 2013-14 | 2016-17 | 93.3333 | 0 | 28 | 2 | 30
3 | Construction of VG Barrack at Maksha | 30 | 2013-14 | 2016-17 | 93.3333 | 0 | 28 | 2 | 30
4 | Construction of VG Barrack at Chingmellen | 30 | 2013-14 | 2016-17 | 93.3333 | 0 | 28 | 2 | 30
5 | Construction of VG Barrack at Changang | 30 | 2013-14 | 2016-17 | 93.3333 | 0 | 28 | 2 | 30
6 | Construction of VG Barrack at Sipongsang | 30 | 2013-14 | 2016-17 | 93.3333 | 0 | 28 | 2 | 30
7 | Construction of VG Barrack at Kuthur | 30 | 2013-14 | 2016-17 | 93.3333 | 0 | 28 | 2 | 30
8 | Construction of VG Barrack at Huker | 30 | 2013-14 | 2016-17 | 93.3333 | 0 | 28 | 2 | 30
Appendix-IX
Commitment of the Government-list of Incomplete capital works -Contd.
SL. No. | Name of the Project/ Works | Estimated cost of work/ date of Sanction | Year of commen-cement | Target year of completion | Physical progress of work (in per cent) | Expen-diture during the year | Progressive expenditure to the end of the year | Pending Payments | Revised cost if any/date of revision
(` in lakh)
9 | Construction of VG Barrack at Yangoi | 30 | 2013-14 | 2016-17 | 93.3333 | 0 | 28 | 2 | 30
10 | Construction of VG Barrack at Noklak Village | 30 | 2013-14 | 2016-17 | 93.3333 | 0 | 28 | 2 | 30
11 | Construction of VG Barrack at Alisopur | 30 | 2013-14 | 2016-17 | 93.3333 | 0 | 28 | 2 | 30
12 | Construction of VG Barrack at Khucel | 30 | 2013-14 | 2016-17 | 93.3333 | 0 | 28 | 2 | 30
13 | Construction of Commandant VG Office Tuensang | 150 | 2013-14 | 2016-17 | 78.6667 | 0 | 118 | 32 | 150
14 | Construction of VG Barrack at Changiangshou | 30 | 2013-14 | 2016-17 | 93.3333 | 0 | 28 | 2 | 30
15 | Construction of VG Barrack at Changiang | 30 | 2013-14 | 2016-17 | 93.3333 | 0 | 28 | 2 | 30
16 | Construction of VG Barrack at Shancsa Village | 30 | 2013-14 | 2016-17 | 93.3333 | 0 | 28 | 2 | 30
17 | Construction of VG Barrack at Chenwetnyu | 30 | 2013-14 | 2016-17 | 93.3333 | 0 | 28 | 2 | 30
18 | Construction of VG Barrack at Totok Chingnyu | 30 | 2013-14 | 2016-17 | 93.3333 | 0 | 28 | 2 | 30
19 | Construction of VG Barrack at Tangnyu | 30 | 2013-14 | 2016-17 | 93.3333 | 0 | 28 | 2 | 30
20 | Construction of VG Barrack at Sheanghah Wansa | 30 | 2013-14 | 2016-17 | 93.3333 | 0 | 28 | 2 | 30
21 | Construction of VG Barrack at Yaongyimchen | 30 | 2013-14 | 2016-17 | 93.3333 | 0 | 28 | 2 | 30
Appendix-IX
Commitment of the Government-list of Incomplete capital works -Contd.
(` in lakh)
SL. No. | Name of the Project/ Works | Estimated cost of work/ date of Sanction | Year of commen-cement | Target year of completion | Physical progress of work (in per cent) | Expen-diture during the year | Progressive expenditure to the end of the year | Pending Payments | Revised cost if any/date of revision
22 | Construction of VG Barrack at Yongyak | 30 | 2013-14 | 2016-17 | 93.3333 | 0 | 28 | 2 | 30
23 | Construction of VG Barrack at Kyusndong | 30 | 2013-14 | 2016-17 | 93.3333 | 0 | 28 | 2 | 30
24 | Construction of VG Barrack at Zanger Village | 30 | 2013-14 | 2016-17 | 93.3333 | 0 | 28 | 2 | 30
25 | Construction of VG Barrack at Yingphire | 30 | 2013-14 | 2016-17 | 93.3333 | 0 | 28 | 2 | 30
26 | Construction of VG Barrack at Phor EAC Hq. | 30 | 2013-14 | 2016-17 | 93.3333 | 0 | 28 | 2 | 30
|  | 900 |  |  |  | 0 | 818 | 82 | 900
32. Department of Higher Education
1 | Construction of 100 bedded boys hostel at Dimapur College, Dimapur | 410 | 2013-14 | 2015-12-01 | 92.439 | 0 | 379 | 31 | 410
2 | Construction of 2 bedded staff quarter at Phek College, Phek | 200 | 2013-14 | 2014-15 | 75 | 0 | 150 | 50 | 200
3 | Construction of 50 bedded boys hostel at Phek College, Phek | 300 | 2013-14 | 2014-15 | 56.6667 | 0 | 170 | 130 | 300
4 | Construction of 100 bedded boys hostel at Kohima College, Kohima | 400 | 2013-14 | 2015-16 | 62.5 | 0 | 250 | 150 | 400
5 | Construction of conference hall at Peren College, Peren | 120 | 2015-16 | 2016-17 | 75 | 0 | 90 | 30 | 120
6 | Attached to Boys Hostel Sao Chang College, Tuensang | 27 | 2013-14 | 2014-15 | 95.5556 | 0 | 25.8 | 1.2 | 27
Appendix-IX
Commitment of the Government-list of Incomplete capital works -Contd.
(` in lakh)
SL. No. | Name of the Project/ Works | Estimated cost of work/ date of Sanction | Year of commen-cement | Target year of completion | Physical progress of work (in per cent) | Expen-diture during the year | Progressive expenditure to the end of the year | Pending Payments | Revised cost if any/date of revision
7 | Attached to Girls Hostel Sao Chang College, Tuensang | 27 | 2013-14 | 2014-15 | 95.5556 | 0 | 25.8 | 1.2 | 27
8 | Attached to Boys Hostel G.H.S.S, Longkhim | 27 | 2013-14 | 2014-15 | 95.5556 | 0 | 25.8 | 1.2 | 27
9 | Attached to Girls Hostel G.H.S.S, Longkhim | 27 | 2013-14 | 2014-15 | 95.5556 | 0 | 25.8 | 1.2 | 27
10 | Attached to Boys Hostel G.H.S.S, Kiphire | 27 | 2013-14 | 2014-15 | 95.5556 | 0 | 25.8 | 1.2 | 27
11 | Attached to Girls Hostel G.H.S.S, Kiphire | 27 | 2013-14 | 2014-15 | 95.5556 | 0 | 25.8 | 1.2 | 27
12 | Attached to Boys Hostel G.H.S.S, Longleng | 27 | 2013-14 | 2014-15 | 95.5556 | 0 | 25.8 | 1.2 | 27
13 | Attached to Girls Hostel G.H.S.S, Longleng | 27 | 2013-14 | 2014-15 | 95.5556 | 0 | 25.8 | 1.2 | 27
14 | Upgradation of Library Building under infrastructure Grants to Colleges at Dimapur Government College | 200 | 2018-19 | 2021-22 | 0 | 0 | 0 | 200 | 200
15 | Upgradation of classroom under infrastructure Grants to Colleges at FAC, Mokokchung | 200 | 2018-19 | 2021-22 | 0 | 0 | 0 | 200 | 200
16 | Construction of Girls Hostel under infrastructure Grants to Colleges at Kohima College | 200 | 2018-19 | 2021-22 | 0 | 0 | 0 | 200 | 200
Appendix-IX
Commitment of the Government-list of Incomplete capital works -Contd.
(` in lakh)
SL. No. | Name of the Project/ Works | Estimated cost of work/ date of Sanction | Year of commen-cement | Target year of completion | Physical progress of work (in per cent) | Expen-diture during the year | Progressive expenditure to the end of the year | Pending Payments | Revised cost if any/date of revision
17 | Construction of Hostels for ST Girls students under Equity initiative at Kohima Science College, Jotsoma | 500 | 2018-19 | 2021-22 | 0 | 0 | 0 | 500 | 500
18 | Construction of New College under New Model Degree Colleges at Tzupaksa, Mongkolemba | 1200 | 2018-19 | 2021-22 | 0 | 0 | 0 | 1200 | 1200
|  | 3946 |  |  |  | 0 | 1245.4 | 2700.6 | 3946
33. Legal Metrology & Consumer Protection, Kohima
1 | Strengthening of Legal Metrology Infrastructure - Construction of Working Standard Laboratory (WSL) at Mon | 50 | 2015-16 | 2016-17 | 50 | 0 | 25 | 25 | 50
2 | Strengthening of Consumer Fora – Construction of District Consumer Fora Building at Mon | 60 | 2014-15 | 2015-16 | 59.0833 | 0 | 35.45 | 24.55 | 60
3 | Const. of Working Laboratory (WSL) at Longleng, Peren, Kiphirie, Mon &Tuensang | 250 | 2015-16 | 2016-17 | 60 | 0 | 150 | 100 | 250
4 | Construction of District for a (DF) Office Bldg. at Zunheboto, Mon & Tuensang | 200 | 2015-16 | 2016-17 | 87.5 | 0 | 175 | 25 | 200
|  | 560 |  |  |  | 0 | 385.45 | 174.55 | 560
Appendix-IX
Commitment of the Government-list of Incomplete capital works -Contd.
(` in lakh)
SL. No. | Name of the Project/ Works | Estimated cost of work/ date of Sanction | Year of commen-cement | Target year of completion | Physical progress of work (in per cent) | Expen-diture during the year | Progressive expenditure to the end of the year | Pending Payments | Revised cost if any/date of revision
34 | Industries & Commerce
1 | Extension of Hotel Japfu at Kohima | 983.12 | 2013-14 | 2015-16 | 0 | 0 | 0 | 0 | 983.12
2 | Construction of Nagaland Emporium at Kohima | 986.53 | 2013-14 | 2015-16 | 0 | 0 | 0 | 0 | 986.53
3 | Construction of Boundary Wall & Maingate at NMBC, Toluvi, Dimapur | 75 | 2022-23 | 2023-24 | 46 | 34.98 | 34.98 | 0 | 75
4 | Repair & Renovation of District Industires Centre Office, Zunheboto | 25 | 2022-23 | 2023-24 | 46 | 11.66 | 11.66 | 0 | 25
|  | 2069.65 |  |  |  | 46.64 | 46.64 | 0 | 2069.65
| Grand Total | 192850.34 |  |  |  | 165.77 | 84217.29 | 111479.05 | 201117.25

## Sheet2
4 | Construction of Pukhungri-Avankhu-Layshi road | 1042 | 2003-04 | 42095 | 94 | 0 | 2188.87 | 150.13 | 2339
8 | Construction of DUDA Students Hostel at Jotsoma (Phase-I) | 490 | 2013-14 | 42705 | 50 | 0 | 200 | 290 | 490
9 | Construction of DUDA Directorate | 829 | 2012-13 | 42705 | 70 | 0 | 420 | 409 | 829
10 | Completion of DUDA Guest House at Sovima | 450 | 2012-13 | 42705 | 70 | 0 | 200 | 250 | 450
3 | (DRC) District Institute for Education & Training (DIET) Wokha | 811.5 | 2012-13 | 42736 | 50 | 0 | 133 | 678.5 | 811.5
4 | District Institute for Education & Training (DIET) Peren | 648.57 | 2015-16 | 42278 | 50 | 0 | 247.5 | 401.07 | 648.57
5 | District Institute for Education & Training (DIET) Kiphire | 825.61 | 2015-16 | 2016 | 50 | 0 | 349.5 | 476.12 | 825.61
6 | Block Institute of Teacher Education (BITE) Aboi | 485.72 | 2015-16 | 42826 | 50 | 0 | 133.67 | 352.05 | 485.72
7 | Block Institute of Teacher Education (BITE) Medziphema | 421.1 | 2015-16 | 43101 | 50 | 0 | 115.86 | 305.24 | 421.1
8 | Block Institute of Teacher Education (BITE) Akuluto | 570.41 | 2015-16 | 43101 | 40 | 0 | 157.09 | 413.33 | 570.41
9 | Block Institute of Teacher Education (BITE) Bhandari | 523.87 | 2015-16 | 42583 | 20 | 0 | 144.21 | 379.66 | 523.87
10 | Block Institute of Teacher Education (BITE) Sechu | 484.17 | 2012-13 | 42461 | 70 | 0 | 314.9 | 169.27 | 484.17
11 | Block Institute of Teacher Education (BITE) Chuchuyimlang | 485.72 | 2012-13 | 42826 | 80 | 0 | 275.64 | 210.08 | 485.72
12 | Block Institute of Teacher Education (BITE) Longkhim | 596.05 | 2012-13 | 42705 | 80 | 0 | 314.91 | 281.15 | 596.05
13 | Training Hostel, District Institute for Education & Training (DIET) Zunheboto | 400.2 | 2013-14 | 43009 | 80 | 0 | 200 | 200.2 | 400.2
1 | Storm Water Management of Kohima City | 1113.01 | 2017-04-07 | 43379 | 75 | 7.29 | 816.47 | 541.54 | 1358.01
2 | Construction of Storm Drainage at Midland, Kohima (Pkg-1) | 60 | 2017-04-23 | 43212
3 | Construction of Storm Drainage at Midland, Kohima (Pkg-2) | 60 | 2017-04-23 | 43212
4 | Construction of Storm Drainage at Kenuozou, Kohima (Pkg-3) | 10 | 2017-04-23 | 43030
5 | Construction of Storm Drainage at Dzuvuru, Kohima (Pkg-4) | 30 | 2017-04-23 | 43030
6 | Construction of Storm Drainage at High School, Kohima (Pkg-5) | 30 | 2017-04-23 | 43030
7 | Construction of Storm Drainage at Lower Jail, Kohima (Pkg-6) | 55 | 2017-04-23 | 43212
8 | Construction of Footpath in Dimapur Town | 768.58 | 2017-04-20 | 43392 | 80 | 8.88 | 669.21 | 730.79 | 899.57
9 | Construction of Footpath at Zeliangrong Colony, Dimapur (Pkg-7) | 22.41 | 2017-04-23 | 43030
10 | Construction of Footpath at Nagagoan Colony, Dimapur (Pkg-8) | 19.35 | 2017-04-23 | 43030
11 | Construction of Footpath at Lhomithi Colony, Dimapur (Pkg-9) | 9.52 | 2017-04-23 | 43030
12 | Construction of Footpath at Midland Colony, Dimapur (Pkg-10) | 14.78 | 2017-04-23 | 43030
13 | Construction of Footpath at Residency Colony, Dimapur (Pkg-11) | 19.6 | 2017-04-23 | 43030
14 | Construction of Footpath at Aokong Colony, Dimapur (Pkg-12) | 14.87 | 2017-04-23 | 43030
15 | Construction of Footpath at Burma Camp, Dimapur (Pkg-13) | 14.97 | 2017-04-23 | 43030
16 | Construction of Footpath at Kalibari Colony, Dimapur (Pkg-14) | 15.49 | 2017-04-23 | 43030
17 | Supply Order for Septage Management Equipment for Dimapur under AMRUT 2015-16 | 8.79 | 2018-11-27 | 43475 | 70 | 15.89 | 164 | 86 | 165.43
18 | Work order for supply of cesspool cleaner vehicle | 156.64 | 2018-03-22 | 43241
1 | Major Repair and Renovation of Government Press Office Building Phase-I, Chandmari, Kohima | 150 | 42644 | 43374 | 60 | 26.4 | 79.19 | 52.79 | 150
1 | Construction of 100 bedded boys hostel at Dimapur College, Dimapur | 410 | 2013-14 | 42339 | 90 | 144 | 379 | 31 | 410
3 | Construction of Inspection & Certification Centre, Dimapur | 1440 | 42948 | 2018-19 | 95 | 300 | 600 | 0 | 1440
1 | Major Repair and Renovation of Government Press Office Building Phase-I, Chandmari, Kohima | 150 | 42644 | 43374 | 60 | 26.4 | 79.19 | 52.79 | 150