|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| **Period** | **Road Amount (no of works)** | **Bridges Amount (no of works)** | **Building Amount (no of works)** | **Others@ Amount**  **(no of works)** | **Total amount involved** |
| **(₹** **in Lakh)** | | | | | |
| **Upto 2021-22** | **7,21,393.66 (713)** | **3,831.00(16)** | **8,831.00(39)** | **1,54,69,388.00(80)** | **1,62,03,443.66(848)** |
| **2022-23** | **1,03,694.70 (75)** |  | **5,720.00(2)** |  | **1,09,414.70(77)** |
| **2023-24** | **81,366.48 (43)** |  | **19,625.00(4)** | **1,415.00(1)** | **1,02,406.48(48)** |

@ Others categories in addition to Roads, Bridges, Buildings etc., are mentioned for greater granularity as per information in respective State Accounts. 'Others' in the column indicates works in residual categories.

Works with the original estimated cost of 100 Lakhs or more are shown below.

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.NR** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence-ment** | **Target year of completion** | **Physical progress of work (in per**  **cent)** | **Expenditure during the year 2023-24** | **Progressive Expenditure to the end of 31**  **March, 2024** | **Pending payments to the end of 31**  **March, 2024** | **Revised cost, if any and date of sanction** |
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 |
| ***(₹ in lakh)*** | | | | | | | | | |
|  | **Roads** |  |  |  |  |  |  |  |  |
| 1 | Widening & Strengthening of Nallabelli to Girnibavi via Duggondi from Km 10/0 to 18/2 in Warangal Rural District | 1,500.00/  07.06.2023 | 2023 | 2025 | 99% | 1,082.21 | 1,082.21 | 337.91 | - |
| 2 | Widening & Strengthening of NagarKurnool to Gopalpet via Thudukurthy from Km 0/0 to 14/0 in Nagarkurnool Dist.(Balannce works) | 1,800.00  /25.09.2018 | 2018 | 2024 | 70% | - | 1,147.39 | - | 700.00/  06.02.2024 |
| 3 | Construction of HLB at Km 1/8 on Kistampet to Gangaram road via Suddala in Mancherial District | 1,000.00/  28.04.2022 | 2022 | 2024 | 98% | 781.99 | 781.99 | 34.26 | - |
| 4 | Widening and Strengthening of Korepally to Thanugula via Vilasagar from Km 0/0 7/0 in Karimnagar District | 1,000.00/  28.04.2022 | 2022 | 2024 | 40% | - | - | 218.85 | - |
| 5 | Widening and Strengthening of Single Lane to Double Lane Road from Challur to Kesavapatnam (Km 0/0 to  Km 17/0) | 2,500.00/  28.04.2022 | 2022 | 2024 | 80% | 701.99 | 701.99 | 1,024.68 | - |
| 6 | Widening and Strengthening of Single Lane to Double Lane Road from Bavupet (Asifnagar) to Pakirpet to Kurikyala Road from 0/0 to 16/0 Km in Karimnagar  District | 2,400.00/  28.04.2022 | 2022 | 2024 | 5% | - | - | - | - |
| 7 | Widening and Strengthening of Thadikal to Chenjerla via Yeradapalle Road from Km 0/0 to 9/0 in Karimnagar District | 1,350.00/  04.10.2022 | 2022 | 2024 | 50% | 210.55 | 210.55 | 271.98 | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 8 | Widening and Strengthening of Indurthi to Sundaragiri road from Km 0/0 to 10/0 in Karimnagar District | 1,500.00/  04.10.2022 | 2022 | 2024 | 85% | - | - | 130.38 | - |
| 9 | Widening and Strengthening of Indurthi to Husnabad road from Km 0/0 to 16/0 in Karimnagar District | 2,400.00/  04.10.2022 | 2022 | 2024 | 90% | 91.65 | 91.65 | 966.55 | - |
| 10 | Widening and Strengthening of Single Lane road to Double Lane from Medipally to Govindaram in km 0/0 to km 15/0 in Jagtial District | 2,000.00/  28.04.2022 | 2022 | 2024 | 61% | 928.95 | 928.95 | - | - |
| 11 | Widening and strengtheing of Mallial to Pegadapalli road from Km 0/0 to 14/410 in Jagityal district | 2,000.00/  28.04.2022 | 2022 | 2024 | 50% | 412.24 | 412.24 | 442.08 | - |
| 12 | Widening and Strengthening of the road from NH-63 to Rangapet in Km 0/0 to 10/280 in Jagityal District | 1,500.00/  28.04.2022 | 2022 | 2024 | 100% | 1,180.44 | 1,180.44 | - | - |
| 13 | Widening and Strengthening of Kallur to Yousufnagar road from km 0/0 to 10/0 in Jagtial District. | 1,400.00/  28.04.2022 | 2022 | 2024 | 13% | - | - | 187.61 | - |
| 14 | Widening and strengthening of existing single lane road to double lane from Chilvakodur to Sthambampally in Km 0/0 to Km 11/5 in Jagtial District | 1,600.00/  28.04.2022 | 2022 | 2024 | 67% | 355.65 | 355.65 | - | - |
| 15 | Widening & Strengthening of Road to Peddalingapur via Baddenapally, Ramannapally & Baswapur from Km 0/0 to 14/0 in Rajanna Siricilla District | 2,000.00/  28.04.2022 | 2022 | 2024 | 83% | - | - | 815.26 | - |
| 16 | Widening and Strengthening of Lingannapeta to Korutlapet via Mallareddipet from Km 0/0 to 10/200 in Rajanna Siricilla district | 1,500.00/  28.04.2022 | 2022 | 2024 | 30% | - | - | - | - |
| 17 | Widening & Strengthening of PWD Road at Madaka to Gumpula from km 13/800 to 25/800 in Peddapally district | 1,600.00/  28.04.2022 | 2022 | 2024 | 61% | 914.86 | 914.86 | 609.46 | - |
| 18 | Widening and Strengthening of Konijarla- Chinthakani road from Km 0/0 to Km 15/5 in Khammam district | 2,000.00/  28.04.2022 | 2022 | 2024 | 60% | 54.28 | 54.28 | 809.23 | - |
| 19 | Construction of HLB at Eswaramandharam Village at Km 4/8-10 of Bhagavathaveedu - Maddivarigudem road and improvement of connecting road from Rajupeta to Perikasingaram from Km 0/0 to 3/0 in Khammam district | 1,500.00/  28.04.2022 | 2022 | 2024 | 95% | 499.49 | 499.49 | - | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 20 | Widening and Strengthening of Ghanpur - Inavole road via Kunoor , Garnepalli, Ontimamidipalli and Singaram from Km 13/0 to 30/0 in Warangal Urban district | 2,000.00/  28.04.2022 | 2022 | 2024 | 90% | 1,578.65 | 1,578.65 | - | - |
| 21 | Widening and Strengthening Bammera to Zaffargadh via Thammadapally Road from Km 0/0 to 15/0 in Jangaon  district | 1,500.00/  28.04.2022 | 2022 | 2024 | 85% | 1,018.63 | 1,018.63 | - | - |
| 22 | Widening from Single lane to Double lane of Dhantalapally - Peddamupparam - Kuntapally road from Km 0/0 to 10/0 in | 1,400.00/  28.04.2022 | 2022 | 2024 | 55% | 384.13 | 384.13 | - | - |
| 23 | Widening & Strengthening of Kalwakurthy to Raghupatipet road from Km 12/2 to Km 20/0 and Km 12/0 to Km 20/0 of Malkapur to Telkapally road in  Nagarkurnool District | 2,000.00/  28.04.2022 | 2022 | 2024 | 50% | 589.70 | 589.70 | 527.03 | - |
| 24 | Widening & Strengthening of road from NH- 167 to 1) Uppunuthala via Kondareddypally, Polkampally, Dindi Chinthapally from Km 18/2 to 27/0 and 2)DindiChinthapally to Vangoor road via Uppalapahad X  road, Machinanipally from Km 0/0 to 10/0 in Nagarkurnool District | 2,200.00/  28.04.2022 | 2022 | 2024 | 93% | 1,385.02 | 1,385.02 | 542.08 | - |
| 25 | Widening and strengthening of road from Narsaipally cross road to Chennaram Km 0/0 to Km 21/0 via  Mailaram,Kadirepad, Rajapur,Singaipally and Machupally in Kodair Mandal, Nagarkurnool Dist. | 3,000.00/  28.04.2022 | 2022 | 2024 | 45% | - | - | - | - |
| 26 | Widening and Strengthening of 1)Wanaparthy to Pebbair road from Km 3/0 to 19/7 ( for a leangth of 6 Km in Non- Forest strches of the road) and 2) Kothapet X road  (Wanaparthy to Pangal road) to Mahammadapur from Km 0/0 to 4/0 in Wanaparthy District | 1,500.00/  04.10.2022 | 2022 | 2024 | 65% | 851.87 | 851.87 | - | - |
| 27 | Strengthening of Chintapally (on Hyderabad - Nagarjunasagar road) to Padmatpally (on NH- 167) from Km 0/0 to 18/0 and Widening from Single lane to Double lane from Iddampally to NH-167 from Km 0/0 to 5/0 in Nalgonda District | 1,500.00/  28.04.2022 | 2022 | 2024 | 25% | 189.32 | 189.32 | 109.33 | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 28 | Widening & Strengthening of Keethavarigudem - Veldanda - Munagala road from Km 0/0 to Km 18/0 in Suryapet district | 2,000.00/  28.04.2022 | 2022 | 2024 | 90% | 828.72 | 1,231.73 | 587.54 | - |
| 29 | Widening and Strengthening of (1) Suryapet- Nemmikal - Danthalapally road from Km 10/100 to 10/800, Km 25/8- 10 and Km 32/0 6 (2) Widening and Strengthening of Nakrekal- Gurajala road (Shaligowraram to Gurajala) from Km 17/3 to 23/0 (3) Widening and Strengthening of Phanigiri to Shanthinagar road from Km 11/2 to 14/2 in  Suryapet district | 1,500.00/  28.04.2022 | 2022 | 2024 | 40% | 294.09 | 294.09 | - | - |
| 30 | Widening & Strengthening of Choutuppal to Sangem road from Km 0/0 to 13/2 in Yadadri- Bhongir District | 1,800.00/  28.04.2022 | 2022 | 2024 | 32% | 90.16 | 90.16 | 252.45 | - |
| 31 | Widening & Strengthening from single lane to double lane of NH16 to Velpoor (via) Kuknoor, Komanpally road km.0/0 to 9/0 in Nizamabad district | 1,500.00/  28.04.2022 | 2022 | 2024 | 60% | 841.38 | 841.38 | 261.08 | - |
| 32 | Widening & Strengthening of 1) Nizamabad- Warni road from km 15/0 to 19/0 and 2) Improvements to Nizamabad Bypass from Km 0/0 to 4/6 including construction of HLB in Km 4/6 in Nizamabad District. | 2,600.00/  28.04.2022 | 2022 | 2024 | 45% | 1,074.96 | 1,074.96 | - | - |
| 33 | Improvements to Doangoan to Jukkal via Dostpally from Km 0/0 to 8/0 in Kamareddy district | 1,200.00/  28.04.2022 | 2022 | 2024 | 65% | - | - | 268.92 | - |
| 34 | Widening and strengtheing of Shanigaram to Sundaragiri road from Km 0/0 to 12/0 in Siddipet District | 1,800.00/  04.10.2022 | 2022 | 2024 | 65% | 91.54 | 91.54 | 731.67 | - |
| 35 | Widening and Strengthening of Dubbak to Mustabad road via Rajakkapet from Km 0/0 to 8/380 in Siddipet  District. | 1,200.00/  28.04.2022 | 2022 | 2024 | 60% | - | - | 633.53 | - |
| 36 | Widening and Strengthening of Mundrai - Nagarajupally road from Km 0/0 to Km 14/4 in Siddipet District | 2,000.00/  28.04.2022 | 2022 | 2024 | 80% | 1,282.37 | 1,282.37 | 218.56 | - |
| 37 | Widening and Strengthening of Doulathabad to Karnapally (R&B) Road via Gollapally and Karimnagar Villages from Km 0/0 to 10/4 Siddipet District (for a length of 9.4 Km only) | 2,205.00/  04.10.2022 | 2022 | 2024 | 50% | - | - | 736.62 | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 38 | Widening and strengthening of Donti - Malkapur road (via Palata, Potharam, Ramaipally, Yavapur , Narsampally) from Km 0/0 to Km 11/0 including HLB at 9/8-10 in Medak District | 2,000.00/  28.04.2022 | 2022 | 2024 | 85% | 684.79 | 684.79 | 577.25 | - |
| 39 | Improvement to (1) Narayankhed to Masanpally road from Km 0/0 to Km 12/0 (2) Pastapur - Kuppanagar Road from Km 12/6 to Km 14/6 in Sanga Reddy district | 2,000.00/  28.04.2022 | 2022 | 2024 | 0% | - | - | - | - |
| 40 | Widening and strengthening of Shamshabad to Kollapadakala road from Km 7/4 to 22/0 in Ranga Reddy  district | 1,500.00/  28.04.2022 | 2022 | 2024 | 86% | 721.53 | 985.41 | 146.36 | - |
| 41 | Widening and Strengthening RCI gate to Meerkhanpet road via Raviryal, Kongarakalan, Thimmapur,Madhapur, Gummadavally and Akulamylaram from Km 11/4 to Km  34/2 in Rangareddy Dist | 3,000.00/  28.04.2022 | 2022 | 2024 | 98% | 1,903.26 | 1,903.26 | 577.04 | - |
| 42 | Widening & Strengthening of existing Single lane to double lane from Km 10/0 to 26/0 of Kothur - Keshampet road in Ranga Reddy District | 2,000.00/  28.04.2022 | 2022 | 2024 | 90% | 1,050.54 | 1,050.54 | - | - |
| 43 | Widening and strengthening from Km 30/0 to Km 48/0 of Shadnagar - Amangal road | 3,700.00/  28.04.2022 | 2022 | 2024 | 93% | 1,453.15 | 1,453.15 | 830.10 | - |
| 44 | Widening & Strengthening of road from Narapally(NH- 163) to Ranganayaka Swamy Temple at Edulabad village via - Korremul in Medchal-Malkajgiri district | 1,500.00/  28.04.2022 | 2022 | 2024 | 70% | 600.54 | 600.54 | 266.77 | - |
| 45 | Widening and Strengthening of 1) Tandur- Dharur road Km 9/0 to 18/0 in Vikarabad District and 2) Widening and Strengthening of Tunikimetla - Narayanpet road from  Km 21/0 to 23/0 in Narayanpet District. | 1,700.00/  04.10.2022 | 2022 | 2024 | 10% | - | - | 261.13 | - |
| 46 | Widening and Strengthening of Huzurabad to Amudalapally (via) Metpally, Sirsapally road from km 0/0 to 13.705 in Karimangar District | 1,500.00/  20.12.2016 | 2016 | 2019 | 100% | - | 1,384.21 | - | - |
| 47 | Widening and Strengthening of Yanagundi - Damaragidda road from Km 0/0 to 12/5 in Mahabunagar District | 1,300.00/  20.12.2016 | 2016 | 2019 | 100% | 169.62 | 1,183.12 | - | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 48 | Widening and Strengthening of Barkas to Nadargul road from km 2/0 to 10/0 and Midhani Town ship (Km 10/0 of Barkas - Nadargul road to Nagarjunasagar road from km8/8 to 15/0 in Rangareddy District | 1,600.00/  20.12.2016 | 2016 | 2019 | 100% | - | 1.01 | - | - |
| 49 | Widening and Strengthening of Road from Chinnagottimukla to JeediPally road from Km 0/0 to 16/0 via Gomarum and Manoharabad in Medak District | 2,000.00/  20.12.2016 | 2016 | 2019 | 100% | 215.46 | 2,165.85 | - | - |
| 50 | Widening and Strengthening of Sagar PWD road to Nadergul village via Kongarkalan and Adibatla village  from km 0/0 to 17/5 in Rangareddy District | 1,100.00/  20.12.2016 | 2016 | 2019 | 100% | - | 547.93 | 354.90 | - |
| 51 | Widening & Strengthening of Bheemaram Gurijal via Nannel road from Km from 8/0 to 20/0 in Mancherial  District | 1,400.00/  25.09.2018 | 2018 | 2020 | 100% | - | 648.85 | 707.96 | - |
| 52 | Widening & Strengthening of Vemulawada to Dongalamarri road via Chekkapally from Km 0/0 to 18/0 ( Working reach from Km 1/2 to15/0) in Rajanna Siricilla  District | 1,400.00/  25.09.2018 | 2018 | 2020 | 100% | - | 1,490.38 | - | - |
| 53 | Widening & Strengthening of Gumpula to Edulapur road from Km 8/250 to 20/200 in Peddapally District | 1,400.00/  25.09.2018 | 2018 | 2020 | 100% | - | 1,046.88 | - | - |
| 54 | Widening & Strengthening of Shabazpally to Namilikonda road from KM 9/450 tO 17/2 in Rajanna Siricilla District | 900.00/  25.09.2018 | 2018 | 2020 | 100% | 230.76 | 887.10 | - | - |
| 55 | Widening & Strengthening of Gollapally - Arevally road from Km 0/0 to 10/630 in Jagitial District | 1,300.00/  25.09.2018 | 2018 | 2020 | 100% | 204.95 | 1,283.37 | - | - |
| 56 | Widening & Strengthening of Gollapally to Almaspur junction on Yellareddypet to Marrimadka road from Km  0/0 to 10/3 in Rajanna Sircilla District | 1,300.00/  25.09.2018 | 2018 | 2020 | 100% | 368.75 | 1,210.05 | 119.07 | - |
| 57 | Widening & Strengtheing of PWD road to Nukalampadu via jannaram from Km 0/0 to 11/0 in Khammam District | 1,000.00/  25.09.2018 | 2018 | 2020 | 100% | - | 814.62 | - | - |
| 58 | b) Widening & Stengthening of Koratlagudem to Pinampally via Surdepalli , Ramachandra Puram & Bodulabanda - Ramachandrapuram including  reconstruction of CD Works from Km 0/0 to 14/4 in Khammam District | 1,500.00/  25.09.2018 | 2018 | 2020 | 100% | - | 1,201.16 | - | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 59 | Widening & Strengthening of Kalwakurthy to Raghupathipet road from Km 0/0 to 19/2 (Working reach from Km 1/300 to12/300)in Nagarkurnool District | 1,400.00/  25.09.2018 | 2018 | 2020 | 100% | 189.64 | 1,201.94 | - | - |
| 60 | Widening and Strengtheing of Akkannapet - Uppulingapur road from Km 0/0 to 23/0 in Medak  District | 3,000.00/  25.09.2018 | 2018 | 2020 | 100% | - | 2,876.32 | - | - |
| 61 | Widening & Strengthening of Arepally to Kanthatmakur from Km 0/0 to16/085 in Warangal Urban District | 2,000.00/  25.09.2018 | 2018 | 2020 | 100% | - | 2,020.77 | 10.26 | - |
| 62 | Widening & Strengthening of PWD Road from Velmal thanda to Thangedapally x Road from Km 0/0 to 11/5 via Kondakal , Mokila , Tangutur , Proddutur in Rangareddy District | 1,400.00/  25.09.2018 | 2018 | 2020 | 100% | - | 313.00 | 312.58 | - |
| 63 | Widening & Strengthening of PWD road from Kandukur to Kollapadakala road via Kandukur, Kothaguda, Jaithwaram, Pulimamidi, Dhannaram, Chippalapalli,  Porandla, Kollapdakala from Km 0/0 to 16/0 (Working reach from Km 0/0 to 13/0) in Rangareddy District | 1,600.00/  25.09.2018 | 2018 | 2020 | 100% | 483.09 | 1,249.26 | - | - |
| 64 | Widening & Strengthening of road from a) PWD road to Yadaram from Km 0/0 to 7/6 b) Lalgadimalakpet to Hyd- Karimnagar - Ramagundam road from Km 0/0 to 3/8  Medchal - Malkajgiri District | 1,400.00/  25.09.2018 | 2018 | 2020 | 100% | - | 1,183.04 | 20.00 | - |
| 65 | Widening & Strengtheing of Marlapadu to Parvathapuram road from Km 0/0 to 10/620 in Khammam District | 1,300.00/  25.09.2018 | 2018 | 2020 | 100% | - | 583.39 | - | - |
| 66 | Widening & Strengtheing of Muthagudem (via) Lankasagar road from Km 0/0 to 10/780 in Khammam District | 1,300.00/  25.09.2018 | 2018 | 2020 | 100% | - | 671.95 | - | - |
| 67 | Improvements by widening & strengthening of the road from NH-44 to Gubidi road from Km 0/0 to 15/0 including construction of minor bridges in Adilabad district. | 2,000.00/  28.04.2022 | 2022 | 2023 | 100% | 924.65 | 924.65 | 857.18 | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 68 | Widening & Strengthening of Nallabelli to Girnibavi via Duggondi from Km 0/0 to 11/0 in Warangal Rural District | 1,500.00/  28.04.2022 | 2022 | 2023 | 100% | 1,417.24 | 1,417.24 | 205.69 | 1,637.00 |
| 69 | Widening and Strengthening Upparagudem to Peddavangara road from Km 0/0 to 10/0 in  Mahabubabad district | 1,200.00/  28.04.2022 | 2022 | 2023 | 100% | 880.57 | 880.57 | 293.35 | - |
| 70 | Widening & Strengthening of Oglapur - Dharmaram road from Km 0/0 to 13/340 in Warangal Rural District | 1,500.00/  28.04.2022 | 2022 | 2023 | 100% | 835.72 | 987.32 | 207.19 | - |
| 71 | Widening and stretngthening of NH-44 to Velpoor via Brahmanpally , Thorlikonda , Janakampet, Sahebpet road from Km 0/0 to 14/1 in Nizamabad District | 2,100.00/  28.04.2022 | 2022 | 2023 | 100% | 1,536.84 | 1,536.84 | - | - |
| 72 | Widening & Strengthening of Nandaram to Bapalli Thanda from Km 0/0 to 25/0 (Working reach Km9/0 to 23/0) in Vikarabad District | 1,800.00/  19.12.2018 | 2018 | 2020 | 100% | - | 1,668.28 | 198.65 | - |
| 73 | Widening & Strengthening of road from Adilabad to Nirala via Landasangvi, Arli, Ada Villages from Km 0/0 to 15/0 in Adilabad District | 4,024.00/  09.06.2023 | 2023 | 2025 | 25% | - | - | 1,113.58 | - |
| 74 | Construction of H.L. B at Km.5/4 on Adilabad-Kerameri road. | 500.00/  02.11.2020 | 2021 | - | 100% | 43.74 | 371.00 | 69.18 | - |
| 75 | Improvements by Widening and Stregthening of Old NH- 7 road through Adilabad town from Km 192/4 to 198/5 in Adilabad District | 4,430.00/  06.02.2018 | 2018 | - | 92% | 70.56 | 3,269.62 | 136.58 | - |
| 76 | Reconstruction of High Level Bridge at Km.0/8 of Kuntala water fall road in Adilabad district under FDR | 330.00/  19.12.2022 | 2023 | - | 100% | 91.22 | 91.22 | 152.31 | - |
| 77 | Reconstruction of High level bridge at Km.0/2 on Boath- Nigni road in Adilabad district under FDR | 225.00/ 31.3.2023 | 2023 | 2024 | 90% | - | - | 66.29 | - |
| 78 | Reconstruction of HLB at Km.4/4 on Kapri-Bela road in Adilabad district | 320.00/  19.12.2022 | 2023 | 2024 | 30% | - | - | - | - |
| 79 | Improvements by widening and strengthening of Old NH 7 passing through Adilabad town from Km 197/0 to 200/2 in Adilabad District. | 1364.6/  06.04.2022 | 2022 | 2024 | 70% | 155.64 | 362.67 | 140.80 | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 80 | Widening & Strengthening of Utnoor-Asifabad road from Km 3/2 to 25/0 in Adilabad District. ( Now Kumrambheem Asifabad Dist) | 2,000.00/  20.11.2013. | 2013-14 | - | 100% | - | 1,625.27 | 374.73 | - |
| 81 | Sirpur-Bijjur road from KM 0/0-19/7 in Kumrambheem Asifabad Dist | 2,500.00  /27.11.2014 | 2014-15 | - | 100% | - | 2,470.00 | 30.00 | - |
| 82 | Asifabad-Tiryani via Chirrakunta, Dampur road from KM 0/0-32/0 in Kumrambheem Asifabad Dist | 3,850.00/  27.11.2014 | 2014-15 | - | 100% | - | 2,720.18 | 1129.82 | - |
| 83 | Widening & Strengthening of Kagaznagar - Penchikalpet road from km 5/2 to 20/0 in Kumrambheem Asifabad Dist (Km 5/2-19/6) | 1,800.00/  27.11.2014 | 2014-15 | - | 100% | - | 1,787.30 | 12.70 | - |
| 84 | Construction of High Level Bridge at km 3/6-8 on Sirpur- makodi road in Kumrambheem Asifabad Dist. | 155.00/  27.11.2014 | 2014-15 | - | 100% | - | 82.87 | 72.00 | - |
| 85 | Widening & Strengthening of Jainoor-Mamidipally road from km 16/650 to 23/400 in Kumrambheem Asifabad  Dist | 750.00/  27.11.2014 | 2014-15 | - | 100% | - | 532.20 | 217.80 | - |
| 86 | Construction of HLB at km 13/4-6 on Jainoor- Mamidipally road in Kumrambheem Asifabad Dist. | 150.00/  16.11.2017. | 2017-18 | - | 100% | - | 127.72 | 22.28 | - |
| 87 | Construction of high level bridge of peddavagu at km 33/6 on road from Vemanapally to Penchikalpet road from km 0/0 to 35/0 via Girivelli Gerrew of Sirpur(T)  Constituency in Kumrambheem Asifabad District. | 2990.00/  29.12.2016 | 2017-18 | - | 100% | - | 2,608.53 | 381.47 | - |
| 88 | Widening of BT road from Hatti-Jodeghat (V) of Kerameri (M) in Adilabad Dist. ( Now Kumrambheem Asifabad Dist) | 700.00/  16.11.2017. | 2017-18 | - | 100% | - | 124.50 | 575.50 | - |
| 89 | 1) Sirpur-Bijjur road from Km.22/0-31/0. 2) Sirpur-Bijjur road from Km.31/0 -52/2..3) Khagaznagar-Kadam- Babasagar road from KM 5/8-25/6 in Kumrambheem  Asifabad Dist | 4900.00/  27.11.2014 | 2014-15 | 2024 | 95% | - | 4,532.64 | 367.36 | - |
| 90 | Construction of High Level Bridge at Km 145/0 on Basar-Luxettipet road in Adilabad district | 265.00/  27.11.2014 | 2015-16 | - | 100% | - | - | - | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
|  | Construction of High Level Bridge at Km 145/0 on Basar-Luxettipet road in Adilabad district (Part work withdrawl from original agreement) |  | 2017-18 | - | 100% | - | 173.00 | 46.00 | - |
| 91 | Re Construction of Bridge in place of weak and narrow bridge at Km.132/4-6 on Basar- Luxettipet Road in Adilabad District. | 242.00/  27.11.2014 | 2017-18 | - | 100% | - | 136.00 | - | - |
| Construction of HLB at Km. 132/4-6 on Basar- Luxettipet Road in Adilabad District. (Newly formed Mancherial District) (part work withdrawn from original  agreement) | 2019-20 | - | 100% | - | - | 33.00 |
| 92 | Widening & Strengthening of Gudem - Madaripet road from km 0/0 to 15/8 in Adilabad Dist | 1800.00/ 27.11.14 | 2016-17 | - | 100% | 114.00 | 1,356.00 | - | - |
| 93 | Subwork of Forming approahces to constructed bridge from Km 24/830 to 25/688 and Km 25/945 to 26/200 including strengthening of missing link road in Neelwai village limits from Km 23/800 to 26/200 on C-V Road for the main work of Widening of Single lane road to Double lane road to connecting Mandal head quarters to  District head quarters for Chennur-Vemanapally road from Km 13/0 to 31/125 in Adilabad District. | 475.00/  27.11.2014 | 2020-21 | 2024 | 30% | - | 100.47 | 0.99 | - |
| 94 | Construction of HLB across river Godavari Near Mancherial from Mancherial to Basanthnagar via Anthargoan of Peddapalli District to connect Mancherial  town in Mancherial District. | 16400.00/  30.5.2022 | 2023-24 | 2025 | - | - | 53.25 | 245.00 | - |
| 95 | Construction of H.L.B. at Km.1/6 of NH-7 Gandhinagar road in Adilabad Dist. | 300.00/  27.11.2014 | 2016-17 | 2024 | 90.00% | 21.37 | 187.39 | 42.00 | - |
| 96 | Construction of High level bridge across Godavari River near Panchagudi (vg) of Lokeshwaram Mandal of  Adilabad Dist. | 10,810.00/  27.11.2014 | 2015-16 | 2024 | 95.00% | 280.55 | 9,422.44 | 255.00 | - |
| 97 | Widening of Singal Road to Double lane Road to Yellareddypet to Marrimadla road from KM 0/0 to 25/0. in Karimnagar District | 2500.00/  27.11.2014 | 2016 | 2024 | 80% | 254.39 | 3,175.15 | 231.41 | 5,000.00/  28.5.2020 |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 98 | Construction of Sircilla bye-pass road from KM.0/0 to 11/0 in Karimnagar Dist. | 3,000.00/  27.11.2014 | 2017 | - | 100% | 17.91 | 8,451.21 | 0 | 9,500.00/  15.7.2020 |
| 99 | Widening and Strengthening of Right side by pass road to Vemulawada town from Km 0/0 to 1/2 in Rajanna- Siricilla District | 324.00/  27.11.2014 | 2021 | - | 100% | - | 184.47 | 131.79 | - |
| 100 | Construction of HLB at Km 3/2-4 of Vemulawada Branch road ( Mulavagu) in Karimnagar district | 2,800.00/  08.12.2015 | 2016 | 2017 | 55% | 241.6 | 1,741.68 | - | - |
| 101 | Improvements to Chandurthy to Mothukuraopet road from Km. 0/0 to 13/0 in Karimnagar district. | 1,975.00/  10.08.2016 | 2017 | 2019 | 65% | 0 | 968.00 | - | - |
| 102 | Widening and Strengthening of Single Lane to Double Lane from Km. 0/0 to 12/0 of Thangallapally to Turkapally via Mandapally, Rallapet, Katkur,  Gandilachakkapet in Karimnagar District | 2,400.00/  29.08.2016 | 2017 | - | 100% | 0 | 1,414.75 | 386.58 | - |
| 103 | Widening and Strengthening of Single Lane to Double Lane from Km. 0/0 to 13/0 of Jillella X road to  Musthabad in Karimnagar District. | 2,800.00/  29.08.2016 | 2017 | - | 80% | 2.77 | 1,304.03 | 507.74 | - |
| 104 | Widening and Strengthening of six lane from Km.37/0 to 43/4 on Karimnagar - Kamareddy road in Rajanna Siricilla District.  Subwork: Widening of Slab Culvert 2v of 4.00m Clear Span at Km.39/570 & Construction of 2 cell of 4m\*2m Box culvert at Km.39/480. | 122.00/  25.05.2018 | 2021 | - | 100% | 47.08 | 47.08 | 56.08 | - |
| 105 | Construction of 2nd Two lane HLB across Mulavagu near Shabazpally village of Boinpally (M) at Km. 24/4 on Karimnagar-Kamareddy road in KNR Dist. Sub work:  Widening from Double lane to Four lane from Km. 20/2 to 22/8 on Karimnagar-Kamareddy road in R-S Dist. | 1,045.00/04.02.20  17 | 2020 | - | 100% | 0 | 0 | 712.96 | - |
| 106 | Widening and Strengthening of Mustabad to Rallapet via Pothugal, Gannevanipally, Sevalal thanda & Obulapur  from Km. 0/0 to 14/7 in Rajanna Sircilla District | 3,250.00/  23.09.2017 | 2018 | - | 85% | 1,970.31 | 2,303.3 | 87.12 | - |
| 107 | Laying CC Pavement and side drains in the village limits of Pothur to Muskanpet road from Km. 0/0 to 1/0 in  Rajanna Sircilla district. | 270.00/  18.08.2017 | 2019 | - | 100% | 0 | 176.00 | 0 | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 108 | Construction of Minor Bridge along with approaches at km 11/0-2 on Medipally - Bornapally road in Jagtial District | 291.00/  22.11.2014 | 2022-23 | 2024 | 70.00% | - | 138.96 | - | - |
| 109 | Construction of HLB on Dharmapuri - Jaina road at km 0/2 from Km 0/0 to 8/500 | 231.00/  27.11.2014 | 2016-17 | - | 100.00% | - | 190.58 | 16.64 | - |
| 110 | Construction of HLB at KM 25/8-10 on Korutla - Mallapur road in Karimnagar Dist. | 350.00/  27.11.2014 | 2016-17 | - | 100.00% | - | 174.54 | 4.23 | - |
| 111 | Constrution Of High Level Bridge on PWD road to Kotilingala road @ KM 1/4-6 in Karimnagar Dist. | 206.00/  02.06.2016 | 2016-17 | 2024 | 90.00% | - | 91.40 | - | - |
| 112 | Widening and Strengthening A.  Dharmapuri-Jaina road from Km' Z/350 to 3/069 & Km 7/280 to 8/500 B) Donthapur - Jaina road from  Km 0/0 -5/5 including sie drains & side lightening in Jagtial District | 3,000.00/  03.04.2023 | 2023-24 | 2024 | 5.00% | - | - | 90.96 | - |
| 113 | Construction of High Level Bridge on Lyagalamarri via Pattipaka road at Km.3/4-6 in Karimnagar District (New Peddapally District). | 100.00/  27.11.2014 | 2017 | - | 100% | 62.69 | 62.69 | 57.68 | 165.00/  12.5.2017 |
| 114 | Construction of Bridge portion on Manair River at 3/8 on Khammampally - Bhoopalapally road in Karimnagar District | 5,000.00/  09.08.2016 | 2017 | - | 100% | - | 4,733.8 | 149.85 | - |
| 115 | Construction of Peddapally By -pass road connecting to Jagityal Peddapally road at Km 56/6-8 and HKR (SH-1) road at 199/2-4 in Peddapally District. | 650.00/  18.08.2017 | 2018 | - | 46.49% | 302.24 | 302.24 | - | - |
| 116 | Construction of ROB in lieu of LC. No.39 at km. 292/22- 24 of Kazipet -Ballarsha section on Peddapally- Kalvasrirampur road at Km 1/2 in Karimnagar district  (Now in Peddapally District). (2nd Call) | 11,950.00/  21.01.2022 | 2022 | 2024 | 35% | 902.68 | 902.68 | 603.48 | - |
| 117 | Widening & Strengthening of PWD road to Gumpula (via) Madaka from Km 13/8 to 25/8 (Working reach from Km 13/8 to 22/6) in Peddapally District (final Km 13/8 to 21/700) | 1,600.00/  28.04.2022 | 2022 | - | 100% | 914.86 | 914.86 | 609.46 | 1,759.80/  24.12.2023 |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 118 | Improvements to Karimnagar - Kamareddy (old) Road from Km 4/4 to 9/6 including CD works in Karimnagar District(Formation of approaches & connecting road between two bridges) | 3,200.00/  27.11.2014 | 2017 | 2024 | 45% | 729.21 | 1,614.16 | 486.79 | 9,000.00/  21.12.2021 |
| Improvements to Karimnagar - Kamareddy (old) Road from Km 4/4 to 9/6 including CD works in Karimnagar District | 2,800.00/  27.11.2014 | 2017 | - | 50% | - | 1,185.40 | - |  |
| 119 | Widening to Four lane road from Km 0/0 to 12/74  Jammikunta to Lalithapur road in Karimnagar District | 3,300.00/  18.3.2017 | 2017 | - | 71% | 213.65 | 2,568.01 | - | - |
| 120 | Improvements to Huzurabad to Sunderagiri road from Km 0/0 to 0/750 including Construction of Side drains and Foot path at Huzurabad Town limits in Karimnagar  District | 600.00/  02.09.2021 | 2021 | - | 42% | - | 251.96 | - | - |
| 121 | Widening of single lane to double lane Road from (a) Jammikunta-Lalithapur Road from Km 12/740 to 21/6, Km 22/4 to 24/4 and 25/3 to 30/150 and (b) Manakondur to Utoor Road from Km 0/0 to 0/8 , Km 4/060 to 4/660  and Km 6/5 to 13/6 in Karimnagar District | 3,555.00/  3.9.2015 | 2015 | 2024 | 74% | 529.36 | 5,244.01 | - | 7,110.00/  18.09.2018 |
| 122 | Construction of High Level cable stayed bridge across Manair River at Sadhashivpally connecting Hyderabad - Karimnagar - Ramagundam road and Rayapatnam - Kodad road (NH563) in Karimnagar Dsit. Sub work:Improvemetns to road from Kaman to Housing board colony (at Km.163/0 of Hyderabad - Karimnagar - Ramagundam road) from Km.0/0 to 2/0 including  approach road in Karimnagar Dist. | 3,400.00/  09.08.2017 | 2016 | - | 100% | 875.89 | 3,550.83 | 373.18 | - |
| 123 | Improvements by widening and Strengthening of Karimnagar-Kamareddy road four lane from Km.3/6 to 8/4 in Karimnagar District Sub Work :- Construction of HLB at Km 6/200 on Karimnagar - Kamareddy road in Karimnagar District | 165.00/  17.11.2020 | 2020 | 2024 | 82% | - | 46.79 | 88.90 | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 124 | Improvements by widening and Strengthening of Karimnagar-Kamareddy road four lane from Km.3/6 to 13/4 in Karimnagar District Sub Work :- Construction of HLB (4 Lane) at Km 10/665 & Km 12/745 on  Karimnagar - Kamareddy road in Karimnagar District | 360.00/  31.10.2020 | 2020 | 2024 | 50% | - | 110.71 | - | - |
| 125 | Construction of High Level Bridge across Chalivagu between Tekumadla and Raghavareddypeta Village in Warangal District | 1,595.00/  08.01.2013 | 2013 | - | 100% | - | 1,231.75 | 89.55 | - |
| 126 | Widening & Strengthening of Chityal-Mogullapally Road from Km.0/0 to 7/0 (working reach 0/0-5/8) & Chityal- Jadalpet Road from Km.0/0 to 9/7 in JS-Bhupalpally District. | 2,500.00/  18.12.2017 | 2017 | - | 100% | - | 1,838.45 | 192.54 | - |
| 127 | Construction of HLB @ Km 2/6-8 on PWD road to Pratapagiri via Bopparam in Karimnagar District (Now J.S. Bhupalpally District) | 305.00/  20.02.2018 | 2020 | - | 100% | - | 157.54 | 68.99 | - |
| 128 | Widening of Regonda - Jakaram road from Km 0/0 to 17/730 | 2,000.00/27.11.20  14 | 2015 | - | 100% | - | 1,991.53 | - | 2,119.00/ 2017 |
| 129 | Widening of Single lane to double lane for the road PWD road Thadicherla from Km 0/0 to 12/7 in karimnagar District ( Newly formed District Jayashankar  Bhupalpally) | 1,500.00/  27.11.2014 | 2015 | - | 100% | - | 1,433.80 | 58.66 | - |
| 130 | Widening of single lane to Double lane of Mahadevpur - Mukunour -Kankanour - Kataram road from Km.79/6 to 90/6 in Karimnagar ( Newly formed District Jayashankar Bhupalpally)- TSP Work | 1,140.00/  21.12.2015 | 2016 | - | 100% | - | 1,028.04 | 127.82 | - |
| 131 | Widening of single lane to Double lane of PWD road Pegadapally to Madaram from Km.0/0 to 19/2 in Karimnagar District ( Newly formed District Jayashankar Bhupalpally)- (Working reach Km 0/0-14/2)TSP Work | 1,500.00/  21.12.2015 | 2016 | - | 100% | - | 1,689.86 | - | - |
| 132 | Widening of single lane to Double lane of PWD road Pegadapally to Madaram from Km.14/2 to 19/2 in Karimnagar District ( Newly formed District Jayashankar Bhupalpally)- STSDF Work | 750.00/  16.11.2017 | 2017 | - | 100% | - | 682.52 | - | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 133 | Widening of Single Lane to Double Lane roads to connecting mandal head quarters to district head quarters of Mohd. Ghousepally to Girnibavi from Km 0/0 to 11/0 in Warangal District. | 1,330.00/  27.11.2014 | 2015-16 | - | 100% | - | 1,002.00 | 14.00 | - |
| 134 | Widening & Strenthening of Wardhannapet - Annaram road from Km 0/0 to 10/0 in Warangal District. | 1,200.00/  27.11.2014 | 2015-16 | - | 100% | - | 782.00 | - | - |
| 135 | Widening and Strengthening of Machapur - Laxmipuram (via) Elakathurthy road from Km.0/0 to 9/4 in Warangal Rural District | 1,880.00/  05.01.2018 | 2018-19 | - | 100% | 237.00 | 1,638.10 | - | - |
| 136 | Construction of HLB across Akeru Vagu on R/F Katriala to Kothapally Village of Wardhannapet Mandal in Warangal Rural District. | 1,530.00/  31.07.2018 | 2019-20 | - | 100% | 301.69 | 1,219.52 | - | - |
| 137 | Construction HLB across Akeru Vagu on R/F  Jaganthanda of Liaberthy in Warangal Rural District. | 1,810.00/  31.07.2018 | 2019-20 | 2024 | 80% | - | 1,154.73 | 87.88 | - |
| 138 | Improvement to Kummarikuntla - Narsimhulapet road from km 12/5 to 15/5 in Mahabubabad Distrct. | 300.00/  28.09.2020 | 2021 | - | 100.00% | 9.00 | 189.13 | - | - |
| 139 | Widening of Single lane to Double lane roads to connecting Mandal Head Quarters to District Head Quarters of Yellandu Pakhal Road Km.48/0 to 59/1 in  Warangal District. | 1,350.00/  05.09.2015 | 2016 | - | 100.00% | 1.32 | 47.88 | - | - |
| 140 | Widening to 4 lane Kazipet-Peddammagadda road from Km 8/3 to 9/470 in Warangal town from 2 Lane to 6 Lane in Warangal district | 1,150.00  /30.09.2015 | 2015-16 | - | 100.00% | 0 | 557.15 | 19.52 | - |
| 141 | Widening and Strengthening of Double lane to Four lane Huzarabad to parakal Road from Km 0/0 to 30/5 in Karimnagar Dist (Reach from Km 6/0 to 30/5 of  Hanumakonda Dist) | 14,225.00/13.02.2  016 | 2016-17 | - | 100.00% | 2,366.63 | 14,375.84 | 0 | - |
|  | Sub-work: PROVIDING CENTERLINE PAINTING AND ROAD SAFETY INTERVENSIONS ON HUZURABAD PARAKAL ROAD FROM 0/0-35/500 IN HANUAMKONDA |  | 2022-23 | - |  | 0 | 0 | 173.01 | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 142 | Widening and strengthening of Dharmasagar to Velair via Saipet, Mallikudurla road from single lane to double lane from Km.0/0 to 20/7 in Warangal Urban District | 2,500.00/  03.11.2017 | 2021-22 | - | 100.00% | 793.01 | 1,959.94 | 1226.10 | 3,600.00/  31.3.2023 |
| 143 | Improvements to Mallareddypally to Sudanpally road from Km.0/0 to 3/4 with Construction of H.L.B cum  check dam in Warangal Urban District | 600.00/  21.08.2018 | 2021-22 | - | 100.00% | - | 461.22 | - | - |
| 144 | Widening and Strengthening of PWD road to Kothakonda via Gatlanarsingapoor from Km 0/0 to 7/0 in Hanumakonda District | 1,600.00/  06.01.2022 | 2022-23 | - | 100.00% | 1211.28 | 1,211.28 | 0 | - |
| 145 | Widening & Strengthening of Arepally to Parkal road fom km 7/5 - 20/526 in Hanumakonda district. | 2,900.00/  31.07.2023 | 2023-24 | 08.10.2025 | 1.00% | 20.28 | 20.28 | - | - |
| 146 | Widening & Strengthening of Parkal to Narlapur road fom km 0/0 - 12/5 in Hanumakonda district. | 2,500.00/  31.07.2023 | 2023-24 | 08.10.2025 | 2.00% | 0 | 0 | 19.68 | - |
| 147 | Widening and strengthening of Venkatayyapalem- Chintakani Road from Km 0/0 to 14/020 | 2,057.00/  27.11 .2014 | 2015 | - | 100.00% | - | 1,346.36 | 108.97 | - |
| 148 | Construction of HLB at Km.6/0-2 of PWD Kamepally,  Vutukoor | 259.00/  27.11.2014 | 2018-19 | - | 100.00% | - | 235.91 | - | - |
| 149 | Wideing and strengthening to Kusumanchi to Nelakondapally road from km 0/0-18/57 | 3,100.00/  27.11 .2014 | 2016 | - | 100.00% | 21.600 | 2,994.64 | - | - |
| 150 | Widening to two lane from km 0/0 to 0/550 & 2/450 to 9/6, 11/0 to 27/2 of Yellandu - Dornakal road | 3,100.00/  27.11.2014 | 2016 | 2024 | 90% | - | 2,050.07 | 182.27 | - |
| 151 | Improvements to MV Palem to Thirumalayapalem road from km 0/0 to 3/0 | 285.00/  18.12.2017 | 2018 | - | 100.00% | - | 134.11 | - | - |
| 152 | Improvements to Anasagaram to Kamalapuram from km.0/0 to 5/0 in Khammam District | 300.00/  15.2.2018 | 2018 | - | 100.00% | - | 286.19 | - | - |
| 153 | Improvements to Aarekodu to Kaachirajugudem road Km.0/0 to 2/4 | 300.00/  15.2.2018 | 2018 | - | 100.00% | - | 246.91 | 2.07 | - |
| 154 | Imp.to Pocharam to Chegomma via (Muthyalammagudem) road Km.0/0 to 7/6 | 491.00/  22.9.16 | 2017 | - | 100.00% | 160.880 | 355.42 | - | - |
| 155 | Construction of High Level Bridge across Aakeru River in Km.5/4-7 on Thirumalayapalem Mulkalapally road (12Vx16M) | 960.00/ 31.8.17 | 2017 | - | 100.00% | 204.800 | 774.44 | - | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 156 | Construction of High Level Bridge cum check dam across Palair Vagu at Km.0/6-8 on Suridepally - Kistapuram road | 2,800.00/ 31.8.17 | 2017 | - | 100.00% | 0.000 | 2,356.00 | - | - |
| 157 | Construction of High Level Bridge cum Check dam across Munneru River on ZP Road to Papatpally (via)  Maddivarigudem, Polisettygudem, Mangalagudem | 1,442.00/ 31.8.17 | 2017 | - | 100.00% | 182.460 | 1,397.71 | - | - |
| 158 | Improvements to Warangal X road to Teldurapally via Gurralapadu from km 0/0 to 4/0 | 450.00/  18.12.2017 | 2019 | - | 100.00% | 0.000 | 282.99 | - | - |
| 159 | Improvements to Muthyalagudem to Muthyalagudem road (via) Thimmakkapeta & Thallacheruvu road from km 0/0 to 10/950 | 560.00/  18.12.2017 | 2018 | - | 100.00% | 132.800 | 242.50 | 209.46 | - |
| 160 | Widening and strengthening to Budha Stupam road to Khammam Kodad R&B road from km.0/0 to 1/8 | 449.00/ 22.9.16 | 2017 | - | 100.00% | - | 332.74 | 85.69 | - |
| 161 | (a) Improvements Khammam -Devarapally road from 2 lane to four lne including drains and Illumination from Km 10/4 (Sri Sri Circle) to KM 14/8 (New Collectorate- V.Venkatayapalem) in Khammam town limits(Radial Roads to Khammam outer Ring road. (b) Improvements to Suryapet-Aswaraopet Road from Km 51/0 (Ponnekal) to Km 52/0-two lane to four lane including drains and  illumination in Khammam District. | 3,500.00/ 44281 | 2022 | - | 100.00% | 952.990 | 3,059.96 | - | - |
| 162 | Construction High Level Bridge cum checkdam across Aakeru river on Azmirathanda-Rakasithanda road in Khammam District (12Vx16M) | 1,500.00/ 31.8.17 | 2018 | - | 100.00% | 0.000 | 946.64 | - | - |
| 163 | Widening and strengthening of Khammam-Kodad road from km.17/0 to 21/2 (Nelakondapally town limits) | 1,700.00/ 1.9.18 | 2018 | - | 100.00% | 5.45 | 1,582.94 | - | - |
| 164 | Widening and strengthening of Tallampadu to Kondapuram via Narsimhapuram road from km.0/0 to  4/5 | 500.00/ 15.2.2018 | 2018 | - | 100.00% | - | 231.30 | - | - |
| 165 | Widening and strengthening of Thirumalayapalem to Pocharam via Kokkireni, Gopalapuram, Yerragadda road  from km.0/0 to 12/5 in Khammam District | 1,500.00/  15.2.2018 | 2018 | - | 100.00% | 4.95 | 1,080.01 | - | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 166 | Improvements to Teldarpally to Yedavalli via Lakshmipuram road from km.0/0 to 5/8 | 500.00/ 15.2.2018 | 2018 | - | 100.00% | - | 411.00 | - | - |
| 167 | Improvements to Teldarupally to Venkatagiri in Khammam Rural mandal from km 0/0 to 4/0 | 500.00/ 15.2.2018 | 2018 | - | 100.00% | - | 288.67 | - | - |
| 168 | Imp.to Kondapuram X road to Mootapuram (via) Seetharampuram, Kondapuram, Jeellacheruvu and Agraharam km.0/0 to 17/600 | 2,325.00/ 22.9.16 | 2017 | - | 100.00% | - | 2,144.06 | 69.14 | - |
| 169 | Improvements to road from R&B road to Valya thanda to Arekodu thanda via Regula thanda road Km.0/0 to 3/3 | 200.00/ 15.2.2018 | 2018 | - | 100.00% | - | - | - | - |
| 170 | Improvements to Khammam - Papatapally road (via) Danavaigudem, Ramannapeta, Kamanchikallu from Km 0/5-14/7 ( working reach from Km. 0/5-5/7 ) including connecting road to FCI Bye pass road for 0.60Km in  Khammam District | 3,300.00/  15.04.2021 | 2023 | 2025 | 10% | - | - | 289.21 | - |
| 171 | Construction of High Level Bridge comprising 300mts. Cable stayed and 120mts. RCC at type at km.57/6-58/2 of Suryapet-Aswaraopet road in Khammam town limits. | 18,000.00/  19.01.2023 | 2024 | 2026 | - | - | - | 371.88 | - |
| 172 | Re construction of bridge on Nelakondapally- Palair road in Km 16/8-10 of Khammam district (5V of 10M) | 230.00/ 30.12.15 | 2020 | - | 100% | - | 207.21 | 12.91 | - |
| 173 | Re-Construction Bridge on PWD road to Matoorpet - (Via) Nidhanapuram road km 6/6-8 | 138.00/ 28.8.17 | 2022 | - | 80% | 120.74 | 120.74 | - | - |
| 174 | Reconstruction of bridges on Palair - Marripeda road Km 3/4-6 (4V of 8M) | 232.00/ 30.12.15 | 2020 | - | 0% | - | - | - | - |
| 175 | Providing BT road from Pinjaramadugu to Nemalipuri road from km.0/0-3/0 in Kamepally Mandal of Khammam District. | 210.00/  07.12.2022. | 2023 | 2024 | 100% | 182.80 | 182.80 | - | - |
| 176 | Construction of HLB Across Wyra river connecting Rayapatnam - Illuru road at km 3/2-4 and Dendukur - Chillukur road at km 2/2-4 | 1,550.00/  27.11.2014 | 2016-17 | - | 82% | 721.51 | - | 218.00 | - |
| 177 | Widening to two lane from km 0/0 to 14/6 of Mylaram - Chandrulagudem road in 1 Khammam district | 1,850.00/  18.01.2017 | 2017 | - | 100% | - | 680.86 | 1,169.14 | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 178 | Widening to two lane from km 0/0 to 17/2 of Kothagudem -Mylaram Copper Mines 2 road in Khammam district | 2,250.00/  18.01.2017 | 2017 | - | 100% | - | 1,905.07 | 35.93 | - |
| 179 | Construction of HLB at km 0/6-8 of  Rajapuram - Ulvanoor road in Khammam district. | 970.00/  18.01.2017 | 2021 | - | 100% | 170.56 | 358.82 | 611.18 | - |
| 180 | Widening to two lane from Km 0/0 to 18I3  4 of Rajapuram-Ulavanoor road in Khammam District. | 2,400.00/  18.01.2017 | 2017 | - | 100% | - | 649.69 | 1,750.31 | - |
| 181 | Widening & Strengthening of existing Double lane road to Four lane road from Km 0/0- 1/500 of Aswaraopeta - Burgampadu Road (in Aswaraopeta Town  Limits) in Bhadradri Kothagudem District. | 1,350.00/  09.03.2023 | 2023 | 2025 | 5% | - | - | - | - |
| 182 | Construction of CRS Masony,Dividers, CC drains, Providing of Centre,lighting & Strengthening of Khammam,Devarapally road from km l19/0-121/0 in Bhadradri Kothagudem district(Aswaraopeta Town  Limits). | 1,000.00/  09.03.2023 | 2023 | 2025 | 10% | - | - | - | - |
| 183 | Widening of Single lane road to Double lane road Connecting Mandal head Quarter to District head quarter for Indalwai - Bheemgal road from Km. 23/0 to 38/5 in Nizamabad District. under 60 (C) a)Km 24/550 to 27/0 b) km 13/0 to 24/550c)km 27/0 to 38/5 | 1,650.00/  27.11.2014 | 2015-16 | - | 100% | - | 1,253.19 | 66.14 | - |
| 184 | Widening of Single lane road to Double lane road connecting Mandal Head quarter to District Head quarter for Sirikonda-Vemulawada road from KM 0/0 to 20/5 in  Nizamabad Dist. | 2,500.00/  27.11.2014 | 2015-16 | - | 90% | 53.85 | 1,565.04 | 236.29 | - |
| 185 | Formation of Bye Pass road to nizamabad town in Nizamabad dist from km 0/0 to 11/0 in Nizamabad dist. | 6,630.00/  23.09.2008 | 2008-09 | - | 100% | - | 5,709.51 | 187.41 | - |
| 186 | Construction of RUB at Km 0/0 on NizambadNarsi road at Railway Km 460/8-9 on Secunderabad Manmad line in Nizamabad District (Construction of CC Pavement for approaches and Drains) | 2,280.00/  27.05.2012 | 2018-19 | - | 100% | 186.18 | 1,974.19 | 14.32 | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 187 | Construction of HLB at Km 12/4 on Dichpally Nizamabad road in Nizamabad district | 310.00/  23.02.2013 | 2016-17 | - | 100% | - | 74.73 | 62.49 | - |
| 188 | Widening of Dichpally - Nzbd road from km 3/7 to 14/4(Widng km 3/7 to 12/2 and constn of drains from km 6/0 to 6/4,10/2 to 11/2 and km 12/4 to 13/2) sub work:- Providing central median and lighting in km 0/0 to 3/7 in  Nizamabd District(4th call) | 320.00/ 7.8.2018 | 2023-24 | 2024 | 33.00 | - | - | 105.09 | - |
| 189 | Construction of Box culvert in km 6/4-6, 7/8-10 on Manikbandar-Gangaram-Simrajpally road in Nizamabad  dist | 300.00/  30.12.2015 | 2017-18 | 2024 | 40.00 | - | 120.32 | 0 | - |
| 190 | Widening from double lane to four lane in Bheemgal town of in Nizamabad District (i) Kammarpally- Bheemgal road from km.19/750 to 20/150 (ii) Morthad Bheemgal road from km.16/5 to 17/0 (iii) Bheemgal- Muchkur road from km.0/0 to 0/6 (iv) Bheemgal Thumpally road from km.0/0 to 0/750 (v) Indalwai-  Bheemgal road from km.37/550 to 38/5 | 1,379.00/  19.08.2020 | 2021-22 | - | 100% | - | 1,068.76 | 72.01 | - |
| 191 | Widening of single lane to double lane of (i) Bheemgal- Muchkur road from Km 5/7 to 8/7 & 11/720 to 12/220 in  Nizamabad District (including pipri junction improvements) | 510.00/  19.08.2020 | 2021-22 | - | 100% | 24.11 | 217.96 | 59.75 | - |
| 192 | Widening & Strengthening from single lane to double lane of Pallikonda to Devakkapet (via) Rahathnagar road  from km.0/0 to 10/0 in Nizamabad District. | 1,000.00/  19.08.2020 | 2022-23 | - | 100% | 70.48 | 636.10 | 131.52 | - |
| 193 | Construction of Bypass road(i) Mothe village from 0/0 to 1/0, (ii) Bheemgal town from km.0/0 to 1/5 & Construction of road from Devakkapet to Thatipally road  from km.0/0 to 10/0 in Nizamabad District. | 1,170.00/  19.08.2020 | 2022-23 | - | 100% | 250.52 | 341.84 | 192.47 | - |
| 194 | Widening from double lane to four lane in Yergatla mandal head quarter of Nizamabad district.   1. Battapur-Gudur road from km.0/0 to 0/420& 0/420 to 0/580 2. Kammarpally Tadpakal road from km.8/780 to 9/3 | 500.00  /19.08.2020 | 2022-23 | - | 100% | 94.23 | 185.22 | 90.89 | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 195 | Improvements to the road from Panchagudi Bridge approaches to Nandipet from km.10/320 to 20/124 in Nizamabad district. | 2,300.00/  19.08.2020 | 2021-22 | - | 100% | 458.85 | 575.05 | 1,484.60 | - |
| 196 | Construction of road from Manala to Marrimadla from km 1/0 to 9/0 in Nizamabad District | 850.00/  19.08.2020 | 2023-24 | 06.07.2024 | 20% | - | 0 | 0 | - |
| 197 | Improvements to Mendora crossing to Rudrangi (via) Manala road from KM 29/7 to 30/5 in Rajanna Sircilla District | 107.00/  19.08.2020 | 2022-23 | - | 100% | - | 96.58 | 0 | - |
| 198 | Widening from double lane to four lane of (i)Nagpur to Hyderabad section of Old NH7 from km.294/8 to 295/9 ( Mupkal Mandal head Quarter), (ii) Widening the  existing road in Medora mandal head quarter from double lane to multi lane from km.0/0 to 0/9 & (iii) Widening from single lane to double of Mupkal-Pochampad dam  road from km.0/0 to 1/6 in Nizamabad district.( Mupkal Project road) in Nizamabad District. | 950.00/  19.08.2020 | 2022-23 | - | 100% | 280.95 | 799.02 | - | - |
| 199 | Widening & Strengthening from single lane to double  lane of Mendora Crossing to Rudrangi (via) Manala road from km.13/0 to 29/7 in Nizamabad District.(km 16/7 to | 1,430.00/  19.08.2020 | 2022-23 | 2024 | 65.00% | 85.06 | 722.88 | 0 | - |
| 200 | Widening S.L to D.L road of Mothey to Badabheemgal from km 0/0 to 5/0 in Nizamabad District.(working reach 0/0 to 4/1) | 660.00/  28.07.2022 | 2022-23 | - | 100% | 356.41 | 356.41 | 166.28 | - |
| 201 | Widening and Strengthening from Single Lane to Double Lane of NH-44 to Chengal via Padkal, Kaligote, Chintalur from km 0/0 to 14/0 in NIzmabad district.(Working reach 1/2 to 14/0) | 1850.00/  28.07.2022 | 2023-24 | - | 100% | - | - | 1,354.4 | - |
| 202 | Improvements to Konapur to Athmakur road from existing Cart Track to Double lane from km 0/0 to 2/0 in Nizamabad district.& 2) Improvements to link road from  Vannel B Dharmora road to Vempally-Renjarla road from km 0/0 to 1//8 in Nizambad District. | 350.00/  28.07.2022 | 2023-24 | 12.03.2025 | 75% | - | - | 133.55 | - |
| 203 | Widening S.L to D.L road of Choutapally to Karimnagar Boarder road from km 0/0 to 5/240 in Nizamabad District. | 745.00/  19.09.2022 | 2023-24 | - | 100% | 415.83 | 415.83 | 239.93 | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 204 | Widening S.L to D.L road of Kammarpally Approach Road to Bilyanaik Thanda from km 0/0 to 2/6 including Construction of Minor Bridge 2V x10.00m span in Nizamabad District. | 450.00/  19.09.2022 | 2023-24 | 01.11.2024 | 65.00% | - | - | 275.87 | - |
| 205 | Widening and Strengthening of Nizamabad - Warni road to four lane from km 0/8 to 2/6 in Nizamabad district. B) Improvement to Byepass road to Nizamabad town in Nizamabad district from km 7/8 to 10/2 in Nizamabad District.  c) Widening and Strengthening of Nizamabad - Narsi road to Four lane from km 6/1 to 7/0 in Nizamabad  District | 1,850.00/  19.09.2022 | 2023-24 | 23.01.2025 | 20.00% | - | - | 208.88 | - |
| 206 | Widening and Strengthening of Bodhan to Sunkini road to from km 6/2 to 15/0 in Nizamabad district. | 1,250.00/  07.01.2023 | 2023-24 | 07.06.2025 | 10.00% | - | - | 26.3 | - |
| 207 | Widening and Strengthening of Rurdur Pothangal road to Pentakhurd via Raikur from km 0/0 to 5/8 in Nizamabad  district. | 905.00  /07.01.2023 | 2023-24 | 2025 | 10.00% | - | - | 37.38 | - |
| 208 | Construction of HLB at Km 3/0-2 across MuthyalavadiVagu on MaddulaGadkole road in  Nizamabad District ( ts amount Rs.860.00 lkhs) | 950.00/  24.06.2023 | 2023-24 | 05.06.2025 | 25.00% | 252.27 | 252.27 | - | - |
| 209 | Formation of 4 lane road from km 26/200-27/765 (From Vivekananda Chowrasta to Masjid in Nandipet Town) on Jankampet Navipet-Nanidepet road in Nizamabad Disrict | 1,200.00/  04.07.2023 | 2023-24 | 19.03.2025 | 60.00% | 612.63 | 612.63 | 0 | - |
| 210 | Widening existing single lane to Double lane connecting Mandal Head Quarter to District Head Quarter for road Takkadpally- Jukkal from km 0/0 to 10/150 in  Nizamabad District | 1,105.00/  27.11.2014 | 2015-16 | - | 100% | - | 877.55 | 65.45 | - |
| 211 | Providing C C Pavement ( BT road edge to Drain in Banswada town) in Km.148/0to 151/6 of Hyderabad -  Medak - Bodhan road in Nizamabad District | 690.00/  28-04-2015 | 2015-16 | - | 100% | - | 394.74 | - | - |
| 212 | Widening and Strengthening Kandaballur to Karnataka border (via) Sopur road from km 0/0 to 13/2 in Nizamaabd district | 1,400.00/  27.11.2014 | 2016-17 | - | 100% | - | 950.40 | - | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 213 | Construction of HLB at KM 151/4-6, on HMB road in Nizamabad district | 270.00/  27.11.2014 | 2016-17 | - | 100% | - | 186.25 | - | - |
| 214 | Construction of HLB at KM 21/4-6, on Jakoora-Mondi sadak road in Nizamabad district | 150.00/  27.11.2014 | 2016-17 | - | 100% | - | 109.83 | - | - |
| 215 | Construction of HLB at km 4/2 on Jukkal Madnoor road in Nizamabad Dist. | 305.00/  27.11.2014 | 2017-18 | - | 100% | - | 179.36 | - | - |
| 216 | Construction of HLB across Manjeera River from Dharmareddy to Muddapur via Venkampally road PR  road) in Nizamabad District | 3600.00/  27.11.2014 | 2017-18 | - | 100% | - | 1,617.55 | 79.61 | 3,890.00/  30.05.2016 |
| Formation of approach road to main work consrtuction of HLB across Manjeera River from Dharmareddy to Muddapur via Venkampally road PR road) in Nizamabad  District.(Newly formed Kamareddy Dist) | 2017-18 | - | 100% | 119.96 | 1,442.01 | - |
| 217 | Widening & Strengthening to Malthumedda - Gandhari PWD road via Mengaram from Km 0/0 to 32/6 in  Nizamabad district (Now in Kamareddy district) | 3,300.00/  27.11.2014 | 2017-18 | - | 100% | - | 3,358.79 | - | 3,485.00/  24.05.2022 |
| 218 | Widening and Strengthening to Thumpally X road to Machareddy X Road from Km 0/0 to 12/3 ( Working Reach from Km 0/0 to 3/0 and Km 11/8 to 12/3 ) in  Kamareddy District | 573.00/ 10-01-  2020. | 2020-21 | - | 100% | - | 441.55 | - | - |
| 219 | Widening and Strenthening of existing double lane road to four lane road on Hyderabad-Medak-Bodhan road from Km 117/9 to 119/0 (Yellareddy tankbund portion) Nizamabad district- Sub-work: Construction of HLB @ Km 117/9 and 118/8 on Hyderabad-Medak-Bodhan road  in Kamareddy district. | 500.00  /27.11.2014 | 2020-21 | - | 100% | - | 402.38 | 66.07 | - |
| 220 | Widening and strengthenin from double lane to four lane road of (i) Banswada-Uppalwai road from Km 25/3 to 26/6 (in Gandhari town limits) & (ii) Construction of HLB at Km 10/6-8 of Gandhari-Chedmal road in Kamareddy District | 920.00/  19.08.2020 | 2021-22 | - | 100% | 283.97 | 713.97 | - | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 221 | Widening of single lane to double lane road to Khandeballur to Karnataka Border via Vajrakandi, Sopur from 11/0 to 13/720 in Kamareddy district | 500.00/  27.11.2014 | 2021-22 | - | 100% | 8.17 | 324.47 | - | - |
| 222 | Widening of Single Lane to Double Lane road of Jukkal to Madnoor road from Km 13/0 to 18/4 in Kamareddy  District | 1,000.00/  19.08.2020 | 2021-22 | - | 100% | - | 707.67 | - | - |
| 223 | Improvements to i) Banswada- Bichkunda road from Km 0/7 to 2/0 (Km 0/0 to 1/1 Four lane and Km 1/1 to 2/0 Double lane) & ii) Pothangal to Hegdoli Camp via Karegaon, Hungarga road from Km 0/0 to 6/2 and iii) Construction of Box culvert (6m x 3m) 3 cells at Km 2/0-  2 on Kotagiri to Ethoda road in Nizamabad District | 624.00/  19.08.2020 | 2021-22 | - | 100% | - | 92.90 | - | - |
| 224 | Widening & Strengthening of Ankole to Hajipur road via Ankole camp from km.0/0 to 7/0 in Kamareddy district.(Working reach from 0/0 to 3/8) | 600.00/  19.08.2020 | 2021-22 | - | 100% | - | 500.35 | - | - |
| 225 | Re Construction of the HLB at Km 2/8-10 on Someshwar- Pothangal Road in Kamareddy District | 275.00/  23.05.2018 | 2018-19 | - | 100% | - | 220.81 | - | - |
| 226 | Widening of existing Double lane to four lane of (i) Nagpur - Hyderabad road section of NH 7 of Biknoor Town limits from Km 389/7 to Km 392/250 in Kamareddy District (ii) Improvements to Karimnagar Kamareddy Yellareddy road from Km 93/8 to 96/0 in Kamareddy District (iii) Widening and Strengthening of Domakond Muthyampet road from Km 8/6 to 10/6 (in  Domakonda town limits) in Kamareddy District | 1,000.00/  19.08.2020 | 2021-22 | - | 100% | - | 770.42 | - | - |
| 227 | Widening and Strengthening Edgi(Big) to Maharastra Border (via) Gulla fromkm 0/0 to 9/0 | 1,250.00/  27.11.2014 | 2017-18 | 2024 | 65% | - | 563.54 | - | - |
| 228 | Widening and Strengthening Jukkal Madnoor road from Km 0/0 to 13/0 in Nizamabad District | 1,900.00/  27.11.2014 | 2018-19 | - | 95% | - | 1,508.89 | - | - |
| 229 | Widening of Existing single lane road to Double lane road to Old NH-7 Narsannapalli to Bhiknoor via Kyasampalli, Muthyampet, Domakonda, Gottimukkala, Laxmidevunipally road from km 0/0 to 15/4 | 2,500.00/  17.04.2023 | 2023-24 | 2024 | 15% | - | - | 144.86 | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 230 | Construction of Box culverts at km 8/990, 10/280 & 13/170 on Madnoor - Pothangal road in Kamareddy District. | 300.00/  27.04.2021 | 2022-23 | 2024 | 30% | - | 24.14 | 51.42 | - |
| 231 | Construction of Four lane road on Karimnagar Kamareddy Yellareddy road from km 76/8 to 79/0 in  Kamareddy district | 1,400.00/  13.10.2022 | 2023-24 | - | 98% | - | 751.48 | 586.48 | - |
| 232 | Widening and Strengthening of existing single lane/Inermediate lane road Agapally - Kalwakurthy km 0/0 to 24/0 in R.R.District. | 3,000.00/ 2014 | 2015 | - | 100% | 193.00 | 2,143.00 | 109.55 | - |
| 233 | Improvements, Widening & Strengthening the exisitng carriageway of Hayathanagar - Anajpur road Km. 8/2 to 14/0 in R.R. Dist. | 2,400.00/ 2017 | 2018 | 2024.00 | 90% | - | 2,061.00 | - | - |
| 234 | Improvements & Stregthening the existing carriageway of Ibrahimpatnam to Anajpur road from KM. 0/0 to 13/0 in R.R. Dist. | 2,455.00/ 2017 | 2018 | - | 100% | 758.00 | 2,274.00 | 189.00 | - |
| 235 | W&S to Kothur to Solipur road from km 0/0 to 17/100 in R.R.Dist (Working reach from km 2/0 to 13/4) | 6,775.00/ 2018 | 2021 | - | 100% | 1,414.00 | 6,172.00 | 489.00 | - |
| 236 | W&S to Sagar PWD road to Sagar PWD (via) Eliminedu, Pocharam and Mangalpally village from a) Single lane raod to double lane road from Km 0/0 to 15/587 and b) Construction of Four lane carriageway approach road to TSIIC Industrial area from Km 0/0 to 0/650 in Ranga  Reddy District. | 5,920.00/ 2022 | 2022 | - | 100% | 4,064.00 | 4,064.00 | 661.00 | 7,000.00/ 2023 |
| 237 | Widening and Strengthening from Single lane to Double lane road from Maheshwaram to NH765 (via) Thummaloor from km 0/0 to 5/100 in R.R.Dist (Actual  length fropm km 0/0 to 4/940). | 1,420.00/ 2022 | 2023 | 2024 | 30% | 304.00 | 304.00 | - | - |
| 238 | Widening and strengthening of existing single lane to double lane road from Km 0/0 to 9/7 of Kadthal gate to  Padkal gate in Ranga Reddy District | 1,890.00/ 2023 | 2023 | 2025 | 3% | - | - | - | - |
| 239 | Improvements to Radial Road No.30 (Extn) i.e, Gopanpally Tanda 'X' Roads to Kollur from Km 0/0 to  7/7 in Hyderabad. | 10,333.66/  14.09.2015 | 2015-16 | 30.04.2025 | 80% | 1,397.67 | 6,539.88 | 0 | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 240 | Improvements of Radial Road No.30 i.e., from Hyderabad Central University Bus Depot to Vattinagulapally Village on Outer Ring Road in Ranga Reddy District | 15,200.00/18.05.2  016 | 2016-17 | 31.08.2024 | 40% | 143.61 | 728.85 | - | - |
| Improvements of Radial Road No.30 i.e., from Hyderabad Central University Bus Depot to Vattinagulapally Village on Outer Ring Road in Ranga Reddy District work withdrawn under clause 60-C from Km 3/100 to 8/340 | 2017-18 | 31.08.2024 | 90% | 5.91 | 2,717.31 | 225.60 |
| Improvements of Radial Road No.30 i.e., from Hyderabad Central University Bus Depot to Vattinagulapally Village on Outer Ring Road in Ranga Reddy District work withdrawn under clause 60-C from  Km 8/340 to 9/460 | 2022-23 | 31.08.2024 | 50% | - | 243.55 | - |
| 241 | Improvements of Radial Road No.30 i.e., from Hyderabad Central University Bus Depot to Vattinagulapally Village on Outer Ring Road in Ranga Reddy District.Sub work:- Construction of Flyover at ch: 7+855 on Radial Road No 30 at Gopanpalli thanda in  Rangareddy district (2nd Call) | 2,850.00/  18.05.2016 | 2019-20 | 31.12.2023 | 100% | 458.74 | 1,245.18 | 182.10 | - |
| 242 | Improvements of Radial Road No.7 Extn i.e Edulanagulapally to Kondakal Road from Km.0/0 to 5/7 (LHS) and from Km.0/0 to 2/3(RHS) and from Kondakal  to Mokhila Village (Master Plan Road) from Km. 5/7 to 10/2 in Hyderabad | 19,984.00/26.08.2  016 | 2017-18 | 31.03.2025 | 70% | 1,285.70 | 6,105.34 | 512.83 | - |
| Improvements of Radial Road No.7 Extn i.e Edulanagulapally to Kondakal Road from Km.0/0 to 5/7 (LHS) and from Km.0/0 to 2/3(RHS) and from Kondakal to Mokhila Village (Master Plan Road) from Km. 5/7 to 10/2 in Hyderabad work withdrawn under clause 60-c from Km 0/0 to 4/290 LHS Road | 2023-24 | 31.03.2025 | 100% | 1,816.24 | 1,816.24 | 1,816.24 |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
|  | Improvements of Radial Road No.7 Extn i.e Edulanagulapally to Kondakal Road from Km.0/0 to 5/7 (LHS) and from Km.0/0 to 2/3(RHS) and from Kondakal to Mokhila Village (Master Plan Road) from Km. 5/7 to 10/2 in Hyderabad work withdrawn under clause 60-c  from Km 4/290 to 9/300 LHS Road |  | 2023-24 | 31.03.2025 | 90% | 3,994.68 | 3,994.68 | 3024 |  |
| 243 | Improvement of Radial Road No.7 i.e., from Tellapur Junction to Edulanagulapally from km 0/0 to km 6/570 in Hyderabad | 9,400.00/  25.06.2016 | 2017-18 | 31.03.2025 | 80% | 576.16 | 8,753.91 | 2.00 | 12,700.00/  19.10.2020 |
| 244 | Construction of ROB in view of LC No.20 at Railway Km. 139/6-7 of Secundrabad - Wadi Section and at Km. 18/6-10 of Chevella - Shankarpally road in RR Dist (Sub- Work:- Impts to Chevella - Shankarpally road from Km.  18/900 to 19/800 & Constn of New Minor Bridge on U/S of existing Bridge (Widening) at Km. 19/4-6 in RR Dist) | 306.00/  09.01.2018 | 2019-20 | 30.06.2024 | 70% | - | 139.00 | 167.00 | - |
| 245 | Widening & Strengthening the existing carriageway  5.50mts to 10.00mts of JP Dargha gate to JP dargha Road from Km.0/850 to Km.9/2 in Rangareddy District | 1,800.00/  27.11.2014 | 2015-16 | 31.12.2017 | 100% | - | 1226 | 0 | - |
| 246 | Shankerpally-Marpally road from KM 21/6 to 22/450, 29/0 to 31/600 & 33/0 to 38/0 | 1,224.00/  27.11.2014 | 2015 | - | 100% | 0 | 1,194.00 | - | - |
| 247 | 1. Nagasamundram-Bantaram road from KM 0/0 to 10/2 & 2. Dharur-Kotepally road from KM 0/0 to 11/6 | 3150.00/  27.11.2014 | 2015 | - | 100% | 132.00 | 2,584.00 | - | - |
| 248 | Vikarabad-Tandur road from KM 3/0 to 39/3 | 5,220.00/  27.11.2014 | 2017 | 2024 | 70% | - | 3,256.00 | - | - |
| 249 | Pargi-Nancherla road from KM 16/0 to 30/0 including  C.D Works | 1,800.00/  27.11.2014 | 2016 | - | 100% | - | 1,510.00 | 112.00 | - |
| 250 | Tandur-Kotepally road from KM 20/0 to 25/425 | 600.00/  27.11.2014 | 2016 | - | 100% | - | 602.00 | - | 742.00/  31.08.2018 |
| 251 | Tandur-Turmamidi road from KM 0/0 to 23/325 | 2,400.00/  27.11.2014 | 2016 | - | 100% | - | 2,160.00 | - | - |
| 252 | Tandur Bypass road from KM 0/0 to 12/0 | 7,800.00/  27.11.2014 | 2019 | 2025 | 40% | 438.00 | 2,968.00 | 473.00 | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 253 | Construction of H L B across Kagna River near Jeevangi village at Km.5/8 on Basheerbad to Karankote road in Ranga Redy District. | 1,000.00/  27.11.2014 | 2017 | 2024 | 80% | - | 974.00 | 88.00 | 1,340.00/  20.02.2018 |
| 254 | Construction of Bridge at KM 73/6 to 74/0 on Mahaboobnagar-Chincholi road | 1,000.00/  27.11.2014 | 2016 | - | 100% | 0 | 1,570.00 | - | 1,680.00/  30.05.2016 |
| 255 | Construction of Bridges & Culverts on Manneguda- Vikarabad-Sadashivapet road from KM 11/6-8,14/4-6, 16/6-8 | 250.00/  27.11.2014 | 2017 | 2024 | 70% | - | 173.00 | 1.56 | 290.00/  12.05.2017 |
| 256 | Construction of Bridge at KM 22/8-10, 23/8-10 & 32/6-8 on Vikarabad - Tandur road | 380.00/  27.11.2014 | 2018 | - | 100% | - | 1,080.0 | 108 | 1,530.00/  20.02.2018 |
| 257 | Construction of Bridge at KM 8/8-10 & 10/4-6 on Tandur-Kotepally road | 400.00/  27.11.2014 | 2018 | 2024 | 75% | 50 | 516.00 | 0 | 890.00/  02.06.2016 |
| 258 | Construction of Bridges & Culverts on Vikarabad- Thangadpally road from KM 8/0-2 KM 10/6-8 & 11/2-4 | 120.00/  27.11.2014 | 2017 | 2024 | 70% | 71.00 | 268.00 | 0 | 550.00/  12.05.2017 |
| 259 | High level Bridge at KM 5/2-4 & 12/0-2 on Chittampaly- Lalpahad road | 525.00/  27.11.2014 | 2016 | 2024 | 90% | 0 | 286.00 | 0 | - |
| 260 | Construction of Bridges on i) Shankerpally-Marpally road from KM 9/4-6,12/8-10, 16/0-2, 20/0-2, 25/4- 6,31/8-10, 36/6-8 & 36/8-1 0 (ii) Budhera-Marpally road from KM 12/4-6 | 550.00/  27.11.2014 | 2018 | 2024 | 50% | 696.00 | 1,178.00 | - | 1,200.00/  12.05.2017 |
| 261 | Widening to Four Lane Carriageway with C.C Pavement in Tandur Town on Tandur-Kotepally Road from KM 0/0 to 1/0 in Vikarabad District | 750.00/  09.11.2017 | 2018 | - | 100% | 0 | 560.00 | 36 | - |
| 262 | Widening and strengthening of single lane to double lane road of M.V.S.Road from KM 22/0 to 26/0 | 850.00/  28.09.2016 | 2017 | 2024 | 80% | 0 | 633.00 | - | - |
| 263 | Widening and strengthening of two lane to four lane road of M.V.S.Road from KM 32/0 to 34/0 | 1,000.00/  28.09.2016 | 2017 | 2024 | 70% | 196 | 635.00 | 125.00 | - |
| 264 | Widening & Strengthening to Rajivrahadari (Shamirpet) to Usharpally Road from Km 0/0 to 17/0 | 2,000.00/  27.11.2014 | 2016-17 | - | 100% | 0 | 2,236.00 | 0 | 2,730.00/  24.05.2019 |
|  | Widening and Strengthening of Rajiv Rahadari to Usharpally from Km 0/0 to 17/0 in Ranga Reddy Dist.(Now in Medchal-Malkajgiri(Dist.) |  | 2019-20 | - | 100% | 0 | 16.35 | 0 |  |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 265 | Improvements to intermediate ring road form Km 24/5 to 31/4 in Medchal-Malkajgiri District | 1,500.00/  27.11.2014 | 2015-16 | - | 100% | 0 | 970 | 0 | - |
| Improvemenets to Intermediate Ring Road from Km 24/5 to 31/4 (Bachupally to Gandimaissamma Jn) in RR District (Now in Medchal Malkajgiri District).Sub work: Improvements to Intermediate Ring Road from Km 30/4  to 31/254 in Medchal Malkajgiri District | 2021-22 | - | 100% | 0 | 102 | 0 |
| 266 | Construction of Bridge at Km. 23/2- 6 on Wadiaram - Medak road | 400.00/  27.11.2014 | 2016 | - | 100% | - | 287.43 | - | - |
| 267 | Construction of HLB in Km 3/0-2 on Chevella to Pocharam road in Medak Dist | 135.00/  27.11.2014 | 2016 | 2024 | 65% | - | 69.57 | - | - |
| 268 | Construction of Bridge at Km. 5/2- 4 on Shankarampet - Masaipet road (5v of 10m) | 330.00/  27.11.2014 | 2016 | 2024 | 65% | - | 176.62 | - | - |
| 269 | Widening of Medak to Siddipet road DL to FL from km. 0/0 to 2/0 (Medak Town Limits) in Medak  District Under Corenet Plan | 454.00/  14.07.2015 | 2016 | - | 100% | - | 290.08 | - | - |
| 270 | Improvements to Medak to Siddipet road from Km. 19/0 to 20/2 & 20/5 to 23/0 (Ramayampet town  limits) in Medak District | 780.00/  29.10.2015 | 2016 | - | 100% | - | 396.73 | - | - |
| 271 | Strengthening of Hyderabad - Medak -Bodhan road from km 78/7 to 84/3 in Medak District | 1,515.00/  24.12.2015 | 2015 | - | 100% | - | 604.33 | 77.03 | - |
|  | Strengthening of Hyderabad - Medak -Bodhan road from km 78/7 to 84/3 in Medak District (Balance work) | - | 2021 | 2024 | 90% | 303.90 | 401.89 | - | - |
| 272 | Improvements of Minor Bridges on Narsapur-Kuknoor road at Km 2/8- 10, 8/6-8, 10/6-11/0, 15/4-6 in Medak District | 330.00/  30.12.2015 | 2016 | - | 100% | - | 306.14 | 26.10 | - |
| 273 | Improvements of Minor Bridges on Shankarampet- Narayankhed road (via) Regode in Km 8/8 to 9/2, Km 12/2 to 12/8 in Medak District | 210.00/  30.12.2015 | 2017 | 2024 | 35% | - | 65.76 | - | - |
| 274 | Improvements & Strengthening of Hyderabad - Medak - Bodhan road from Km 80/3 to 85/0 (Medak Town Limits) in Medak District Under Corenet Plan Sub Estimate :  Construction of footpaths along with table drain | 170.00/  29.07.2016 | 2022 | - | 100% | - | - | 52.44 | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 275 | Construction of Minor Bridges in km 4/738 and Km 5/027 (including approaches)on Medak-Sardana road in Medak District (Newly formed Medak District)" | 325.00/  20.08.2016 | 2017 | - | 100% | - | 189.68 | 65.86 | - |
| 276 | Widening and strengthning the Budera - Sirur road from Km 0/0 to 10/4 in Medak Dist. | 700 .00/  06.11.2015 | 2020-2021 | - | 100% | 0 | 531.52 | 48.68 | - |
| 277 | Widening and strengthening of Kangti-Kodapgal road from Km 0/0 to 13/646 in Medak District | 1,850.00/  19.2.2016 | 2020-2021 | - | 100% | - | 1,176.68 | - | - |
| 278 | Impts to Kandakam road from NH9 at Shiv shakthi Lodge to NH9 at Mysamagudi (via) Gollakeri, Harijanawada Eshwarnagar in Sadashivpet Municipality from Km 0/0 to 2/510 in Medak District.(Balance work) | 1,188.00/  22.09.2021 | 2021-2022 | 2024 | 75% | 0 | 638.74 | - | - |
| 279 | Improvements to Zaheerabad-Bider road from Km 1/0 to 19/2 (Appropriate reaches) in Sangareddy District | 300.00/  22.09.2021 | 2021-2022 | - | 100% | 0 | 269.18 | 0 | - |
| 280 | Improvements to NH-9 to Sangareddy (via) Pedapur, Mubarakpur road from Km 0/0 to 10/0 | 1,200.00/  04.09.2015 | 2021-2022 | 2024 | 65% | - | 532.59 | - | - |
| 281 | Improvements to Narayankhed- Digulwadi road from Km 0/0 to 35/7 | 5,300.00/  16.10.2015 | 2021-2022 | - | 100% | 10.56 | 615.53 | 180.95 | - |
| 282 | Improvements to Nizampet"X" road to Kalher from Km 0/0 to 15/8 | 1,900.00/  16.11.2015 | 2021-2022 | - | 98% | 2.64 | 1,364.64 | - | - |
| 283 | Widening of Single lane carriageway to double lane of Narsapur PWD road to Begumpet PWD road from Km  0/0 to 6/5 in Medak Distrct (Now Sangareddy district) | 650.00/  10.10.2017 | 2020-2021 | 2024 | 90% | - | 427.5 | 0.0 | - |
| 284 | Widening of Single lane carriageway to double lane from Km 1/4 to 4/2 of Isnapur ODF to Indrakaran | 280.00/  10.10.2017 | 2020-2021 | 2024 | 95% | - | 169.66 | - | - |
| 285 | Widening of carriageway from Single lane to double lane of Jogipet- Vatpally road from km 17/0 to 21/0 | 500.00/  09.11.2015 | 2021-2022 | - | 100% | 0 | 402.05 | 45.47 | - |
| 286 | Widening of Single lane carriageway to double lane from Km 9/0 to 15/0 of Patancheru- Malkapur road | 600 .00/  09.11.2015 | 2020-2021 | 2024 | 90% | - | 355.75 | - | - |
| 287 | Widening of Single lane carriageway to double lane from Km 2/4 to 6/7 of Alipur to Kothur road | 450.00/  06.11.2015 | 2020-2021 | - | 100% | 0 | 294.92 | 0.0 | - |
| 288 | Widening of carriageway from Single lane to double lane of Sangupet- Pocharam road from Km 10/0 to 14/0 | 500.00/  09.06.2017 | 2021-2022 | 2024 | 90% | - | 272.41 | - | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 289 | Widening of Single lane carriageway to double lane from Km 12/7 to 18/450 of Zaheerabad- Bonuspur road | 550.00/  06.11.2015 | 2020-2021 | - | 100% | - | 402.89 | - | - |
| 290 | Construction of HLB in Km 1/0-2 on Pochapur"X" Road to Krishnapur (via) Khanapur | 228.00/ 5.7.2016 | 2020-2021 | - | 100% | 0 | 162.01 | - | - |
| 291 | Construction of HLB in Km 9/2-4 on Road from Shankarampet to Narayankhed road (via) Bujrampally (4V of 10M) | 268.00/ 5.7.2016 | 2020-2021 | - | 100% | 0 | 167.27 | - | - |
| 292 | Construction of HLB in Km 28/8-10 on Narayankhed- Masanpally(via) Nallavagu (7V of 8M) | 295.00/  05.07.2016 | 2020-2021 | - | 100% | 0 | 196.00 | 48.68 | - |
| 293 | Construction of HLB in Km 29/6-8 on Narayankhed- Masanpally(via) Nallavagu (5V of 10M) | 325.00/  05.07.2016 | 2020-2021 | - | 100% | 0 | 217.61 | - | - |
| 294 | Construction of HLB in Km 13/4-6 on Peddapur - Ananthasagar road | 255.00/  20.12.2016 | 2020-2021 | - | 100% | 18.99 | 192.96 | - | - |
| 295 | Construction of HLB in Km 2/8-10 of SNA"X" Road to Singoor project road | 280.00/  20.12.2016 | 2020-2021 | - | 100% | 0 | 181.87 | 25.24 | - |
| 296 | Construction of HLB at Km 6/8-10 of Kangti-Kodapgal road in Medak district ( 3V of 8M) | 210.00/ 29.4.2016 | 2020-2021 | - | 100% | 39.21 | 181.38 | - | - |
| 297 | Construction of HLB in Km 21/4-6 of Narayankhed- Digulwadi road (5V of 10M) | 350.00/ 9.1.2017 | 2020-2021 | - | 100% | 34.61 | 295.57 | - | - |
| 298 | Construction of HLB in Km 12/6-8 on Patancheru- Malkapur road in Medak district | 240.00/  11/09/2017 | 2020-2021 | - | 100% | 0 | 168.27 | - | - |
| 299 | Construction of HLB in Km 21/8-10 of Kothapally- Chinthakunta road | 265.00/ 29.4.2016 | 2021-2022 | 2024 | 75% | 0 | 107.28 | - | - |
| 300 | Construction of HLB in Km 13/8-10 on Road from Muduguntal to Chapta"X" Road (4V of 8M) | 180.00/  14/07/2016 | 2021-2022 | 2024 | 70% | 44.15 | 160.77 | - | - |
| 301 | Construction of HLB in Km 0/6-8 of Narayankhed- Digulwadi road | 260.00/  01/07/2016 | 2021-2022 | 2024 | 0% | 0 | 0 | 0 | - |
| 302 | Construction of HLB in Km 1/0-2 on PWD Road Malchelma to Govindpur (via) Jadimalkapur in Medak  district (8V of 10M) | 397.00/  29/04/2016 | 2021-2022 | 2024 | 90% | 0 | 265.95 | 33.24 | - |
| 303 | Construction of HLB in Km 11/2-4 on Road from Kohir to Gudgarpally (via) Badampet (5V of 10M) | 290.00/  29/04/2016 | 2021-2022 | 2024 | 70% | 0 | 45.02 | - | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 304 | Improvements of Minor Bridges on Narayankhed- Digulwadi road in Km 6/6 to 7/2, Km 17/4 to 18/0, 27/6 to 28/0, 29/0 to 29/4 in Medak District | 720.00/  02.06.2016 | 2021-2022 | 2024 | 75% | 0 | 242.88 | - | - |
| 305 | Construction of Four lane carriageway from IDA Pashamailaram Industrial park to outer Ring road (i.e., at Patancheru-Shankerpally road junction) from Km 0/0 to  4/5 in Sangareddy district | 4,500.00/  16.7.2022 | 2021-2022 | - | 95% | 442.66 | 2,739.64 | 969.63 | - |
| 306 | Improvements to Ponnala - Thimmareddypally road from Km. 0/0 to 20/5 in Medak District | 2,672.00/  27.11.2014 | 2015 | - | 100% | - | 1,921.00 | - | - |
| Improvements to Ponnala - Thimmareddypally road from Km. 0/0 to 20/5 in Medak District.  Improvements to balance Reaches on Ponnala-  Thimmareddypally road from Km 6/430 to 7/270 (in Marpadaga Village Limits) in Siddipet District. | 2023 | - | 100% | - | - | 175.00 |
| 307 | Widening of carriageway from double lane to four lane on Siddipet bye Pass road from from Km 0/0 to 14/2 in Medak District | 5,000.00/  27.11.2014 | 2015 | - | 100% | - | 3,408.00 | 72.00 | - |
| 308 | Widening of carriageway from Single lane to Double lane Ibrahimpur to Dubbak road from km 6/4 to 8/2  &10/0 to 18/2 in Medak District | 1,200.00/  27.11.2014 | 2015 | - | 100% | - | 791.00 | - | - |
| 309 | Widening of carriageway from Single lane to Double lane Jakkapur to meet Medak-Siddipet road from Km 0/0to 24/2 in Medak District: Improvements to Balance reaches on Jakkapur to meet Medak-Siddipet Road from Km 1/8-2/1 (in Gopulapur Village Limits) and from Km 7/6-8/0 (in Narayanraopet Village Limits) in Siddipet  District. Sub Estimate Amount of Rs.218.00 Lakhs. | 218.00/  27.11.2014 | 2022 | 2024 | 75.00% | 8.00 | 126.00 | - | - |
| 310 | Widening of Carriage way to 6 L from Km. 63/8 to 67/6 Siddipet town limits on Medak to Siddipet  road in Medak District Withdrawn under 60 © Package-I | 2,000.00/  26.10.2015 | 2019 | - | 100% | - | 21.00 | 2.00 | - |
| 311 | Widening & Strengthening of Filter bed to Mustabad road via Kappalakunta from km. 0/0 to 1/0 in Siddipet District. | 118.00/  22.08.2017 | 2017 | - | 100% | - | 162.00 | 29.00 | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 312 | Improvements to Bussapur to Thimmayapally road from km. 31/0 to 39/0 (Working reach from Km 57/500 to60/600) in Siddipet District. | 1,000.00/  18.12.2017 | 2018 | 2024 | 60.00% | - | 460.00 | - | - |
| 313 | Improvements to (i) Medak - Siddipet road from km.34/0 to 38/0 (ii) Medak - Siddipet road from km.39/0 to 55/0 (iii) Medak - Siddipet road from km.55/0 to 63/8  (iv) Elkathurty - Siddipet road from km.19/370 to 26/0 in Siddipet District. | 590.00/  07.08.2018 | 2018 | - | 100% | - | 471.00 | 74.000 | - |
| 314 | Widening & Strengthening to 4 Lane in Km.49/8 to 54/3 on Machareddy - Mustabad - Siddipet road in Siddipet District | 1,655.00/  06.09.2018 | 2019 | 2024 | 95.00% | 112.00 | 1,280.00 | - | - |
| 315 | Widening & Strengthening to 4 Lane in Km.26/8 to 32/9 on Sircilla - Siddipet road in Siddipet District | 3,000.00/  06.09.2018 | 2019 | 2024 | 65.00% | 647.00 | 2,396.00 | - | 4,400.00/  22.04.2022 |
| 316 | Construction of Four lane road from Siddipet to Ellanthakunta mandal head quarter (from km 0/0 to 22/0)  on Siddipet - Kistapur road in Siddipet District. | 9,000.00/  19.03.2021 | 2023 | 2025 | 20.00% | 1,149.00 | 1,169.00 | 203.00 | - |
| 317 | Construction of Four lane road from Siddipet to Ellanthakunta mandal head quarter (from km 0/0 to 22/0) on Siddipet - Kistapur road in Siddipet District Sub- Work: Maintenance work from Km 10/0 to 22/0 (Work in reach 11/4 to 15/520, 15/8 to 18/0 and 20/100 to 20/500)  of Siddipet-Ellanthakunta road in SIddipet District. | 231.00/  19.03.2021. | 2023 | - | 100.00% | - | - | 184.00 | - |
| 318 | Construction of Outer Ring Road to Siddipet town from Km 0/0 to 87/190 (Working Reach from Km 13/360 to 33/030, 36/580 to 55/930 & Km 63/650 to 84/794) in Siddipet District. | 16,400.00/07.12.2  020. | 2022 | 2024 | 85.00% | 3,246.00 | 11,493.00 | 1776.00 | - |
| 319 | Construction of HLB at Km 18/4-6 (near Dargapally Village on Machapur-Nanganoor Road in Siddipet District) (9 Vents of 10m Span) | 715.00/  09.11.2021 | 2022 | 2024 | 55.00% | 111.00 | 234.00 | 81.00 | - |
| 320 | Widening & Strengthening of existing Single lane to double lane road of NH7 to Deverkadra (via) Vemula, Laxmipally from Km.0/0 to 17/3 in Mahabubnagar District. | 2,336.00/  27.11.2014 | 2016 | 2024 | 30% | - | 414.96 | 135.48 | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 321 | Widening SL to DL connecting MHQ to DHQ for Mahabubnagar-Mannanur road from Km.8/4 to 10/8 in Mahabubnagar District. | 300.00/  27.11.2014 | 2015 | - | 50% | 0 | 159.59 | 0 | - |
| 322 | Formation of Bye Pass Road to the Mahabubnagar town starting from km 6/8 of Mahabubnagar -Nalgonda Road (R/s) and ends at km 3/4-6 of Mahabubnagar-Raichur  Road in Mahabubnagar District. | 9,670.00/  12.09.2016 | 2017 | - | 100% | 0 | 3862 | 0 | - |
| 323 | Improvements to the road from CC Kunta to Kurumuthy Swamy Temple road from km 0/0 to 4/800 and Bridge at  km 0/4 in Mahabubnagar District | 4,000.00/  04.09.2018 | 2022 | 2024 | 80% | 1,048.22 | 2,608.81 | 375.54 | - |
| 324 | Construction of HLB at km 3/800 including formation of approaches for a length of 1.70km on NH-44 to Kurumurthy swamy temple road via Varne, Perur in  Mahabubnagar District | 1,800.00/  25.04.2022 | 2022 | 2024 | 65% | 269.84 | 269.84 | 220.75 | - |
| 325 | Improvements to Mahabubnagar-Mannanur road from Km.1/0 to 3/0 in Mahabubnagar District (Sub-work for Construction of 4 lane Minor Bridge at Km.1/0-2 of Mahabubnagar - Mannanur road in Mahabubnagar District) | 210.00/  10.12.2012 | 2023 | 2024 | 40% | 0 | 0 | 42.71 | - |
| 326 | Construction of HLB at km.4/8-10 on Nawabpet PWD road to Kondurg upto kollur road in Mahabubnagar district | 300.00/  27.11.2014 | 2021 | - | 100% | 0 | 174.00 | 82.69 | - |
| 327 | Widening and Strengthening of Appakapally - Koilkonda Road for 28.150 Kms (Km 0/0-10/0 of Appakapally Gundumal Road and Km 0/0 -18/150 of Kotakonda - Koilkonda Road) in Narayanpet SDF Grant | 5,600.00/  04.11.2022 | 2023 | 2025 | 30% | 0 | 0 | 879 | - |
| 328 | Widening SL to DL connecting MHQ to DHQ for Tunkimetla-Narayanpet Road from Km.56/0 to 67/137 in Mahabubnagar District.(working reach 56/0 to 65/2) | 1,583.00/  27.11.2014 | 2016 | - | 100% | 0 | 1023 | 60.06 | - |
| 329 | Widening single lane to double lane Mandal head quarter to district head quarter of NH-7- Itkyal Road Km. 0/0 to 7/0. | 850.00/  27.11.2014 | 2015-16 | 2024 | 54.00% | 0 | 453.59 | 0 | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 330 | Widening single lane to double lane Mandal head quarter to district head quarter of Dharur Old Road Km. 0/0 to 1/1. | 150.00/  27.11.2014 | 2015-16 | - | -% | 0 | 0 | 0 | - |
| 331 | Widening single lane to double lane Mandal head quarter to district head quarter of YIA Road Km. 51/6 to 57/0  (work in Km. 51/6 to 53/0) | 320.00/  27.11.2014 | 2015-16 | - | -% | 0 | 0 | 0 | - |
| 332 | Widening single lane to double lane of Yerrigera - Ieeja - Alampur Road Km. 21/0 to 27/0 and Km. 30/0 to 36/5. | 1,688.00/  27.11.2014 | 2015-16 | 2024 | 61.00% | 0 | 1,028.75 | 0 | - |
| 333 | Construction of HLB at Km 18/2-4 on NH-7 to Venkatapur road in Mahabubnagar District. (5 vents of 8 m span)(Satarla Vagu) | 255.00/  27.11.2014 | 2017-18 | - | 100% | 0 | 146.21 | 0 | - |
| 334 | Construction of HLB at Km 10/4-6 on NH 7 - Pragatoor road in Mahabubnagar District.(6 vents of 10 mts span)( Garlapadu Vagu) | 252.00/  27.11.2014 | 2017-18 | - | 20.00% | 0 | 0 | 9.95 | - |
| 335 | Construction of HLB at km. 14/2-4 of Gattu - ieeja road in Mahabubnagar District.( 7 Vents of 10m  span)( Eklaspur Vagu) | 620.00  /27.11.2014 | 2017-18 | - | 53.00% | 0 | 326.23 | 0 | - |
| 336 | Construction of HLB at Km 30/6-8 on Gadwal -Raichur road in Mahabubnagar District. ( 10 V of 10m  Span)( Nandini Vagu) | 795.00/  27.11.2014 | 2017-18 | - | 100% | 0 | 539.13 | 64.24 | - |
| 337 | Construction of HLB at Km. 55/6-10 on Y-I-A Road (Kalkuntla Vagu)(12 vents of 10m )Kalkuntla Vagu) | 600.00/  27.11.2014 | 2020-21 | 2024 | 80.00% | 0 | 399.82 | 36.05 | - |
| 338 | Construction of 4- lane HLB at Km 29/2-4 on Gadwal - Ieeja road in Mahabubnagar District.( 7 vents of 10.00 m span)( Ieeza Peda Vagu) | 700.00/  12.05.2017 | 2022-23 | 2024 | 80.00% | 389.11 | 389.11 | - | - |
| 339 | Widening and strenthening of existing yerrigera - Ieeja - Alampur Road From Km 10/3 To 24/0 (Working Reach km 10/3 To 21/0) in Mahabubnagar | 1,060.00/  06.12.2013 | 2017-18 | 2024 | 18.00% | 0 | 185.99 | 176.63 | - |
| 340 | Widening and strenthening of existing Ieeja - Rajapur Road From Km 0/0 To 14/0 (Working Reach km 0/0 To 7/0 & Km 8/7 to 14/0 ) in Mahabubnagar District. | 1,274.00/  22.01.2014 | 2023-24 | 06.10.2024 | 26.00% | 0 | 324.25 | 14.26 | - |
| 341 | widening and strengthening of Gadwal - Ieeja km from 17/4 to 26/0 in Mahabubnagar District | 925.00/  12.12.2013 | 2016 | - | 100% | 0 | 647.87 | 142.2 | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 342 | Construction of Bridge across River Tungabadra near Alampur in Mahabubnagar District (RDC Work) | 3,500.00/  23.12.2008 | 2009-10 | - | 100% | 0 | 3,443.04 | 294.55 | - |
| 2016-17 | - |  | 0 |  |  |
| 343 | Gadwal Outer Ring Road Km. 0/0 to 6/270. | 2,300.00/  17.2.2014 | 2015 | 2024 | 50% | 0 | 513.04 | 107.55 | - |
| 344 | Widening & Strengthening of existing Single lane to double lane road of Telkapally-Lingala from Km.0/0 to 19/8 in Mahabubnagar District. | 2400.00/  27.11.2014 | 2016 | - | 100% | -- | -- | 349.52 | - |
| 345 | 1. Peddakothapalli-Nagulapally Road from Km.0/0 to 9/0 2. Narsaipally-Nagarkurnool road from Km.10/0 to 12/0 (Est.Rs 1100.00 + 250.00=1350.00) | 1,350.00/  27.11.2014 | 2016 | 2024 | 95% | 757.17 | -- | -- | - |
| 346 | Widening & Strengthening of existing Single lane to double lane road of Teegalapally-Yapatla from Km.0/0 to 23/050 Road inMahabubnagar District. | 3,112.00/  27.11.2014 | 2017 | 2024 | 85% | 97.45 | 1723 | -- | - |
| 347 | Widening & Strengthening of existing Single lane to double lane road of Singotam-Yedutla from Km.0/0 to 27/3 in Mahabubnagar District. | 3,686.00/  27.11.2014 | 2017 | 2024 | 27% | - | 685 | -- | - |
| 348 | Widening and strengthening of existing Single lane to Double lane road of Teegalapally - Yapatla from Km 0/0 to 23/050 in Mahabubnagar District. Sub work : Construction of CC road from Km 6/550 to Km 7/050 in Nagarkurnool District | 105.00/  27.11.2014 | 2023 | - | 100% | -- | -- | 75.79 | - |
| 349 | Construction of HLB at Km.48/6-8 on Mahabubnagar to Mannanure road road in Mahabubnagar District. | 775.00/  27.11.2014 | 2017 | - | 100% | 467.85 | -- | -- | - |
| 350 | Construction of bridges at km.7/8-10, 10/6-8, 10/8-10 & 18/2-4 on Veldanda - Sirsangandla road in Mahabubnagar Dist | 430.00/  27.11.2018 | 2021 | 2024 | 70% | -- | -- | 58.08 | - |
| 351 | Construction of Footpath from km 45/0 to 48/600 in Nagarkurnool town portion on Mahabubnagar to Mannanur road in Nagarkurnool district | 290.00/  16.01.2018 | 2018 | 2024 | 30% | 65.27 | -- | -- | - |
| 352 | Improvements to Mahabubnagar - Mannanur road from Km 34/200 to 34/800 in Bijinapally town portion in Nagarkurnool District | 195.00/  16.01.2018 | 2018 | - | 100% | 176.3 | -- | -- | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 353 | Periodical Renewals to Wanaparthy - Jadcherla road from Km 18/0 to 51/0 ( in Appropriate reaches ) in Nagarkurnool District | 500.00/  22.03.2018 | 2018 | - | 100% | 354.4 | -- | -- | - |
| 354 | Package I Works - (a) Improvements to Mahabubnagar - Mannanur road from Km 23/0 to 27/0, 33/4 to 34/2 & 34/8 to 41/0 in Nagarkurnool District , (2) Improvements to Mahabubnagar - Mannanur road from Km 41/0 to 43/6  & 53/750 to 55/0 in Nagarkurnool District | 500.00/  07.08.2018 | 2019 | - | 100% | 408 | -- | 31 | - |
| 355 | Widening and Strengthening of Pentlavally X Road to Sreerangapur via Thoomkunta from Km 0/0 to 3/0 in Nagarkurnool District | 450.00/  15.02.2018 | 2018 | 2025 | 0% | -- | -- | -- | - |
| 356 | Improvements to NH765 Dindi to Ulpara via Gajara, Dindichintapally road from Km 7/600 to 21/0 in Nagarkurnool District | 1,300.00/  15.02.2018 | 2019 | - | - | -- | -- | 215.95 | - |
| 357 | Improvements to Wanaparthy - Jadcherla road from Km 18/0 to 26/0 (in Appropriate reaches ) in Nagarkurnool District | 516.00/  05.03.2022 | 2022 | 2024 | 90% | 408.43 | - | -- | - |
| 358 | Improvements to Wanaparthy - Jadcherla road from Km 26/0 to 41/500 (in Appropriate reaches ) in Nagarkurnool  District | 1,671.00/  05.03.2022 | 2022 | 2024 | 85% | 1,116.4 | - | -- | - |
| 359 | Improvements to Shanaipally to Gowreddypally Road from km 24/6 to 30/2 in Nagarkurnool District | 352.6.00/  01.07.2022 | 2023 | 2024 | 80% | 269.4 | - | -- | - |
| 360 | Improvements to Peddakothapally-Nagulapally Road from km 9/0 to 13/3 in Nagarkurnool District. | 753.50  /20.12.2022 | 2023 | 2024 | 40% | 195.44 | - | 118 | - |
| 361 | Widening and Strengthening of Wanaparthy-Kollapur Road from Km. 14/686 to 15/1 and Construction of C.C Side Drain on Wanaparthy - Kollapur road from km. 14/2 to 15/4 in Wanaparthy District (sub work) | 2,300.00/  27.11.2014 | 2022-23 | - | 100% | - | 150.00 | - | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 362 | Widening & Strengthening of existing Single lane to double lane road of Nagarkurnool-Gopalpet (via) Revally from Km.0/0 to 36/4 in Mahabubnagar District.(Wanaparthy Division from km. 12/0 to 36/618 = 24.618 kms,Submerged in Yedula project from km. 16/0 to 20/700 = 4.700 kms , HLB portion 13/180 to 14/150 =  0.97 kms ) 24.618-5.67=18.948 kms. | 4,914.00/  27.11.2014 | 2018-19 | - | 96.06% | 1,387.90 | 4,662.00 | - | 5,336.00/  03.11.2023 |
| 363 | Package 1: (1) Widening and Strengthening of existing I.L/D.L to Four Lane on Wanaparthy - Jadcherla road from km 0/0 to 3/0 in Wanaparthy District, (2) Construction 2v of 10 mts HLB (four lane ) acorss Jerripothulavagu at km 3/8-10 on Wanaparthy - Jadcerla road in Wanaparthy District, (3) Construction of 3v of 10 mts HLB (four lane ) across Thallavagu at km 0/6-8 on  Wanaparthy - Jadcherla road in Wanaparthy district. | 2,700.00/  8.12.2020 | 2021-22 | 22.8.2024 | 60% | - | 900.00 | 707.00 | - |
| 364 | Package-2 (1) Widening and Strengthening of existing S.L/D.L road to Four Lane road on Wanaparthy- Buddaramroad from Km 0/0 to 1/0 in Wanaparthy District, (2) Widening of existing Double lane road to Four Lane road onWanaparthy-Kollapur road from Km 0/0 to 1/0 in Wanaparthy District, (3) Widening & Strengthening of existingDouble lane to Four lane on Wanaparthy to Pebbair road from Km 0/0 to 1/0 in Wanaparthy District, (4)Construction of 10.0 mts span four lane HLB across Nalla cheruvu vaagu at Km 0/4-6 on Wanaparthy -Buddaram ( near Chinthala Hanuman  temple) in Wanaparthy District. | 2,270.00/  8.12.2020 | 2021-22 | 16.8.2023 | 42.65% | 208.00 | 808.00 | 160.00 | - |
| 365 | Construction of By Pass Road from km 0/0 to 8/8 connecting Wanaparthy - Atmakur road (at km 4/6-8 and Wanaparthy - Kollapur road (at km 5/2-4) in Wanaparthy District. | 7,300.00/  3.10.2022 | 2023-24 | 08.10.2025 | - | - | - | - | - |
| 366 | Construction of HLB at km 1/8-10 on Balijapally Branch road in Wanaparthy District | 300.00/ 11.8.2023 | 2023-24 | 5.10.2024 | 20.00% | - | - | - | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 367 | Construction of HLB at km 1/8-10 on Pebbair - Yaparla road in Wanaparthy District | 800.00/ 11.8.2023 | 2023-24 | 8.10.2024 | 24% | - | - | 190.00 | - |
| 368 | Construction of HLB across Ukashettyvagu at Km 21/2-6 on Wanaparthy - Atmakur road in Mahabubnagar District | 925.00/  27.11.2014 | 2023-24 | 04.05.2024 | 43% | 300.00 | 300.00 | - | - |
| 369 | Widening and strengthening of Suryapet -Bheemaram - Shettypalem road (Suryapet to Bheemaram Km 0/0 to 6/0 &Tekumatla bridge to Shettypalem road Km 11/0 to 34/0 in Nalgonda District. | 3,500.00/  27.11.2014 | 2016-17 | - | 90% | -- | 3,498.69 | -- | 4,940.00/  21.09.2017 |
| 370 | Construction of Fly over at Marriguda Junction km 13/6  - 14/0 on NAM road in Nalgonda District (2nd Call) | 4,500.00/  29.04.2022 | 2022-23 | 20.05.2024 | 50% | 211.97 | 228.25 | 1408.12 | 4,500.00/ |
| 371 | W&S to Old NH-9 Narketpally town portion from Km 85/0-88/6 (working Reach 85/4-87/8) in Nalgonda Dist. | 1,600.00/  09.01.2023 | 2023-24 | 19.12.2024 | - | 773.06 | 830.86 | 0 | 1,600.00/ |
| 372 | Kunkuduchettuthanda to Mahaboobnagar - Nalgonda road from Km.32/6 to 42/2 (PA Pally mandal headquarters) in Nalgonda district | 1,200.00/  27.11.2014 | - | - | 100% | 997.73 | 0 | 0 | 1,276.00/  26.04.2024 |
| 373 | Dindi-Devarkonda road from Km.3/5 to 33/8 (connecting Dindi mandal Headquarters) in Nalgonda district | 3,983.00/  27.11.2014 | 2015-16 | - | 100% | 3,493.88 | 0 | 0 | 4,361.00/ |
| 374 | Widening and strengthening Huzurnagar PWD Road to Nalgonda PWD Road (Via) Yadgarpally road from Km 0/0 to 5/0(Working in km 0/0 to 3/8) in Nalgonda District | 400.00/  27.11.2014 | 2015-16 | - | 100% | 285.3 | 0 | 74.00 | - |
| 375 | Improvements to PWD road to Wadapally 0/0 to 1/0 | 180.00/  01.03.2016 | 2016-17 | - | 100% | 102.43 | 0 | 15.6 | - |
| 376 | Widening & Strengthening to Marammagudi- Thungapahad road from km 0/0 to 10/2 & Tripuraram -  Adavidevulapally road from Km.13/2 to 24/4 | 2,600.00/  01.03.2016 | 2016-17 | -- | 100% | 162.1 | 0 | 0 | - |
| 377 | Widening and strengthening of Devarakonda -Madugula road from km 7/2 to 18/8 in Nalgonda District | 900.00/  01.03.2016 | - | -- | 100% | 585 | 0 | 1.15 | - |
| 378 | Construction of HLB in Km. 2/8-10 on Tripuraram - Kukkadam road | 375.00/  28.09.2016 | 2022-23 | - | 60% | 0 | 0 | 182.13 | - |
| 379 | Construction of HLB at Km 0/2-4 on Thummadam - Parvathipuram road | 200.00/  12.05.2017 | 2021-22 | 2025 | - | 0 | 0 | 0 | - |
| 380 | Improvements to Salkunoor to Bommakal cross road via Mangapuram from km 0/0 - 4/2 in nalgonda District | 353.00/  25.05.2023 | 2023-24 | 14.03.2025 | - | 0 | 0 | 0 | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 381 | Formation of Ring road to Huzurnagar Town portion from km 6/150 to 8/150 in Suryapet District. | 600.00/  01.02.2022 | 2022 | 2024 | 10% | 0 | 0 | 0 | - |
| 382 | Widening and strengthening of Single lane to Double lane road connecting Mandal Head Quarters to District Head Quarters from PWD road to Atmakur (S) from km  0/0 to 4/5 in Suryapet District. | 600.00/  27.11.2014 | 2015 | 2024 | 100% | 0 | 504 | 0 | - |
| 383 | Construction of Minor Bridge at Km 13/2-4 on Rammanapet to Yennaram road | 190.00/  27.11.2014 | 2016-17 | 2024 | 80.00% | 0 | 91.8 | 0 | - |
| 384 | Widening and Strengthening to Bibinagar - pochampally road from km 0/0 to 16/400 in Nalgonda District. | 2,100.00/  27.11.2014 | 2015-16 | - | 100% | 0 | 1,223.14 | 216.89 | - |
| 385 | Construction of HLB across Musi River at Manaikunta village to Gurajalavillage in Nalgonda District. | 1,800.00/  27.11.2014 | 2015-16 | - | 100% | 0 | 1,518.52 | 0 | - |
| 386 | Improvements to Bhongir to chityal road from km8/0- 12/295,14/0 to 18/0,35/0 to 37/0 in Yadadri Bhongir dist improvements to Bhongir Jagdevpur road from Km0/0 to  18/0 [appropriate reaches] in Yadadri Bhongir Dist[CRN] | 568.00/  07.08.2018 | 2018-19 | - | 100% | 0 | 356 | 0 | - |
| 387 | Forming 6 lane Ring road around Yadadri Temple along with New Ghat road landing towards North EastCorner  and Link roads in Yadadri. | 23,570.00/  28.02.2018 | 2018-19 | 31.08.2024 | 64.00% | 0 | 15,496.10 | 0 | 23,570.00/  05.03.2022 |
| 388 | W&S of 1)Thurkapally-Yadagirigutta Road from Km. 0/0 to 15/4 2)Kolanpaka - Begumpet Road from Km. 0/0 to 1/4 and Rajapet-Kolanpaka PWD Road to Yadadgirigutta -Rajapet PWD Road via Doodivenkatapur Km. 0/0 to 9/4 in Yadadri Bhongir District 3)PWD Road to Gopalpur via Kondapur, Vasalamarri from Km. 0/0 to 4/6 4)Thurkapally - Rangapur Road from Km. 0/0 to 17/8 (Work in Km. 0/0 to 8/0) 5) Yadagirigutta - Cheriyal Road from Km. 1/0 to 29/5 6)Wangapally - Yadadgirigutta Road from Km.  0/0 to 5/6 7)Raigiri-Mothkur road from Km. 10/0 to 27/0 | 11900.00/04.11.2  019 | 2019-20 | 2024 | 74.00% | 0 | 8,679.71 | 0 | 119.00/  17.09.2020 |
| 389 | Widening and Strengthening of Single lane to four lane road from NH61(Nirmal town ) to Bangalpet via Yellapally ,IDOC from 0/0 to 3/6 Km | 2,800.00/  17.11.2022 | 31.01.2023 | 30.07.2023 | 75% | 1,613.82 | 1,613.82 | - | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 390 | R/F Pyaramoor to Kadali (upto Temple) | 400.00/  22.10.2022 | 15.02.2023 | 14.02.2024 | 25% | 122.44 | 122.44 | - | - |
| 391 | B/w on R/f Macharla to Jorpur | 315.00/  11.08.2022 | 09.10.2023 | 08.10.2024 | 50% | 146.47 | 146.47 | - | - |
| 392 | R/f Degam to Godavari | 465.00/  11.08.2022 | 09.10.2023 | 08.10.2024 | 50% | 284.69 | 284.69 | - | - |
| 393 | Burugupally PWD road to Kondaipally | 132.00/  09.11.2021 | 19.09.2022 | 18.09.2023 | 75% | 88.58 | 88.58 | - | - |
| 394 | PWD Road Magdumpur to Cherlabuthkur- Elabotharam cross road | 200.00/  09.11.2021 | 13.06.2022 | 12.06.2023 | 75% | 132.45 | 132.45 | - | - |
| 395 | Ambari[pet bridge to rampur via Anthargam yellamma temple | 180.00/  09.11.2021 | 25.08.2022 | 24.08.2023 | 25% | 38.67 | 38.67 | - | - |
| 396 | Construction of Bridge At Vengumatla | 400.00/  18.12.2021 | 12.12.2022 | 11.03.2024 | 25% | 116.21 | 116.21 | 192.43 | - |
| 397 | Construction of Bridge at Lothunur | 200.00/  18.12.2021 | 03.03.2023 | 02.03.2024 | 25% | 28.60 | 28.60 | 20.34 | - |
| 398 | Road from Sriramulapally to Shankaraopeta | 130.00/  18.12.2021 | 19.09.2022 | 18.12.2023 | 50% | 114.39 | 114.39 | - | - |
| 399 | Construction of High level bridge on Road from Thimmareddyguda to Pamena | 500.00/  21.07.2021 | 08.09.2022 | 07.03.2024 | 25% | 163.10 | 163.10 | 4.99 | - |
| 400 | Double lane to Road from PWD road to Shanthivanam via Kanha of Nandigam Mandal | 2,515.00/  29.10.2021 | 07.02.2022 | 06.02.23 | 50% | 329.31 | 329.31 | 509.33 | - |
| 401 | Widening of R/F PWD road to Bakaram (via)Yenkepally | 220.00/  09.11.2021 | 22.04.2022 | 21.04.23 | 75% | 178.64 | 178.64 | 37.54 | 620.00/  05.10.2023 |
| 402 | BT on R/F PWD Road to Bakaram (Via) Aziznagar SC Colony, Nagireddyguda of Moinabad (M) | 1,300.00/  07.04.2022 | 27.2.23 | 26.08.2024 | 25% | 694.08 | 694.08 | - | - |
| 403 | Dudiyala to nacharam via allikhanpally | 250.00/  09.11.2021 | 23.03.2021 | 22.03.2022 | 10% | 35.16 | 35.16 | - | - |
| 404 | PWD Road Kothur to Lingamdana | 2,000.00/  12.04.2023 | 04.10.2023 | 03.04.2025 | 75% | 1,164.52 | 1,164.52 | - | - |
| 405 | JP Darga to Eklashkhanpet | 600.00/  12.04.2023 | 08.08.2023 | 07.11.2024 | 75% | 398.06 | 398.06 | 110.73 | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 406 | Providing Double lane road from Aliyabad x road to ghanpur via Medcity hospital | 500.00/  09.11.2021 | 11.01.23 | 10.01.24 | 25% | 65.00 | 65.00 | 83.05 | - |
| 407 | Road from NH 44 to SC colony, Dabilpur Village, Medchal Mandal, Medchal-Malkajgiri District | 260.00/  15.02.2022 | 02.06.22 | 01.06.23 | 50% | 82.05 | 82.05 | - | - |
| 408 | Bridge thumkunta to Jalubhavi tanda | 460.00/  30.01.2023 | 23.03.2023 | 22.03.2024 | 75% | 377.58 | 377.58 | 54.70 | - |
| 409 | Providing B.T on road from Gollapally to Revally PR Road (Ashramam Road) of Revally Mandal of  Wanaparthy Dist | 180.00/  11.08.2023 | 06.02.2023 | 05.06.2024 | 75% | 162.00 | 162.00 | - | - |
| 410 | R&B Road to Palugula thanda (Balance work) | 208.25  /04.03.2023 | 09.10.2023 | 08.10.2024 | 10% | 14.44 | 14.44 | - | - |
| 411 | Road from Kadaguttta thanda to Thonda (Balance work) | 155.55/  04.03.2023 | 12.12.23 | 11.12.24 | 10% | 24.17 | 24.17 | - | - |
| 412 | BT to Road from NH Raghavapur to Gidda banda thanda H/o Thatikonda via Ashwaraopally | 400.00/  09.11.2021 | 29.12.22 | 28.12.23 | 75% | 38.34 | 38.34 | - | - |
| 413 | R&B Road to Palugula thanda via sub station, Ramavaram GP | 100.00/  09.11.2021 | 17.10.22 | 15.10.24 | 25% | 14.44 | 14.44 | - | - |
| 414 | BT to R/F PR Road Jeedikal to Ramchandrugudem, Lingalaghanpur(M) | 180.00/  09.11.2021 | 22.7.22 | 21.7.23 | 75% | 63.99 | 63.99 | - | - |
| 415 | BT to R/f Jittegudem to Mallanagandi(Via) Narayanaloddi thanda at Jittagudem(V) | 120.00/  09.11.2021 | 30.7.22 | 30.6.24 | 50% | 60.00 | 60.00 | - | - |
| 416 | Road from Kadaguttta thanda to Thonda (Thirumalagiri Mandal) | 100.00/  09.11.2021 | 17.10.22 | 16.10.23 | 50% | 24.17 | 24.17 | - | - |
| 417 | Road from ZP Road (Mutharam) to Patimeedi thanda | 280.00/  09.11.2021 | 19.10.22 | 18.4.24 | 25% | 101.24 | 101.24 | - | - |
| 418 | BT R/F Ramalayam temple 0/0 to 0/820 in valmidi village | 265.00/  09.11.2021 | 5.9.22 | 4..9.23 | 75% | 145.60 | 145.60 | - | - |
| 419 | Sri Someshwara laxmi narshimha swamy temple to pradhkshana road 0/645 to 1/400 KM | 400.00/  09.11.2021 | 5.9.22 | 4..9.23 | 75% | 160.08 | 160.08 | - | - |
| 420 | Road from Ravulagadda Cross to Market Yard at Palakurthy | 140.00/  09.11.2021 | 5.7.23 | 4.7.24 | 25% | 73.41 | 73.41 | 26.32 | - |
| 421 | BT to Road From R & B road Pulukurthy to Ramakrishnapur via Chennakeshavulagutta in Damera (M) | 350.00/  09.11.2021 | 01.6.22 | 31.5.23 | 50% | 21.36 | 21.36 | 108.07 | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 422 | Kondur to Ramaram | 180.00/  09.11.2021 | 30.09.2023 | 30.9.24 | 75% | 120.00 | 120.00 | - | - |
| 423 | Rayaparthi to perekede road, rayaparthi village limits | 300.00/  09.11.2021 | 30.09.2023 | 30.9.24 | 75% | 90.00 | 90.00 | - | - |
| 424 | BT to R/F Chennaram to Panthini | 210.00/  09.11.2021 | 15.11.2022 | 14.11.2023 | 50% | 152.95 | 152.95 | - | - |
| 425 | Nuthankal to bikumalla via lingampally machanpally road widening 0/0 to 5/0 KM | 300.00/  09.11.2021 | 01.06.2023 | 31.05.2024 | 50% | 180.64 | 180.64 | - | - |
| 426 | Budidampuda to vankudoth thanda | 300.00/  11.08.2023 | 07.10.2023 | 06.10.2024 | 50% | 37.18 | 37.18 | - | - |
| 427 | Pangidi to Korra thanda | 250.00/  11.08.2023 | 07.10.2023 | 06.10.2024 | 50% | 64.75 | 64.75 | - | - |
| 428 | Gangaram to Satyanarayanapuram | 200.00/  09.11.2021 | 04.06.2022 | 03.06.2023 | 50% | 111.24 | 111.24 | - | - |
| 429 | BT 0n R/F PWD Road To Narayanapuram Hospitat | 110.00/  04.03.2023 | 18.08.2023 | 17.08.2024 | 50% | 32.67 | 32.67 | - | - |
| 430 | R/F PR road to Kasna thanda | 100.00/  09.11.2021 | 14.7.22 | 13.7.23 | 25% | 88.54 | 88.54 | - | - |
| 431 | Baddipadaga to Jyothjiram thanda via husnabad R & B road | 120.00/  09.11.2021 | 07.07.2022 | 06.04.2023 | 25% | 23.44 | 23.44 | 95.97 | - |
| 432 | Kistapur to repaka (Mankonduru constituency) | 240.00/  09.11.2021 | 07.07.2022 | 20.04.2023 | 75% | 136.47 | 136.47 | 55.00 | - |
| 433 | BT on R/F Akkenapally to Siddannapet of Nangnoor mandal | 440.00/  07.01.2023 | 04.12.2023 | 03.12.2024 | 25% | 67.35 | 67.35 | - | - |
| 434 | T01-Road from Rajiv Rahadari at Nancharpally stage to Thornal via Nancharpally, Bakrichepyala, Velkatur, Konaipally, Narmetta, Nangnoor, Ghanpur and  Kondamrajpally | 2,334.50/  23.06.2020 | 2021 | 2023 | 70% | 882.49 | 1,016.40 | 42.38 | - |
| 435 | T01-Road from Adilabad to Indervelly via Ankoli,Wanwat,Pippaldhari, Khandala,Chichdhari and Bursanpatar | 1,581.50/  08.04.2021 | 2021 | 2023 | 0% | - | - | - | - |
| 436 | MRL01-PWD Road Gudur to Dharmapuram via Erravenu, Shathapur, Madhapuram | 1,497.21/  23.06.2020 | 2021 | 2023 | 0% | - | - | - | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 437 | T01-Road from Rajiv Rahadari at Gandhigram to Gudikandula via Ponnala, Kistasagar, Ensanpally, Venkatapur and Bussapur | 14,16.00/  08.04.2021 | 2020 | 2022 | 25% | - | - | - | - |
| 438 | T03-Konaigudem to Nachepalli via Aregudem, Guvvalagudem, Mujjugudem, Anasagaram | 1,303.50/  08.04.2021 | 2021 | 2023 | 100% | 87.00 | 158.00 | 244.22 | - |
| 439 | T07-Hyderabad to Bangalore NH7 to Veerannapally | 1,061.50  /08.04.2021 | 2020 | 2023 | 100% |  | 331.07 | 35.82 | - |
| 440 | MRL06-Erravenu to Kanchanpally of Raghunathpally Mandal via Kothulabad, Gabbeta | 1,043.09/  23.06.2020 | 2021 | 2023 | 80% | - | - | - | - |
| 441 | C/o HLB at Km 1/3 on R/F Sakinaveedu to Buchireddypalem of Yerrupalem Mandal | 1,030.00/  08.04.2021 | 2018 | 2019 | 0% | - | - | - | - |
| 442 | Construction of LSB at KM 1/850 on R/f T01-R/f Sirikonda to Indervelly via Dasnapur, Pittabongaram | 1,016.00/  08.04.2021 | 2018 | 2019 | 30% | - | 49.50 | - | - |
| 443 | MRL14-Road From Thangallapally to Ellanthakunta via Laxmipur,Veljipur,Ernasupally and Rahimkhanpet | 984.00/  08.04.2021 | 2018 | 2019 | 45% | - | 62.00 | - | - |
| 444 | PWD Road Devaruppula to Visnur via Kothagudishelu, Dharmapuram, Mylaram | 972.13/  23.06.2020 | 2018 | 2019 | 0% | - | - | - | - |
| 445 | Mategaon to Limba B via Ekagaon Bijjur Kothalgaon Chinthalbori of Bhinsa mdl | 966.73/  23.06.2020 | 2018 | 2020 | 10% | - | 59.85 | - | - |
| 446 | T01-Salampad Camp to Sunkini Vias. Kumanpally, Khajapur, Humsa, Mandarna, Sunkini | 948.74/  23.06.2020 | 2018 | 2019 | 80% | - | - | - | - |
| 447 | MRL03-R and B road wardhannapet to burahanpally via thirumalayapalli kondur | 948.00/  08.04.2021 | 2018 | 2020 | 40% | - | 190.01 | - | - |
| 448 | T01-Road from RB road at Ramancha to Rajiv Rahadari at Mandapally stage via Chandlapur and Chinnakodur | 924.31/  23.06.2020 | 2021 | 2023 | 60% | 219.58 | 271.29 | 115.30 | - |
| 449 | R/f Settipally to Lingapuram in Gundala Mandal | 910.00/  10.01.2018 | 2021 | 2023 | 90% | - | - | - | - |
| 450 | MRL12-kataram to vilasagar via gummalapaly | 905.50/  08.04.2021 | 2021 | 2023 | 100% | 50.62 | 50.62 | - | - |
| 451 | T01-Chowtapalli to Jupeda via rajaram and Painampalli | 905.00/  08.04.2021 | 2021 | 2023 | 100% | 66.43 | 66.43 | - | - |
| 452 | Bridge on R/f Bhupathipur X RRoad to Ramaraopally via Mootapally and Itikyal | 900.00/  08.04.2021 | 2018 | 2019 | 0% | - | - | - | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 453 | MRL10-RB Road near Polokonda thanda to Dharmapuram PR Road via Palugulathanda, Laxmakkapally | 893.00/  08.04.2021 | 2020 | 2022 | 0% | - | 280.80 | 57.70 | - |
| 454 | R/f MH Border at Kharag to R&B road at Madnoor via Chinna Thadgur Pedha Thadgur Kodichera and  Awalgaon of Madnoor Mdl | 882.53/  23.06.2020 | 2020 | 2022 | 30% | - | 285.71 | - | - |
| 455 | R/f TO1- Palachttu Mandamarri to Awadam via Mamidigattu of Mandamarri (M) | 845.00/  08.04.2021 | 2018 | 2022 | 100% | 232.10 | 552.51 | 82.10 | - |
| 456 | C/o Bridge at 8/800 on R/f Laxmipur to Baddampally | 824.00/  04.03.2018 | 2021 | 2023 | 100% |  | 158.46 | 98.63 | - |
| 457 | T01-Mutyalampadu X road to Station Thadikalapudi | 807.29/  23.06.2020 | 2022 | 2023 | 100% | 276.91 | 276.91 | 505.56 | - |
| 458 | T01-Authapur to Kodakandla via Gantla Kunta and Rangapur | 807.00/  08.04.2021 | 2020 | 2023 | 100% | 277.98 | 435.72 | 58.14 | 495.19/  12.01.2023 |
| 459 | T05-R and B Road Dandupeta to R and B Road C Kathigudem | 781.65/  23.06.2020 | 2021 | 2023 | 100% | 122.89 | 122.89 | 141.23 | - |
| 460 | MRL09-SH7 to Dharmasagar Via Ananthsagar Madipalle | 761.00/  08.04.2021 | 2021 | 2023 | 100% | 176.33 | 176.33 | 163.04 | - |
| 461 | MRL11-RB Road near Pakhala to RB Road near Chennur via Pakhala, Manchuppula | 756.30/  08.04.2021 | 2021 | 2023 | 95% | 107.11 | 239.61 | - | - |
| 462 | Construction of High level bridge on road from Gambhiraopet to Mallareddypet of Gambhiraopet(M) | 750.00  /08.04.2021 | 2021 | 2023 | 95% | 482.19 | 482.19 | - | - |
| 463 | L028-Laxmipur to Baddampally | 707.50/  04.03.2018 | 2021 | 2023 | 95% | 93.77 | 93.77 | 80.83 | - |
| 464 | T02-Namapur to Bundanakal R and B Road via Chekodu Maddikunta Mohinikunta | 700.40/  08.04.2021 | 2021 | 2023 | 75% | - | - | - | - |
| 465 | MRL10-Tunkibollaram to Yadaram via Achaipally, Dasarlapally | 687.00/  08.04.2021 | 2020 | 2022 | 50% | - | 159.99 | - | - |
| 466 | T02-NH road (Eturnagaram) to Kamalapur (Via) Ramnaga | 676.00/  08.04.2021 | 2020 | 2022 | 100% | 414.90 | 608.84 | - | - |
| 467 | T01-PWD road - Chinchalpet - Aknapur - Nareguda | 675.00/  08.04.2021 | 2021 | 2023 | 10% | - | - | - | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 468 | T01-Karjevelly to Motlaguda | 667.60/  16.03.2013 | 2021 | 2023 | 90% | - | - | - | 609/ 27.07.2023 |
| 469 | T02-Muthnur to Pakkernaiktanda | 659.50/  03.04.2018 | 2021 | 2023 | 10% | - | - | - | - |
| 470 | T03-Maheshwaram RnB Road to Konapuram via Gurijala, Lingapur | 659.00/  08.04.2021 | 2021 | 2023 | 90% | - | - | 38.53 | - |
| 471 | T01- R and B Road to Dharmapuram via pubelly,sudimalla | 648.50/  23.06.2020 | 2021 | 2023 | 20% | - | - | - | - |
| 472 | Bandalingapur X Road to Athmakur via Jaggasagar, Ramalachakkapet, Athmanagar | 642.30/  08.04.2021 | 2021 | 2023 | 100% | - | - | 186.40 | - |
| 473 | C/o HLB on across Edula Vagu @7750 mts on R/f Rudrampur to Upparigudem of Kothagudem Mdl | 641.00/  15.02.2014 | 2021 | 2023 | 50% | - | - | 69.36 | - |
| 474 | MRL04-Mogaddhagad PR (BT) Road to Karjepally R and B Road via Veeravelly, Lonavelly | 638.80/  08.04.2021 | 2021 | 2023 | 95% | 132.41 | 132.41 | 33.54 | - |
| 475 | T01-Bakthimalla PWD Road to Musrifa via Hanumanpally, BIjjaram | 636.70/  08.04.2021 | 2021 | 2023 | 10% | - | - | - | - |
| 476 | T05-Sujathanagar to Ramavaram(chunchupally Mandal) via Nemaligudem,Gareebpeta. | 635.99/  08.04.2021 | 2021 | 2023 | 95% | 87.85 | 87.85 | - | - |
| 477 | MRL12-PWD Road to Maripeda via Mallagani thanda and Veeraram | 632.50/  08.04.2021 | 2021 | 2023 | 70% | 117.89 | 117.89 | - | - |
| 478 | Const.of HLB on Shameerpet vagu on R/f Jagadevpur PWD road to Cheekatimamidi ZP road at 2/100 | 630.00/  08.04.2021 | 2021 | 2023 | 100% | 308.83 | 308.83 | 176.69 | - |
| 479 | L041-Karji to motlaguda via rampur | 625.00/  03.04.2018 | 2021 | 2023 | 60% | - | - | 40.47 | - |
| 480 | MRL01-Penpahad to Anantharam to Dosapahad to Dubbagudem | 623.47/  23.06.2020 | 2021 | 2023 | 80% | 161.33 | 221.33 | - | - |
| 481 | Construction of HBL on Chinneru on R/f Shivareddygudem to Reddy nagar | 622.00/  08.04.2021 | 2021 | 2023 | 10% | - | - | - | - |
| 482 | Construction of High level bridge at 2/93 Km on road from Karasguthi PWD Road to Karnataka Boarder v | 620.00/  08.04.2021 | 2021 | 2023 | 80% | - | - | - | - |
| 483 | HLB Bridge on R/F Sujathanagar to ramavaram | 612.00/  08.04.2021 | 2020 | 2023 | 100% | - | 889.12 | 277.90 | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 484 | MRL01-Road From NH Road to Pragathi Singaram via Shayampet and Pathipaka | 609.00/  08.04.2021 | 2021 | 2023 | 100% | 177.52 | 177.52 | 53.89 | - |
| 485 | T01-Dasturabad to Gondguda G via Bhutkur,Munyal, Godserial, | 602.92/  23.06.2020 | 2020 | 2023 | 100% | - | 271.43 | 85.99 | - |
| 486 | MRL04-Rejerla to Thallamada via Siddaram,Narayanapuram | 601.00/  08.04.2021 | 2021 | 2023 | 100% | - | 197.35 | 93.92 | - |
| 487 | HLB on Road from MRL11-Kothur road to toward Lyabarthy cross and rollakal kalleda | 596.47/  08.04.2021 | 2021 | 2023 | 100% | 22.02 | 22.02 | 229.45 | - |
| 488 | T01-Karjevelly to Motlaguda | 593.00/  03.04.2018 | 2021 | 2023 | 100% | 152.11 | 405.83 | - | - |
| 489 | MRL02-PWD Road Mediguda to Maregoan via Kothapally G Kunikasa, ParaswadaB | 584.62/  23.06.2020 | 2020 | 2022 | 100% | - | 1,170.44 | - | 1,755.00/  12.01.2023 |
| 490 | T02-Narsapur G to Gollamada via Anjani, Timmapur | 574.08/  23.06.2020 | 2020 | 2022 | 85% | 246.83 | 859.08 | 56.51 | 1,360.00/  22.11.2022 |
| 491 | T02-Avuravani to NH-65 (via) Kondapakonigudem, Shankar nagar,Yenuguladori, Goplaipally | 572.18/  23.06.2020 | 2021 | 2023 | 100% | 168.67 | 389.10 | 99.77 | - |
| 492 | R/f Velganoor to Kothakommuguda via Rebbanpalli, Muthuyampet and Korvichelma in Dandepally (M) | 563.40/  08.04.2021 | 2021 | 2023 | 100% | - | - | - | - |
| 493 | T01-Gambhiraopet PR Road to Chukkapur Machareddy PWD Road via Brahmanpally Thanda, Ghanpoor(M), Dharni Thanda, Cheruvu Kommu Thanda, Lacchapet,  Banda Rameshwerpally | 561.50/  08.04.2021 | 2021 | 2023 | 70% | - | - | 799.89 | - |
| 494 | T02-Pwd Road to Nagaram via Annaram ,Nagaram and Kazaahmedpally | 557.97/  23.06.2020 | 2021 | 2023 | 7% | 42.46 | 42.46 | 201.68 | - |
| 495 | MRL01-RF Kalvapally Cart Bridge to Gudur (Narketpally-Addanki Highway) Via Avanthipuram | 534.84/  23.06.2020 | 2021 | 2023 | 70% | 110.02 | 110.02 | - | - |
| 496 | HLB at 6.94km on RF Kondareddypally to Lemamidi via kaknoor | 533.00/  08.04.2021 | 2021 | 2023 | 10% | - | - | - | - |
| 497 | MRL16-B.Vellemla to Mogilidori (via) Elikatte, Vembai | 530.60/  23.06.2020 | 2021 | 2023 | 15% | - | - | - | - |
| 498 | HLB on Chennaigudem to Ganganapalem via Kashivarigudem Rajupeta Yeragantlagudem | 530.00/  30.09.2021 | 2020 | 2022 | 95% | - | 120.97 | - | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 499 | MRL02-Mallapoor to Challagarga via  Lolam ,Govindpally,Belia Thanda,Dhammannapet | 529.28/  23.06.2020 | 2020 | 2022 | 100% | - | 62.41 | - | - |
| 500 | R/f PWD Road at Jaklair to PWD Road at Bhoothpur via Rama samudram, Samanpally Manthangode Yeranaganpally, Katrevpally & Bhoothpur in Makthal  mdl | 523.54/  23.06.2020 | 2020 | 2022 | 100% | 67.12 | 263.80 | - | - |
| 501 | MRL10-Chennaigudem to Ganganapalem via Kashivarigudem Rajupeta Yeragantlagudem | 518.00/  30.09.2021 | 2021 | 2023 | 90% | - | - | 48.03 | - |
| 502 | T01-NH44 to Nacharam | 517.00/  08.04.2021 | 2021 | 2023 | 40% | 108.45 | 108.45 | - | - |
| 503 | MRL07-Lokeshwaram to Pendapelli-Wattoli X road Via Malkapur, Sathgoan | 516.46/  23.06.2020 | 2021 | 2023 | 70% | - | - | - | - |
| 504 | MRL02-PWD Road Chennapur to Rajakkapalli | 516.20/  08.04.2021 | 2020 | 2023 | 100% | 103.47 | 414.50 | 28.21 | - |
| 505 | MRL15-MBNR NLG PWD road at 135km 400mt to Sulthanpuram via Tenepally thanda , Yellamonigudem | 511.30/  30.09.2021 | 2020 | 2023 | 100% | 71.27 | 352.11 | 34.39 | - |
| 506 | R/f Shivaramireddypally ZP Road to Naskal upto District Border via Bibipet, Tujalpur of Bibipet mdl | 511.19/  23.06.2020 | 2020 | 2024 | 100% | - | 165.45 | - | - |
| 507 | MRL01-Javaharnagar to Thumkunta Via Malkaram | 511.19/  23.06.2020 | 2020 | 2022 | 30% | 43.09 | 138.90 | 126.88 | 451.6/  11.01.2023 |
| 508 | MRL03-Singitham to Moratga via Raipally c karchal | 508.53/  23.06.2020 | 2021 | 2023 | 90% | 125.62 | 125.62 | 76.44 | - |
| 509 | MRL09-Guniparthy to Cherlapally via Madannapet Shanigaram bathivanipally | 501.00/  08.04.2021 | 2020 | 2023 | 100% | 50.85 | 213.39 | 12.26 | - |
| 510 | T01-R and B road Dharmaram to Puligilla via Nadikuda | 497.00/  08.04.2021 | 2021 | 2023 | 40% | 94.63 | 94.63 | 166.97 | - |
| 511 | MRL01-Kapulakanaparthy PWD Road to Sangem via Katrapalli and Kuntapalli | 497.00/  08.04.2021 | 2021 | 2023 | 90% | - | 94.67 | 345.47 | - |
| 512 | C/o HFL Bridge at Ch 2/400 to 2/600 km on R/f PWD road to Kishannaik thanda of Jaoinoor mdl | 495.00/  30.01.2019 | 2020 | 2023 | 100% | 243.27 | 583.15 | 243.28 | - |
| 513 | Japal to Mukunoor via Manchal Lingampally Thallapally of Manchal Mdl | 494.23/  23.06.2020 | 2021 | 2023 | 100% | 38.12 | 78.01 | 47.77 | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 514 | MRL03-Repaka to Parkal (up tp mandal boundary)via Kanaparthy | 490.10/  08.04.2021 | 2021 | 2023 | 100% | - | 83.67 | - | - |
| 515 | MRL08-Sakinaveedu to Buchireddypalem via Rajuladevarapadu | 489.60/  08.04.2021 | 2020 | 2023 | 100% | - | 198.31 | 132.67 | - |
| 516 | C/o HLB at 1/500 km on R/f R&B Road to Subrampally to Dugnepally via Narayanapur in Chennur mdl | 480.00/  08.04.2021 | 2021 | 2023 | 90% | - | 116.45 | 122.63 | - |
| 517 | MRL10-Mailaram PWD Road to Wargal Gajwel PWD Road via Guntipally , Sheripally | 472.00/  08.04.2021 | 2021 | 2023 | 10% | - | - | 4.99 | - |
| 518 | MRL36-APPAREDDIPALLY TO AMUDAMBANDA THANDA VIA PARVATHAPUR | 470.50/  08.04.2021 | 2021 | 2023 | 10% | - | - | 42.43 | - |
| 519 | MRL18-Parvathagiri to mecharajpally upto mandal limits  Via kalleda,Burgumadla | 470.00/  08.04.2021 | 2021 | 2023 | 10% | - | - | 33.72 | - |
| 520 | MRL01-Upparapally thanda to Jillela thanda via  Venkatagiri,Katrapally, Bhavanigadda thanda,Shiva  shankar nagar | 463.00/  08.04.2021 | 2021 | 2023 | 10% | - | - | 14.46 | - |
| 521 | MRL07-NH44 at Pothulamadugu to Ghanpur R B Road via Kappeta and PathaKappeta | 459.70/  08.04.2021 | 2021 | 2023 | 10% | - | - | 65.85 | - |
| 522 | MRL12-PWD Road to PWD Road Mahabubabad via Polepally, Chandru Thanda, Somarapu Kunta Thanda and Chowlla Thanda | 456.00/  08.04.2021 | 2021 | 2023 | 95% | 78.43 | 78.43 | - | - |
| 523 | MRL02-Road from Kamaram to Laxmipur via Penchikalpet and Keshavapuram | 456.00/  08.04.2021 | 2021 | 2023 | 90% | 64.70 | 193.17 | - | - |
| 524 | C/o LSB on R/f NH 44 Echoda to NH 44 Raghuguda via Girijam and Mukhra of Echoda Mdl | 455.11/  08.04.2021 | 2021 | 2023 | 60% | - | - | 123.68 | - |
| 525 | MRL06-Nagaram to Kundaram Via.Nawabpet, Lingalaghanpur | 454.99/  08.04.2021 | 2021 | 2023 | 60% | - | - | 100.43 | - |
| 526 | MRL11-PWD Road at Somaram to PWD Road Mahabubabad at Madipally Bus Stop via Gurthur, Kantaipalem and Madipally | 453.00/  08.04.2021 | 2021 | 2023 | 80% | - | 36.31 | - | - |
| 527 | MRL08-Bayyannagudem to Agraharam via Nayakulagudem | 452.70/  08.04.2021 | 2021 | 2023 | 10% | - | - | - | - |
| 528 | MRL01-Road from NH9 road at Isnapur X road to PWD road at Indresham via Chitkul Bachuguda | 450.63/  23.06.2020 | 2021 | 2022 | 75% | - | 209.04 | - | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 529 | MRL03-Khammam -Yellandu R and B Road to Manchukonda -Pangidi ZP Road via., Kothacolony, Zinkalathanda, Mallepalli, Ramuluthanda and Bavoji Thanda | 450.40/  08.04.2021 | 2021 | 2022 | 90% | 208.16 | 283.16 | - | 417/ 10.01.2023 |
| 530 | MRL06-Keethavarigudem Kokkireni R and B Road at Rangapuram to Sarvaram Via Kothagudem, Kothur, Keethavarigudem Funchtionhall | 449.27/  23.06.2020 | 2021 | 2023 | 100% | - | 243.54 | 65.24 | - |
| 531 | MRL06-Rf Raikode to Ragavapur Road via Nagwar itikepally kanjamalpur | 448.76/  23.06.2020 | 2021 | 2022 | 100% | - | 231.55 | 68.73 | - |
| 532 | MRL16-Ganugubanda-Thurpugudem road to Bandaram- Suryanaik thanda via Vempaty, Ramannagudemthanda | 447.00/  08.04.2021 | 2021 | 2023 | 90% | 190.79 | 775.30 | - | 1,181.00/  08.08.2023 |
| 533 | MRL11-Kothur road to toward Lyabarthy cross and rollakal kalleda | 447.00/  08.04.2021 | 2021 | 2022 | 90% | 975.37 | 975.37 | - | - |
| 534 | MRL10-R F T03 Manakondur to Vegurupally Road to Banjarpally Via Sadashivpally | 445.50/  08.04.2021 | 2021 | 2023 | 100% | - | 417.48 | - | - |
| 535 | T04-Mallapur to R and B Road Jaggaraopally via Kothapeta Venkatraopally Jaggaraopally | 444.00/  08.04.2021 | 2021 | 2022 | 90% | 229.98 | 315.46 | - | 435.00/  10.08.2023 |
| 536 | L039-Kuntala K to Mathurathanda | 443.32/  03.04.2018 | 2021 | 2022 | 90% | - | 288.05 | - | 535.00/  10.09.2023 |
| 537 | MRL03-Hegdoli to pentakhurd camp via Yadgarpur Ethonda | 443.10/  23.06.2020 | 2021 | 2022 | 90% | 91.03 | 290.40 | - | 367.00/  10.08.2023 |
| 538 | R/f Nandipet PWD road to Mamdapur via Godwal Gangaram manda Rampoor, Venkatapur of Makloor mandal | 438.60/  23.06.2020 | 2021 | 2022 | 90% | - | 190.30 | - | 460.00/  10.09.2023 |
| 539 | MRL13-Kangti PWD Road to Potpally Thanda via Kishan Naik Thanda, Hemla Thanda, Potpally and Naganpally | 437.00/  08.04.2021 | 2021 | 2022 | 65% | 312.44 | 312.44 | 140.91 | - |
| 540 | R/f Ramanjavaram to Pagideru via Golla Kothuru Colony in Manguguru Mandal | 436.84/  23.06.2020 | 2021 | 2023 | 90% | - | - | 147.35 | - |
| 541 | R/f Uppunuthala to Raiched via Tadoor, Chennaram in Uppunuthala mdl | 431.50/  23.06.2020 | 2021 | 2022 | 60% | 98.78 | 98.78 | - | - |
| 542 | MRL15-Road from Thandur PWD Road to Ontelagadda T via Arjun NaikT Anegunta | 431.00/  08.04.2021 | 2021 | 2023 | 0% | - | - | - | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 543 | MRL15-Road from Thandur PWD Road to Ontelagadda T via Arjun NaikT Anegunta | 431.00/  08.04.2021 | 2021 | 2022 | 90% | - | 394.62 | - | - |
| 544 | MRL16-NH65 - Mothey R and B road at Vijayaraghavapuram to Nadigudem to Ravipahad R and B road at Keshavapuram via Kalakova, Jagannadhapuram | 424.00/  08.04.2021 | 2017 | 2019 | 0% | - | - | - | - |
| 545 | T01-Road from Approach road Sikindrapur to Muchkur via Gongoppula | 420.70/  08.04.2021 | 2017 | 2019 | 0% | - | - | - | - |
| 546 | HLB Bridge on BT R/F Mutyalampadu X Road to Station Thadikalapudi at 2/5 | 420.00/  08.04.2021 | 2017 | 2019 | 0% | - | - | - | - |
| 547 | T01-Mirzapally Narsingi to Narsampaly via pedda thanda and Shalipet Rlwy trac | 415.00/  23.06.2020 | 2018 | 2022 | 67% | 42.79 | 185.17 | - | - |
| 548 | construction of bridge across pedda vagu on Road from NH 765 to Ganugattu Thanda at 5/4 to 5/6 | 415.00/  08.04.2021 | 2018 | 2022 | 29% | - | - | 151.19 | - |
| 549 | T01-Jhally to Papaiahpet via Yellaigudem | 412.00/  08.04.2021 | 2013 | 2015 | 0% | - | 439.13 | - | - |
| 550 | MRL02-Anthwar to doulthabad via gundepally and allapur | 410.96/  23.06.2020 | 2018 | 2022 | 0% | - | - | - | - |
| 551 | C/o of HLB on R/F Gambhiraopet PR Road to Chukkapur Machareddy PWD Road via lachapet | 405.00/  08.04.2021 | 2012 | 2014 | 5% | - | 5.68 | - | - |
| 552 | L029-ZP Road to Doddiguda | 402.63/  16.03.2013 | 2020 | 2022 | 75% | - | 134.79 | - | - |
| 553 | T01-Pittalagudem to Kindaram Via.Banjipet | 401.20/  08.04.2021 | 2018 | 2020 | 60% | - | 248.87 | - | - |
| 554 | R/f Jakinalapally to Bomarasipally of Urakonda mdl | 400.50/  23.06.2020 | 2018 | 2020 | 17% | - | 198.61 | - | - |
| 555 | Bridge on R/f NH63 Kalleda to Laxmipur via Gutrajpally | 400.00/  08.04.2021 | 2020 | 2022 | 100% | - | - | 213.98 | - |
| 556 | Cnst.of HLB at 1.350KM on R/f Namathpally - Bollepally | 400.00/  08.04.2021 | 2020 | 2023 | 100% | 186.25 | 187.73 | 155.78 | - |
| 557 | MRL16-Hanwada to Gudimalkapur via Tankara | 397.30/  08.04.2021 | 2018 | 2019 | 0% | - | - | - | - |
| 558 | T01-Chinnarathpally to Mirjampeta Via Tharupally Malliala kothapally | 397.20/  08.04.2021 | 2021 | 2023 | 75% | 97.33 | 97.33 | - | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 559 | Construction of HLB at km 11/200 on R/F Authapur to Kodakandla via Gantlakunt and Rangapur | 395.00/  08.04.2021 | 2010 | 2018 | 5% | - | 19.75 | - | - |
| 560 | MRL08-Israjpally to Gunjapadugu via Govinpally | 394.00/  08.04.2021 | 2018 | 2020 | 90 | - | 112.68 | - | - |
| 561 | MRL01-NH 44 to Rand B road via Amadabakula Boothpur and Pullareddykunta | 392.49/  23.06.2020 | 2021 | 2023 | 100% | 22.21 | 22.21 | - | - |
| 562 | C/o High Level Bridge on R./F PWD Road Madhapur to Katlakunta via Chinnametpally in Korutla (M) | 390.00/  08.04.2021 | 2021 | 2023 | 100% | 29.25 | 29.25 | - | - |
| 563 | Construction of 7V 20m span Bridge at 3/8 Km on R/f Ervachintal to Dattojipet | 385.83/  16.03.2013 | 2018 | 2022 | 0% | - | - | - | - |
| 564 | R/f Tupadal to Bichkunda via Pedda Thakkadpally of Bichkunda mdl | 385.06/  23.06.2020 | 2021 | 2023 | 30% | - | - | - | - |
| 565 | MRL16-Chilkur-Bethole pwd road at 5 km 400 m to NH 65 via Kondapuram, Madhavagudem, Mukundapuram | 385.00/  08.04.2021 | 2018 | 2022 | 60% | - | 91.52 | - | - |
| 566 | T05-Nawabpet to Gangapur | 383.89/  16.03.2013 | 2013 | 2022 | 0% | - | - | - | - |
| 567 | MRL05-Ibrahimpatnam to Nadikuda via Yamapur, Fakirkondapur | 383.40/  08.04.2021 | 2013 | 2022 | 0% | - | - | - | - |
| 568 | Bridge across Yedderu vagu on R/F NH44 to Palmakula via Nanajipur Makthaguda at Km 5/0 shamshabad(m) | 382.00/  08.04.2021 | 2021 | 2023 | 90% | - | 275.80 | - | - |
| 569 | MRL09-Medak PWD Road to Balvanthapur via Dumpalapally | 381.00/  08.04.2021 | 2021 | 2023 | 50% | 3.54 | 3.54 | - | - |
| 570 | C/o HLB on R/F R B Road(jam) to Beeravelly at Km 6/485 | 380.00/  08.04.2021 | 2021 | 2023 | 95% | 100.40 | 100.40 | 49.03 | - |
| 571 | R/f ZP Road Lokurthy to Mustaipet via Gattireddypally and Chakalonipally in Damaragidda Mdl | 377.30/  23.06.2020 | 2021 | 2023 | 95% | 136.42 | 136.42 | - | - |
| 572 | C/O HLB on R/F Ratan Naik T to Polkampet PWD road via Sajjanapally Ekkapally at 6/45in Lingampet (M) | 375.00/  08.04.2021 | 2021 | 2023 | 75% | 63.07 | 63.07 | - | - |
| 573 | Construction of HLB at km 4/220 on R/F Upparpally thanda to Jillela thanda via Venkatagiri Katrapall | 375.00/  08.04.2021 | 2021 | 2023 | 100% | 118.92 | 118.92 | 44.18 | - |
| 574 | C/O HIGH LEVEL BRIDGE AT KM 1/00ON R/F R&B ROAD AT 5.50KM TO DEVAPUR ROAD VIA  REGULAGUDA,GURVAPUR IN | 375.00/  08.04.2021 | 2020 | 2023 | 100% | 138.56 | 299.44 | 37.00 | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 575 | MRL03-Choutapally to Chinthanekkonda | 375.00/  08.04.2021 | 2021 | 2022 | 80% | 0.67 | 73.33 | 313.85 | - |
| 576 | MRL02-Gundareddypally to Baswapur via Muthannapet | 374.00/  08.04.2021 | 2021 | 2023 | 80% | 121.04 | 121.04 | - | - |
| 577 | MRL01-Road from Bejjanki to Regulapally via Cheelapurpally, Cheelapur and Kothapally | 373.00/  08.04.2021 | 2021 | 2023 | 75% | - | - | - | - |
| 578 | R/f Achampet PWD road to Ambagiri via Mylaram Kondanagula (v) of Balmoor Mdl | 372.00/  08.04.2021 | 2021 | 2023 | 0% | - | - | - | - |
| 579 | MRL06-Surepalli to Angadipet (via) Chilkamarri , Neelamnagar | 372.00/  30.09.2021 | 2021 | 2023 | 90% | 22.82 | 522.82 | 69.56 | - |
| 580 | MRL01-PWD Road Gandeed to Balsurgonda R B Road via Reddypally mansorpally kondapur | 371.60/  08.04.2021 | 2021 | 2023 | 90% | - | 45.24 | 145.17 | - |
| 581 | L035-R and B Road to Chinnagudipet Via Parvathipet | 371.50/  03.04.2018 | 2021 | 2023 | 0% | - | - | - | - |
| 582 | C/o R/f NH 44 Echoda to NH 44 Raghuguda via Girijam & Mukkara of Echoda mdl | 370.78/  23.06.2020 | 2012 | 2019 | 90% | - | 204.85 | - | - |
| 583 | MRL04-Road from Uppermallial Fields to Vedira | 370.30/  08.04.2021 | 2021 | 2023 | 100% | 237.71 | 337.71 | - | - |
| 584 | MRL10-Ragatlapally RandB Road to Shivangalapally via Dumala Akkapallay | 368.30/  08.04.2021 | 2021 | 2023 | 71% | 200.00 | 299.68 | 81.76 | - |
| 585 | MRL01-R B Road(Jam) to Beeravelly via Godisera | 368.03/  23.06.2020 | 2017 | 2019 | 75% | - | 390.75 | - | - |
| 586 | MRL10-AMRABAD PWD ROAD TO MYDAMBANDA BUSTAND VIA MUTHARAM, PARUPALLY,POTHARAM | 367.49/  08.04.2021 | 2021 | 2023 | 100% | 63.02 | 133.67 | 8.23 | 249.31/  08.10.2023 |
| 587 | L023-R B Road to Thippapuram | 366.00/  16.11.2017 | 2021 | 2023 | 75% | - | - | - | - |
| 588 | MRL09-Darveshpuram to Sagar PWD Road via Cherlagouraram Kummarigudem Telakantigudem | 365.99/  30.09.2021 | 2021 | 2023 | 40% | - | - | - | - |
| 589 | C/o HLB on R/f Mulkalapally to Mogaralaguppa via Modivarre at 1/km of Mulkalapally mdl | 365.00/  08.04.2021 | 2021 | 2023 | 20% | - | - | 53.56 | - |
| 590 | MRL17-NH44 to Narkhoda via Peddashapur, Chowderguda and Narkhoda | 365.00/  08.04.2021 | 2021 | 2023 | 80% | 523.18 | 951.40 | - | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 591 | R/f NH 765 to Gangatu Thanda, Veldanda (M) | 364.23/  23.06.2020 | 2021 | 2023 | 0% | - | - | - | - |
| 592 | MRL11-Chinthagurthy to Suryathanda via Korlabodu thanda,Ramkya thanda,vankudoth thanda | 362.30/  08.04.2021 | 2021 | 2023 | 0% | - | - | - | - |
| 593 | T10-Bhupathipoor x road to Ramaraopally via Mootapally and Itikyal | 361.50/  08.04.2021 | 2021 | 2023 | 90% | - | 137.34 | - | - |
| 594 | R/f PWD Road Chowdaram to PWD road Hanumanthapur via Marigadi Teddyathanda  Yerrgollapahad and Dodlagadda thanda of Janagaon | 359.03/  23.06.2020 | 2021 | 2023 | 90% | - | 132.26 | 115.43 | - |
| 595 | ML01-Cheruvumundu thanda to Doravarivempally | 356.50/  16.11.2017 | 2021 | 2023 | 60% | 182.55 | 182.55 | 76.97 | - |
| 596 | Construction of Bridge on Kandukur Vagu on R/f Masaipet ZP road to Peddakandukur at 5/500 | 355.00/  08.04.2021 | 2021 | 2023 | 70% | 100.00 | 100.00 | - | - |
| 597 | MRL06-Cherlapalem to Harpirala via Chikataipalem | 353.00/  08.04.2021 | 2021 | 2023 | 90% | - | - | 186.43 | - |
| 598 | MRL02-Gulla PWD road to Jukkal PWD road via Kantali, Longaon | 351.60/  23.06.2020 | 2021 | 2023 | 100% | 322.84 | 322.84 | - | - |
| 599 | C/o HLB on R/F Kukunurpally to Burugupally sivar at km 4/200 via Mangole, Thipparam | 349.00/  08.04.2021 | 2021 | 2023 | 85% | - | 321.68 | - | 675.00/  19.02.2024 |
| 600 | MRL08-Srinagar PWD road to Elgurustation via Enugal | 347.00/  08.04.2021 | 2021 | 2023 | 100% | 357.08 | 357.08 | 107.91 | - |
| 601 | T02-Medak Sardhana PWD road to Burugupally Via Muthaipally and Gajireddypally | 346.20/  23.06.2020 | 2021 | 2023 | 100% | - | - | 63.39 | - |
| 602 | HLB on R/F NLG-CTPL R&B road at 20/2 km to Koratikal | 346.00/  30.09.2021 | 2021 | 2023 | 100% | 46.74 | 85.78 | 26.19 | - |
| 603 | MRL04-NH 222 to Bansapally via Dilawarpur | 344.11/  23.06.2020 | 2021 | 2023 | 100% | 23.36 | 64.68 | - | - |
| 604 | MRL02-VV Palem Manchukonda ZP road at Vepakuntla to manuchukonda-pangidi ZP road at manchukonda via  chinthagurthy,mallepalli,gaddikunta thanda | 343.50/  08.04.2021 | 2021 | 2023 | 100% | - | 228.71 | 153.38 | - |
| 605 | MRL01-R and B Road at Aswapuram to Ammagaripalli via Amerda | 343.04/  23.06.2020 | 2021 | 2023 | 100% | - | 110.00 | 90.26 | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 606 | MRL02-Rajoli Reservoir to Waddepally ML | 340.40/  23.06.2020 | 2021 | 2023 | 100% | - | - | 74.71 | - |
| 607 | R/f Sangojiwada to Dhrmaraopet Sadashivnagar BT road via Kalojiwadi of Tadwai Mdl | 339.85/  23.06.2020 | 2021 | 2023 | 100% | - | - | 195.79 | - |
| 608 | MRL10-Ibrahimpet to Chinthagudem via Palem | 338.00/  30.09.2021 | 2021 | 2023 | 100% | 53.51 | 53.51 | 14.50 | - |
| 609 | T12-Gundur to Rangapur via Mukkurala | 336.50/  08.04.2021 | 2021 | 2023 | 100% | 270.69 | 404.45 | 121.79 | - |
| 610 | L038-Bejjur to Somini | 336.00/  03.04.2018 | 2021 | 2023 | 40% | 19.41 | 19.41 | 20.39 | - |
| 611 | MRL08-Road from PWD Road Sangam K to Kambalpally via Narsapur | 336.00/  08.04.2021 | 2021 | 2023 | 50% | 32.38 | 32.38 | 21.93 | - |
| 612 | C/O Bridge on T02-Mahabubnagar Mannanur PWD road at Nagarkurnool to Manthatigadda at 0/2 to 0/4Km | 335.00/  08.04.2021 | 2021 | 2023 | 65% | 52.28 | 52.28 | 45.62 | - |
| 613 | MRL04-Road from Botlavanaparthy to Paidi Chintalapally via Gollapally,Khanampally | 334.70/  08.04.2021 | 2020 | 2022 | 15% | - | 18.75 | - | - |
| 614 | MRL10-Road from PWD Road Khilavanaparthy to Kummarikunta | 334.39/  08.04.2021 | 2018 | 2022 | 0% | - | - | - | - |
| 615 | R/f PWD Road to Thalamkeri via Gurulingampally in Maganoor Mdl | 332.28/  23.06.2020 | 2018 | 2020 | 10% | - | - | - | - |
| 616 | MRL07-RF CC Kunta to Undyala (via) Nakkala vampu | 330.20/  08.04.2021 | 2018 | 2020 | 15% | - | 20.08 | - | - |
| 617 | MRL05-Bangaruchelimi thanda to Amarsingh thanda via Surya thanda,Chityala,Karre Shankru thanda | 330.00/  08.04.2021 | 2018 | 2020 | 0% | - | - | - | - |
| 618 | Construction of LSB at KM 0/130 to 0/225 on Road from T01 Tamsi B to Kapparla of Tamsi Mandal | 328.51/  08.04.2021 | 2020 | 2022 | 40% | - | 99.51 | - | - |
| 619 | T01-NH44 to Minnipad via Pullur Kalgotla | 327.80/  08.04.2021 | 2020 | 2022 | 75% | - | 238.90 | - | - |
| 620 | T02-Shabad PWD road to Palmakole via Nanajipur Makthaguda Pilloniguda | 326.80/  08.04.2021 | 2017 | 2019 | 30% | - | 23.00 | - | - |
| 621 | MRL03-Thorrur to PWD Road via Gopalagiri,Cherlapalem | 326.30/  08.04.2021 | 2020 | 2022 | 90% | - | 345.75 | - | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 622 | R/f Enkoor to Nacharam via Repallewada Medepalli of Enkoor mdl | 326.00/  08.04.2021 | 2020 | 2022 | 90% | - | 300.57 | - | - |
| 623 | T02-Yamcha to Binola Via Aljapur | 324.90/  08.04.2021 | 2020 | 2022 | 0% | - | - | - | - |
| 624 | T03-Chelmada-Naskal Road to Thujalpur via., Nagaram thanda, Nagaram, Naskal | 321.54/  23.06.2020 | 2021 | 2023 | 10% | - | - | - | - |
| 625 | T25-Peddakarpamula to Chinnakothapally | 321.20/  08.04.2021 | 2020 | 2021 | 15% | - | - | - | - |
| 626 | MRL11-NH Road Katakshapur to Pragathisingaram | 321.00/  08.04.2021 | 2021 | 2023 | 85 | 181.12 | 181.12 | - | - |
| 627 | MRL10-BT road to Anantharam Kishangudem Via Ammanabole | 321.00/  08.04.2021 | 2021 | 2023 | 75 | 89.53 | 89.53 | - | - |
| 628 | R/f Kunsi PWD road to Chegunta X road via Aalampally in Krishna mdl | 320.91/  08.04.2021 | 2017 | 2019 | 50% | - | 179.90 | - | - |
| 629 | MRL12-RandB road to Bijjaram ML via Sangala  Jilledbanda | 320.30/  08.04.2021 | 2021 | 2023 | 100% | - | 186.47 | 143.47 | - |
| 630 | PEDDAVAMPU BRIDGE at 3.99 TO 4.030 KM | 320.00/  08.04.2021 | 2021 | 2023 | 90% | 121.40 | 149.02 | - | - |
| 631 | MRL14-Lingampally X Road to Peddanemila via Alugunuru | 318.00/  08.04.2021 | 2021 | 2023 | 0% | - | - | - | - |
| 632 | T06-Rasimatla to Korkal | 317.50/  04.03.2018 | 2020 | 2023 | 100% | 15.78 | 189.45 | 15.78 | - |
| 633 | MRL17-Raghavapuram to Errabettu thanda via Brahmanapally | 317.28/  23.06.2020 | 2021 | 2023 | 80% | - | 228.38 | - | - |
| 634 | MRL12-PWD ROAD NAGAIPALLI TO PWD ROAD SHATRAJPALLI VIA KONDANNAPET | 317.00/  08.04.2021 | 2020 | 2023 | 100% | - | 246.52 | 114.94 | - |
| 635 | MRL01-Road from Vittunaik Thanda to Mogudampally | 315.97/  23.06.2020 | 2021 | 2023 | 100% | 36.70 | 36.70 | 69.55 | - |
| 636 | MRL08-Khammam-Yellandu R and B road to Vvpalem,Machukonda road at Vepakuntla via Raghunadhapalem | 315.30/  08.04.2021 | 2020 | 2023 | 100% | 79.78 | 355.99 | 79.79 | - |
| 637 | T01-Kukunurpally to Burugupally sivar via Mangole, Thipparam | 314.89/  23.06.2020 | 2021 | 2023 | 0% | - | - | - | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 638 | Construction of Bridge on R/F Beemanapally to Palnativarigudem at 1/3 to 1/4 km of Madgulapally(M) | 313.00/  30.09.2021 | 2020 | 2023 | 100% | - | 227.09 | 89.47 | - |
| 639 | MRL01-NLG-CTPL R and B road at 20 2 km to Koratikal | 312.48/  23.06.2020 | 2021 | 2023 | 5% | - | - | - | - |
| 640 | Construction of bridge from Raikode to Raghavapur at 2/9 Km | 312.00/  08.04.2021 | 2020 | 2022 | 90% | - | 143.36 | - | - |
| 641 | MRL03-Tanikella to Ganeswaram via narling thanda | 311.50/  08.04.2021 | 2020 | 2022 | 30% | - | 72.16 | 50.00 | - |
| 642 | R/f MDR at Bayyaram to NH at Besthagudem via Pathareddypalem, Venkatraopeta, Jaggaram in Pinapaka mdl | 311.00/  08.04.2021 | 2021 | 2023 | 2% | - | - | - | - |
| 643 | MRL22-PWD Road to Apparajpally via Chakru thanda, Damera vancha, line thanda, AR thanda | 310.70/  08.04.2021 | 2021 | 2023 | 5% | - | - | - | - |
| 644 | Construction of HLB on R/F N765 to Shankerakondathanda via Meddagadda Thanda at 3/0 to 3/2 Km | 310.00/  08.04.2021 | 2021 | 2025 | 5% | - | - | - | - |
| 645 | HLB at KM 1.365 on Road from Kamaram to Laxmipur via Penchikalpet and Keshavapur | 310.00/  08.04.2021 | 2021 | 2025 | 0% | - | - | - | - |
| 646 | T03-Road from Ravindranagar to Ambagat | 307.65/  23.06.2020 | 2020 | 2022 | 50% | 511.71 | 511.71 | - | - |
| 647 | MRL02-Sirikonda to Burkacherla via Mekalapati thanda | 306.54/  23.06.2020 | 2021 | 2025 | 0% | - | - | - | - |
| 648 | R/f Baswaipally to Devarakadra in Devarakadra mdl | 306.29/  23.06.2020 | 2020 | 2022 | 80% | - | 117.11 | 45.60 | - |
| 649 | MRL04-R and B Road at Km 5.50 to Devapur Road via Regulaguda | 305.30/  08.04.2021 | 2021 | 2023 | 5% | - | - | - | - |
| 650 | R/f PWD road Indiranagar to Jeelugula via Gopalpur in Elkathruty mdl | 304.00/  08.04.2021 | 2021 | 2023 | 5% | - | - | - | - |
| 651 | MRL08-Chinthakani to Prodduturu | 303.80/  08.04.2021 | 2021 | 2023 | 65% | - | - | 45.60 | - |
| 652 | MRL16-Dharmaram to Agraharam via Chandragiri, Ramnnapet, Nagaram. | 303.70/  08.04.2021 | 2020 | 2022 | 80% | - | 83.33 | - | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 653 | MRL02-Sulthanabad to Regadimaddikunta Via Suddala | 302.70/  08.04.2021 | 2021 | 2023 | 25% | - | - | 72.31 | - |
| 654 | L043-ZP road to Nagu Guda | 300.49/  16.03.2013 | 2021 | 2023 | 5% | - | - | - | - |
| 655 | Constn of High level Bridge at 1/000 Km on Kethini to Dimda | 300.00/  27.02.2017 | 2021 | 2023 | 5% | - | - | - | - |
| 656 | MRL07-NH44 at Pothulamadugu to Ghanpur R B Road via Kappeta and PathaKappeta at 7/450KM TO 7/550  KMS | 300.00/  08.04.2021 | 2021 | - | 0% | - | - | - | - |
| 657 | MRL31-PR ROAD TO MANAJIPET VIA GATTUKADIPALLY | 299.70/  08.04.2021 | 2021 | 2023 | 100% | - | - | 121.37 | - |
| 658 | MRL01-Nidamanoor to Venigandla via Rajannagudem | 297.99/  30.09.2021 | 2021 | 2024 | 5% | - | - | - | - |
| 659 | T01-Gudem to Musthabad via pothugal | 294.00/  08.04.2021 | 2020 | 2023 | 100% | 43.36 | 43.36 | 175.43 | - |
| 660 | HLB on RF MRL02-Domaledgi camp to Bodhan via Ethonda camp Raikur at 12.60KM of Kotagiri mandal | 293.30/  08.04.2021 | 2021 | 2023 | 100% | - | - | 71.92 | - |
| 661 | HLB on R/F Pani thanda to Patimidi gudem via Pagidipally | 293.00/  30.09.2021 | 2021 | 2023 | 15% | - | - | 179.57 | - |
| 662 | MRL16-Road from Ippalaguda to Gouraram PWD Road via Pamulaparthy , Pamulaparthy Banda | 293.00/  08.04.2021 | 2021 | 2023 | 0% | - | - | - | - |
| 663 | MRL12-Kothlabad R and B road to Mekalamasoni thanda upto mandal limits via Burgupally and  Chandraspslly. | 292.00/  08.04.2021 | 2021 | 2023 | 100% | 128.11 | 128.11 | - | - |
| 664 | Construction of HLB at km 2/225 on R/F Thorrur to PWD Road Ammapuram | 292.00/  08.04.2021 | 2020 | 2023 | 100% |  | 299.18 | 38.79 | - |
| 665 | MRL17-Road From R and B Road Rallapet to Jillella- Musthabad Road via Obulapur,Ankireddipally,Deshaipally and Mallapur | 289.10/  08.04.2021 | 2020 | 2023 | 100% |  | 440.75 | 82.79 | - |
| 666 | MRL11-Masaipet-Dharmareddygudem ZP Road to Peddakandukur (via) Bahupet, Thallagudem | 289.00/  08.04.2021 | 2021 | 2023 | 100% | 124.36 | 74.55 | 135.52 | - |
| 667 | MRL02-RF Pervala To Naredgomma | 287.00/  30.09.2021 | 2021 | 2023 | 100% | 173.34 | 173.34 | 56.02 | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 668 | MRL15-R and B road to Yaparla via Bheemla tanda , Miyapur | 287.00/  08.04.2021 | 2020 | 2023 | 100% | 295.25 | 782.75 | 104.38 | - |
| 669 | T05-R and B Road 11.600 Km to R and B Road at Gannaram via Gajjiguda, Mosam | 286.20/  08.04.2021 | 2020 | 2022 | 80% | 147.23 | 529.68 | 48.81 | - |
| 670 | MRL09-NH 44 to Shankarapur via Ghansimiyaguda | 282.50/  08.04.2021 | 2020 | 2022 | 100% | - | 321.84 | - | - |
| 671 | MRL03-Gousukonda to Reddy nagar via Gousukonda thanda,Ramlingampally,Shivareddygudem | 280.50/  23.06.2020 | 2013 | 2020 | 35% | 50.07 | 143.40 | - | 2,215.00/  04.08.2023 |
| 672 | MRL03-Domalapally to Mandal limits (via) Appajipeta, Mirlonigudem | 278.00/  30.09.2021 | 2013 | 2015 | 70% | - | 304.22 | 11.16 | - |
| 673 | T05-NH63 Kalleda to Laxmipur via Gutrajpally | 272.40/  08.04.2021 | 2018 | 2020 | 50% | - | 36.97 | - | - |
| 674 | T01-Medak-Bodmatpally PWD road to Narsingi kodpak PWD road road via Papannapet ,Namapur,Namapur LT  and Chitriyal LT | 272.31/  23.06.2020 | 2018 | 2020 | 5% | - | 6.02 | - | - |
| 675 | C/o Bridge @ 0/0 to 0/4, Km on R/f Anarpally to Karanjiwada | 272.22/  17.09.2010 | 2018 | 2020 | 25% | - | 72.99 | - | - |
| 676 | R/f Pallegadda to NH 167 via Sanjeevakonda, Pusalpad and Raikonda in Marikal mdl | 271.20/  08.04.2021 | 2020 | 2022 | 100% | 42.87 | 480.33 | - | - |
| 677 | MRL05-R F Chinthakunta to R and B Road Karimnagar to jagityal | 270.80/  08.04.2021 | 2020 | 2022 | 100% | - | 524.63 | - | - |
| 678 | Construction of HLB at km 6/020 on R/F PWD Road Thorrur to Kommanapally via Chinthalapally | 270.00/  08.04.2021 | 2021 | 2023 | 100% | 89.37 | 89.37 | - | - |
| 679 | MRL11-PWD Road Annaram to Kasimnagar via Remaddula | 268.90/  08.04.2021 | 2020 | 2022 | 100% | 97.83 | 97.83 | 44.57 | - |
| 680 | MRL03-PWD Road- Chennam-Pagidipally- Nagaram | 268.14/  23.06.2020 | 2021 | 2023 | 0% | - | - | - | - |
| 681 | R/f PWD Road Namathpally to PWD road at km  Jampally to Bollepalli in Bhongir mdl | 268.00/  08.04.2021 | 2020 | 2022 | 90% | - | 267.08 | 63.22 | - |
| 682 | CONSTRUCTION OF HLB AT 5/0 KM ON MRL-05 R/F CHINTHAKUNTA R&B ROAD TO KARIMNAGAR - JAGITYAL ROAD | 265.00/  08.04.2021 | 2021 | 2024 | 60% | - | - | - | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 683 | MRL07-NH44 at Pothulamadugu to Ghanpur R B Road via Kappeta and PathaKappeta at 1/780 to 1/880 | 265.00/  08.04.2021 | 2021 | 2024 | 5% | - | - | - | - |
| 684 | MRL01-Road from NH 65 to Maktha allur via Kothlapur | 261.00/  08.04.2021 | 2021 | 2023 | 100% | - | - | - | - |
| 685 | C/o Bridge at 7/0 Km on MRL02-PWD Road Mediguda to Maregoan via Kothapally G Kunikasa, ParaswadaB | 259.00/  08.04.2021 | 2021 | 2023 | 90% | - | - | - | - |
| 686 | MRL11-Kandulavarigudem to Rollavarigudem via Dirsencherla | 256.70/  23.06.2020 | 2021 | 2023 | 40% | - | - | - | - |
| 687 | T05-Bundanakal to Musthabad via Hanuman nagar | 256.60/  08.04.2021 | 2020 | 2022 | 95% | 260.02 | 505.90 | - | - |
| 688 | MRL04-Shaikpally RB Road to Vepur via Ayodyanagar atayakunta tanda | 255.80/  08.04.2021 | 2020 | 2022 | 50% | - | 308.12 | - | - |
| 689 | MRL08-Kalakota to Narayanapuram | 254.50/  08.04.2021 | 2021 | 2025 | 40% | - | - | 220.02 | - |
| 690 | R/f Ratannaik Thanda to Pilkampet PWD road via Sajjanpally Ekkapally of Lingampet mdl | 252.90/  23.06.2020 | 2020 | 2022 | 40% | - | 128.83 | - | - |
| 691 | MRL07-Road from R and B road at Gangapur to  Velgonda Via Yashwantharaopet, Buggaram | 250.30/  08.04.2021 | 2020 | 2023 | 100% | 216.61 | 212.84 | 76.22 | - |
| 692 | HLB Bridge on BT R/F Mutyalampadu X Road to Station Thadikalapudi at 5/2 | 250.00/  08.04.2021 | 2021 | 2023 | 80% | 185.29 | 185.29 | 61.42 | - |
| 693 | COST OF HIGH LEVEL BRIDGE ON RF BASWAIALLY TO DEVARKADRA AT 5/200 to 5/400 | 250.00/  08.04.2021 | 2021 | 2023 | 100% | 127.27 | 209.07 | 18.21 | 253.02/  08.08.2023 |
| 694 | MRL12-Himmathraopet to Ramaraopet via Nachupally | 249.50/  08.04.2021 | 2021 | 2023 | 95% | 105.88 | 106.22 | - | - |
| 695 | MRL02-Dharur to Peelaram via Kukkinda Dharmapur | 248.83/  23.06.2020 | 2021 | 2023 | 95% | 306.08 | 306.52 | - | 416.00/  10.08.2023 |
| 696 | MRL04-RandB road to Pagunta ML via Neelahalli Nettempad | 248.00/  08.04.2021 | 2021 | 2023 | 90% | 219.21 | 219.64 | 103.38 | 506.00/  10.09.2023 |
| 697 | R/f Jagitial Peddapally road to Kurmapalli via Raginedu in Peddapalli mdl | 248.00/  08.04.2021 | 2021 | 2023 | 95% | - | 0.47 | 83.11 | - |
| 698 | MRL13-PWD Road Lalithapur to Kondapalkala via Ranganayakulapally Devampally | 247.70/  08.04.2021 | 2021 | 2023 | 100% | - | 179.23 | 123.17 | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 699 | MRL02-Dammannapet to Kacharam Via. Kalwakota, Rangapur | 247.60/  08.04.2021 | 2021 | 2023 | 95% | - | 0.52 | 242.81 | 565.00/  10.09.2023 |
| 700 | MRL13-Polampally X road to Kothapally via Nallagonda | 245.30/  08.04.2021 | 2021 | 2023 | 80% | - | 0.39 | - | - |
| 701 | MRL01-Nennal to Kushnapalli via Konampet | 243.55/  23.06.2020 | 2021 | 2023 | 80% | - | - | 159.86 | 625.00/  30.09.2023 |
| 702 | MRL02-Rayaparthy to Mahaboob nagar via Periked Ganeshkunta thanda | 242.50/  08.04.2021 | 2021 | 2023 | 95% | 50.05 | 90.05 | - | - |
| 703 | MRL02-Yendlapally to Rekyathanda PWD road via sapawaththanda and Rekyathanda | 242.50/  23.06.2020 | 2021 | 2023 | 100% | 38.04 | 38.04 | - | - |
| 704 | R/f PWD Road Roamaram to Jeedikal via Masanpally, Seetarampur, Velmajala and Kommaiahpally of Gudala mdl | 241.00/  08.04.2021 | 2021 | 2023 | 30% | - | 37.56 | - | - |
| 705 | MRL16-R and B road to Gudem Via Bekkem Peddabilku | 237.20/  08.04.2021 | 2021 | 2023 | 60% | 29.85 | 29.85 | 61.61 | - |
| 706 | MRL12-R and B Road Guntapally cheruvu thanda to Somarampeta Road via Raasigutta thanda, Banjeru,  Maddimalla | 232.00/  08.04.2021 | 2021 | 2023 | 70% | - | - | 384.35 | - |
| 707 | MRL11-Husnabad-Madatha road to Potharam S via Mohmaddapur , Ummapur, Nagaram. | 231.00/  08.04.2021 | 2021 | 2023 | 95% | 142.62 | 142.62 | 69.36 | - |
| 708 | MRL13-Vellulla to Kondrikarla via Masaipet | 230.2/ 08.04.2021 | 2021 | 2023 | 95% | - | 112.18 | 72.56 | - |
| 709 | MRL09-PWD Road Thorrur to Kommanapally via Chinthalapally | 229.00/  08.04.2021 | 2021 | 2023 | 70% | - | - | 269.89 | - |
| 710 | HLB ON RF SIKINDRAPUR TO MUCHKUR VIA GONGOPPULA AT 785 KM | 228.00/  08.04.2021 | 2021 | 2023 | 90% | 39.50 | 39.50 | 155.70 | - |
| 711 | HLB on RF Slampad camp to Sunkini via kumanpally Hunsa mandarna at 7.45KM of Bodhan mandal | 227.63/  08.04.2021 | 2021 | 2023 | 20% | - | - | 93.67 | - |
| 712 | MRL01-gondriyala Pwd Road to Nh 65 via kothagudem,Mangalithanda | 227.00/  08.04.2021 | 2021 | 2023 | 0 | - | - | - | - |
| 713 | MRL02-Wardhamankota to Jajireddygudem via Narsimhulagudem, Kanchugatlagudem, Thungagudem | 227.00/  08.04.2021 | 2021 | 2023 | 95% | - | - | - | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 714 | R/f Mahabubnagar Mannanur PWD Road at Nagarkurnool to Manthatigadda via Desitikyal, Manthati at Nagarkurnool mdl | 224.50/  23.06.2020 | 2021 | 2023 | 20% | - | - | 33.92 | - |
| 715 | MRL01-Baswapur to Thimmapur (via) Bhairapur, Mallapur, Venkateshwara Temple | 224.00/  23.06.2020 | 2021 | 2023 | 20% | - | - | - | - |
| 716 | C/o 5 vents 10mts span bridge at 8/950 km on road from MRL01-Nennal to Kushnapalli via Konampet | 224.00/  08.04.2021 | 2021 | 2023 | 25% | - | 2.65 | 69.91 | - |
| 717 | T11-Pani thanda to Patimidi gudem via Pagidipally | 224.00/  30.09.2021 | 2021 | 2023 | 10% | - | 0.85 | - | - |
| 718 | T11-R and B Road at Pittalonigudem to R and B Road at Kolkonda Via Banjipet, Kannaiahpally, Kodur  Ramachandrapuram | 223.00/  08.04.2021 | 2020 | 2023 | 100% | 484.64 | 462.95 | 102.74 | - |
| 719 | T02-RF Kalvala X Road to Keshavapur Via Kanaparthi and Valbhapur | 222.50/  08.04.2021 | 2021 | 2023 | 50% | 86.23 | 86.23 | 68.08 | - |
| 720 | MRL09-Addagudur to kotamarthy vai Anantharam | 222.00/  08.04.2021 | 2021 | 2023 | 35% | - | - | - | - |
| 721 | MRL06-Vinjamoor gate to Rainguda | 221.34/  23.06.2020 | 2021 | 2023 | 35% | - | 0.31 | 26.59 | - |
| 722 | T01-Dahegaon to PP Rao Colony via Hathini | 221.12/  23.06.2020 | 2021 | 2023 | 35% | - | 0.41 | 23.99 | - |
| 723 | L039-PWD road to Jhaduguda | 220.5/ 03.04.2018 | 2021 | 2023 | 35% | - | 0.55 | 214.48 | - |
| 724 | MRL13-Chamanpally to Kushanpally | 219.02/  23.06.2020 | 2021 | 2023 | 100% | - | 210.65 | - | - |
| 725 | Construction of HLB on R/F Kalvapally cart bridge to Gudur via Avanthipuram at 8/050 to 8/150 km | 218.00/  30.09.2021 | 2020 | 2022 | 100% | - | 81.06 | - | - |
| 726 | T01-Kolidinne to Rajoli ML via Shantinagar, Waddepally | 216.80/  08.04.2021 | 2021 | 2023 | 20% | - | - | - | - |
| 727 | MRL02-NH9 at Durajpally(Arch) to Chivemla via Khasimpet | 216.00/  08.04.2021 | 2021 | 2023 | 90% | 99.04 | 99.04 | - | - |
| 728 | MRL18-Zp road Nagnur to Ranipur viaTeegalaguttapally | 215.70/  08.04.2021 | 2020 | 2022 | 80% | 93.33 | 93.33 | - | - |
| 729 | MRL08-Pedda Pakalagudem to Chinna Pakalagudem via Satyanarayanapuram | 214.00/  08.04.2021 | 2021 | 2023 | 0% | - | - | - | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 730 | MRL07-TO2 Dhammakapet to Katrepally | 212.50/  08.04.2021 | 2021 | - | 0% | - | - | - | - |
| 731 | HLB ON RF SIKINDRAPUR TO MUCHKUR VIA GONGOPPULA AT 1 55KM | 212.00/  08.04.2021 | 2020 | 2022 | 100% | 100.00 | 273.23 | 112.05 | - |
| 732 | T01-Road from Sirikonda to Indervelly via Dasnapur, Pittabongaram and Harkapur | 212.00/  08.04.2021 | 2021 | 2023 | 50% | - | - | - | - |
| 733 | Construction of Bridge at KM 7/300 on RF Dornakal R B Road to Mulkalapally NH Road via Vennaram | 211.51/  08.04.2021 | 2021 | - | 0% | - | - | - | - |
| 734 | Constn of High level Bridge at 13/900 km on R/f Gudem to Bejjur | 210.50/  27.02.2017 | 2020 | 2022 | 100% | 95.26 | 242.45 | - | - |
| 735 | R/f PWD Mubarak Nagar Sukjith Factory to ZP road via Reddy Camp of Nizamabad mdl | 210.01/  08.04.2021 | 2020 | 2022 | 100% | 139.70 | 155.44 | - | - |
| 736 | MRL01-Thorrur to PWD Road Ammapuram via Kantaipalem | 210.00/  08.04.2021 | 2021 | 2023 | 40% | 69.84 | 69.84 | - | - |
| 737 | MRL04-Chandupatla ZP Road at 1.0Km to Moggaigudem to Rollabanda tanda | 210.00/  08.04.2021 | 2021 | 2023 | 25% | 74.89 | 74.89 | 98.79 | - |
| 738 | Construction of bridge on Road From Vittunaik Thanda to Mogudampally at 2/5 Km | 210.00/  08.04.2021 | 2021 | 2023 | 25% | 36.60 | 36.60 | - | - |
| 739 | MRL01-Thalpnur to keshampet via thalpnur thanda, patha thanda | 209.00/  08.04.2021 | 2021 | 2023 | 70% | 212.82 | 212.82 | 43.47 | - |
| 740 | MRL03-Dacharam Aipur PWD road at 23km 300mts to Kudali via Makthakothagudem | 207.05/  23.06.2020 | 2021 | 2023 | 100% | 212.82 | 212.82 | - | - |
| 741 | MRL13-PWD Road Madhapur to Katlakunta via Chinnametpally | 206.50/  08.04.2021 | 2021 | 2023 | 25% | - | - | - | - |
| 742 | C/o Bridge at 5/0 Km on MRL02-PWD Road Mediguda to Maregoan via Kothapally G Kunikasa, ParaswadaB | 206.00/  08.04.2021 | 2020 | 2022 | 85% | - | 910.55 | - | 1,011.31/  24.02.2023 |
| 743 | MRL01-Gouthapur - Parwathapur via Chintamanipatnam | 206.00/  23.06.2020 | 2021 | 2023 | 50% | - | - | - | - |
| 744 | C/o HLB on R/f R&B Road at Anantharam to Gollagudemd via Kothur at Karakagudem mdl | 205.73/  08.04.2021 | 2021 | 2024 | 75% | 99.98 | 199.98 | - | - |
| 745 | PWD Road - Neelavancha | 205.03/  09.11.2012 | 2021 | 2023 | 25% | - | 24.85 | - | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 746 | L022-Etiguda to Thalai | 205.00/  03.04.2018 | 2021 | 2023 | 25% | - | 54.40 | - | - |
| 747 | MRL14-Road from Jagdevpet to Shakapur Via Kondapur | 204.50/  08.04.2021 | 2021 | 2023 | 25% | 31.34 | 31.34 | - | - |
| 748 | MRL08-Brahmanapally to Rajupeta via Kattigudem, Devanagaram | 204.5/ 08.04.2021 | 2021 | 2023 | 75% | - | - | 52.02 | - |
| 749 | MRL03-R and B Road Sirsapally to Thakalapally via Rajapally | 203.00/  08.04.2021 | 2020 | 2022 | 100% | 56.57 | 149.69 | - | - |
| 750 | MRL07-Chinnamallela to Jayalaxmipuram | 202.00/  08.04.2021 | 2021 | 2023 | 10% | 174.50 | 174.50 | - | - |
| 751 | Construction of 3V Bridge at KM 2/660 on RF PWD Road to Rajulakothapally via Sriramagiri,Venkatapur | 200.00/  08.04.2021 | 2020 | 2022 | 100% | - | 289.82 | 51.29 | - |
| 752 | MRL12-NH9 at 147km to KMM pwd road at chandupatla via Thimmapuram | 200.00/  08.04.2021 | 2021 | 2023 | 10% | - | - | - | - |
| 753 | MRL02-Thorrur to PR Road Venkatapur via Dasru thanda Kevula thand,Kicha thanda | 199.40/  08.04.2021 | 2021 | 2023 | 10% | - | - | - | - |
| 754 | R/f Madwar PWD road to Lalkota PWD Road via Pallegadda, Teelair, Venkatapur and PC Kunta in Marikal mdl | 199.30/  08.04.2021 | 2020 | 2022 | 75% | - | 1,514.35 | - | 2590/  12.01.2023 |
| 755 | MRL05-R and B Road Lingapur to Machanapally Via Pothireddypeta | 198.70/  08.04.2021 | 2021 | 2023 | 75% | - | - | - | - |
| 756 | MRL02-Bheemgal RB road to Akloor via Bada Bheemgal | 196.80/  08.04.2021 | 2021 | 2023 | 10% | - | - | - | - |
| 757 | MRL09-T04 to Guntipalli via Somavarigudem | 196.00/  30.09.2021 | 2021 | 2023 | 100% | 152.07 | 152.07 | 41.89 | - |
| 758 | MRL08-Nagdar PWD Road to Kamareddy District Border Via Garugu Chettu Thanda Raparthy Kalher | 195.00/  08.04.2021 | 2020 | 2022 | 100% | - | 169.64 | - | - |
| 759 | C/O 4 V 10 Mts SPAN BRIDGE AT 0/200 TO 0/400 ON R/F PWD ROAD TO PONAGUDA | 192.50/  04.03.2018 | 2021 | 2023 | 100% | - | 230.75 | 114.24 | - |
| 760 | MRL06-Shalapally to Venkatraopally | 192.00/  08.04.2021 | 2021 | 2023 | 100% | - | - | - | - |
| 761 | Thallavagu Bridge on R/F Sirikonda to Burkacherla via Mekalapati thanda | 190.00/  08.04.2021 | 2021 | 2023 | 100% | 77.66 | 177.66 | - | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 762 | MRL01-Gouraipally to Gurjakunta via Vechareni | 189.74/  23.06.2020 | 2021 | 2023 | 100% | - | - | 26.82 | - |
| 763 | Construction of bridge Road From Thangallapally to Ellanthakunta via Laxmipur,Veljipur,Ernasupally a | 187.00/  08.04.2021 | 2021 | 2023 | 100% | 100.00 | 100.00 | - | - |
| 764 | Kathalapur to Athmakur ia Bhushanraopet, ootapally | 186.40/  08.04.2021 | 2020 | 2022 | 100% | 36.67 | 362.89 | - | - |
| 765 | MRL15-Nagaragouda to KAdmur Bridge via Ragadidoswada | 183.60/  08.04.2021 | 2020 | 2022 | 100% | - | 154.78 | - | - |
| 766 | R/f Kadukuntla to Pebbair PWD road via Kadukuntla Peddagudem and Kistagiri in Wanaparthy mdl | 183.46/  23.06.2020 | 2021 | 2023 | 100% | - | - | - | - |
| 767 | R/f Special repairs to Sugur to Mungamaddinne via  Janumpallly in Pebbair mdl | 183.10/  08.04.2021 | 2021 | 2023 | 100% | 254.33 | 254.33 | 26.82 | - |
| 768 | L033-Kosagutta to Yapalguda | 181.50/  04.03.2018 | 2021 | 2023 | 20% | 62.27 | 62.27 | - | - |
| 769 | C/o High Level Bridge on R/F Dammannapet to Kacharam Via. Kalwakota, Rangapur, MP Medipally | 180.00/  08.04.2021 | 2020 | 2022 | 100% | - | 191.38 | - | - |
| 770 | MRL17-MK Road to NH365 at Thungathurthy Shadikana via Thurupugudem, Ganugabanda | 180.00/  08.04.2021 | 2021 | 2023 | 0% | - | - | - | - |
| 771 | Bridge at km.8.80 on road Rakamcharla - Pudugurthy | 180.00/  08.04.2021 | 2020 | 2022 | 100% | - | 540.13 | - | - |
| 772 | CHAKALIBONDA VAGU at 3.57 to 3.61 | 180.00/  08.04.2021 | 2020 | 2022 | 100% | - | 199.25 | - | - |
| 773 | MRL11-SH - 11 at Thimmapur to Veernapally via Bongulakindi thanda, Bavsingh thanda | 178.50/  08.04.2021 | 2021 | 2023 | 20% | - | 69.30 | - | - |
| 774 | Constn of High level Bridge at 15/400 Km on R/f Gudem to Bejjur | 178.00/  27.02.2017 | 2021 | 2023 | 30% | - | 137.98 | - | - |
| 775 | MRL05-Paspula to Tulsipet via Harichandthanda | 168.27/  23.06.2020 | 2020 | 2022 | 50% | - | 135.54 | - | - |
| 776 | Construction of bridge from Singitham to Moratga at 2/6 Km | 167.00/  08.04.2021 | 2021 | 2023 | 50% | - | - | - | - |
| 777 | C/o Bridge from 2/900 to 3/100 KM on road from MRL06-Keslaguda to Devapur via Durvaguda,  Kobbaiguda | 164.43/  08.04.2021 | 2020 | 2022 | 70% | - | 223.40 | - | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 778 | MRL04-PWD Madharam to Pharma Company via Mantrikunta,Kistaipally. | 163.60/  23.06.2020 | 2020 | 2022 | 100% | - | 461.02 | - | - |
| 779 | MRL08-Jagdevpur PWD Road Cheekatimamidi ZP Road at 3km 500 Mtrs to Bommalaramaram Nagineniplly ZP Road at 3km Via Machanpally, Hazipur | 161.00/  08.04.2021 | 2021 | 2023 | 70% | - | - | - | - |
| 780 | L030-PWD ROAD MONDIKUNTA TO MAMILLAVAI | 159.90/  03.04.2018 | 2021 | 2023 | 50% | - | - | - | - |
| 781 | construction of high level bridge at 10.20 km on road from velganoor to kothakommuguda | 158.00/  08.04.2021 | 2020 | 2022 | 50% | - | - | - | - |
| 782 | T01-PWD Road to Mandal Limits at Loknaik Thanda  Vai Vatpally, Dudyal | 158.00/  08.04.2021 | 2020 | 2022 | 50% | 120.83 | 152.10 | - | - |
| 783 | MRL04-Road from Brahmanpally X Road to Essampet via Akenpally | 155.30/  08.04.2021 | 2021 | 2023 | 35% | 45.32 | 105.32 | - | - |
| 784 | C/o HLB on R/f Dharmaraopet to PWD road in Dandepalli Mdl | 155.00/  08.04.2021 | 2021 | 2023 | 35% | - | - | - | - |
| 785 | SH - 11 at Thimmapur to Veernapally via Bongulakindi thanda, Bavsingh thanda | 154.00/  08.04.2021 | 2021 | 2023 | 0% | - | - | - | - |
| 786 | C/o HLB at Km 4/450 on R/f Mogaddhagad PR (BT) Road to Karjepally R&B Road via Veervelly, Loanvellly | 153.00/  08.04.2021 | 2021 | 2023 | 15% | - | - | - | - |
| 787 | Construction of HLB at 5/925 on R/F Gundareddypally to Baswapur via Muthannapet | 152.00/  08.04.2021 | 2021 | 2023 | 0% | - | - | - | - |
| 788 | Construction of High Level Bridge on R/F NH44 to Minnipad via Pullur Kalgotla at 5/8 to 6/0 km | 150.00/  08.04.2021 | 2021 | 2023 | 90% | - | - | 64.93 | - |
| 789 | C/O HLB ON ROAD FROM MALLANNAGUTTA to  modegoan at 11/19 km | 150.00/  08.04.2021 | 2020 | 2022 | 70% | - | 247.69 | - | - |
| 790 | C/O Bridge on R/F T02, road FromJakinalpally to Bommraspally at Km 5/6-8, Urkonda Mandal, Nagarkurno | 150.00/  08.04.2021 | 2021 | 2023 | 100% | 113.05 | 113.05 | 160.87 | - |
| 791 | Bridge at km.6.600 on road Anthwar to Doulthabad via Gundepally | 148.00/  08.04.2021 | 2021 | 2023 | 30% | 50.00 | 50.00 | 24.97 | - |
| 792 | MRL06-Gantlakunta to PR Road via Ramoji thanda,Enamedi thanda and Pochampally | 148.00/  08.04.2021 | 2021 | 2023 | 100% | 125.03 | 125.03 | 54.40 | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 793 | C/0 HLB ON ROAD FROM MALLANNAGUTTA TO  MODEGOAN chainage 10 /5 km | 145.00/  08.04.2021 | 2021 | 2023 | 95% | - | - | - | - |
| 794 | Construction of bridge on R/F Chadupatla ZP road at 1.0km to Moggaigudem | 145.00/  08.04.2021 | 2021 | 2023 | 100% | 86.16 | 86.16 | 76.23 | - |
| 795 | L052-PR road to Tummalapahad | 143.50/  03.04.2018 | 2020 | 2023 | 100% | 59.44 | 103.44 | 74.15 | - |
| 796 | C/o 3 vents 10.00mts at 8/750km on road from MRL01- Nennal to Kushnapalli via Konampet | 140.00/  08.04.2021 | 2021 | 2023 | 95 | 89.01 | 89.01 | - | - |
| 797 | C/o HLB at 2/50 km on Road from Mangalpet PWD Road to Gunukula kunta via Namlimet Pothanpally M Mad | 140.00/  08.04.2021 | 2021 | 2023 | 85 | 300.87 | 300.87 | 89.76 | - |
| 798 | C/o Minor Bridge at Ch4/8 Km on R/f BakthimallaPWD Road to Musrifa via Hanumanpally, Bijjaram | 139.00/  08.04.2021 | 2021 | 2023 | 80 | 43.60 | 43.60 | - | - |
| 799 | Construction of HLB on R/F Kunsi PWD road to Chegunta X road at 4/0-4/2 Km | 136.00/  08.04.2021 | 2021 | 2023 | 80 | 160.01 | 235.01 | 103.83 | - |
| 800 | C/O HIGH LEVEL BRIDGE AT KM 2/28ON R/F R&B ROAD AT 5.50KM TO DEVAPUR ROAD VIA  REGULAGUDA,GURVAPUR IN | 132.00/  08.04.2021 | 2021 | 2023 | 100 | 7.87 | 28.30 | 74.76 | - |
| 801 | MRL01-Induvasi to Ieeja ML via Boyalagudem | 131.55/  23.06.2020 | 2021 | 2023 | 80 | 237.36 | 372.33 | - | - |
| 802 | L029-PWD road to Potharajtemple | 131.30/  03.04.2018 | 2021 | 2023 | 80 | 100.04 | 440.32 | - | - |
| 803 | MRL02-Ghattu to Maddelabanda upto ML | 128.75/  23.06.2020 | 2021 | 2023 | 100 | 23.76 | 23.76 | 389.50 | 515.00/  09.10.2023 |
| 804 | L028-Ravindranager to Korsini | 128.50/  03.04.2018 | 2021 | 2023 | 80 | 113.10 | 251.59 | - | - |
| 805 | GUDDIMOTHA VAGU BRIDGE at 6.44to 6.47 | 128.00/  08.04.2021 | 2021 | 2023 | 100 | 183.21 | 271.56 | 211.56 | 590.70/  12.01.2023 |
| 806 | L054-PR road to Lachimpur B | 126.98/  03.04.2018 | 2021 | 2023 | 30 | - | - | - | 990.00/  09.10.2023 |
| 807 | C/o Bridge at Km 6/600 on R/f Laxmipur to Baddampally | 125.50/  04.03.2018 | 2021 | 2023 | 100 | 230.92 | 230.92 | - | 360.00/  08.10.2023 |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 808 | C/o High Level Bridge on R/F SH7 to Dharmasagar via Ananthasagar madipalle , in Hasanparthy (M) | 125.00/  08.04.2021 | 2021 | 2023 | 100 | - | 731.23 | - | 1,100/  09.10.2023 |
| 809 | L032-PWD Road to Edlagudam | 120.00/  04.03.2018 | 2021 | 2023 | 70 | - | 103.53 | - | - |
| 810 | C/o HLB on R/F Paspula to Tulsipet via Harichandthanda | 120.00/  08.04.2021 | 2021 | 2023 | 80 | 75.00 | 323.32 | 136.97 | 675/ 09.10.2023 |
| 811 | Constructin of HLB on R/f Appareddypally to AmudambandaThanda(via)Parvathapur at ch1/0 in  Ghanpur(M) | 120.00/  08.04.2021 | 2021 | 2023 | 90 | 246.53 | 536.52 | - | - |
| 812 | Construction of Bridge at Km 4.80 on road NH-65 to Mallaressygudem via Areguda an d Katrev | 118.00/  08.04.2021 | 2021 | 2023 | 100% | 182.66 | 282.66 | 49.79 | - |
| 813 | L030-8/600 of L028 to Chamanapally | 114.50/  04.03.2018 | 2021 | 2023 | 100 | - | - | 118.32 | - |
| 814 | C/o High Level Bridge at KM 1/130 on R/F Ashoknagar to Peddammagadda | 110.00/  08.04.2021 | 2021 | 2023 | 100 | - | 400.74 | 212.18 | - |
| 815 | Construction of LSB at 3/400 to 3/600 on road from T01- Road from Tamsi B to Kapparla of Tamsi Mandal | 108.00/  08.04.2021 | 2021 | 2023 | 100 | 169.29 | 475.70 | - | - |
| 816 | construction of high level bridge at 6.45 km on road from velganoor to kothakommuguda | 108.00/  08.04.2021 | 2021 | 2023 | 15% | - | - | - | - |
| 817 | C/o HLB at Km 3/750 on R/f Mogaddhagad PR (BT) Road to Karjepally R&B Road via Veervelly, Loanvellly | 105.00/  08.04.2021 | 2021 | 2024 | 45% | - | 50.00 | - | - |
|  | **BRIDGES** |  |  |  |  |  |  |  |  |
| 1 | C/o causeway on R/F Pegadapally to Edumotlapallythanda | 100.00/  04.04.2015 | 2016 | - | 62.04% | 0 | 99.27 | - | 160.00/ 27.3.18 |
| 2 | C/O BRIDGE ON R/F YAKINPUR TO SANGEM, MP KORUTLA | 212.00/  04.04.2015 | 2016 | - | 45.24% | 0 | 185.47 | - | 410.00/ 9.5.2018 |
| 3 | Construction of Low Level Causeway on R/F Narayanaraopet to Pedda Lingareddypally via Yellamma Temple in Siddipet Mandal | 144.00/  04.04.2015 | 2016 | - | 55.86% | 0 | 105.01 | - | 188.00/ 8.3.16 |
| 4 | C/O of High Level Bridge; On R/F: Damarancha to Old Banswada via Nagaram | 232.00/  04.04.2015 | 2016 | - | 48.52% | 0 | 162.54 | - | 335.00/ 17.1.20 |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 5 | C/o OF High Level Bridge; Achanpally to Peddamavandi | 350.00/  04.04.2015 | 2016 | - | 94.42% | 0 | 330.47 | - | - |
| 6 | C/o Bridge on R/F Road From Anantharam To Thakkallapalli, MP Jagitial | 200.00/  04.12.2015 | 2018 | - | 97.42% | 31.73 | 194.83 | - | - |
| 7 | Construction of Bridge (Low Level) on Road From Korutla Jambi Gadde to Sangem MP.Korutla | 350.00/  04.12.2015 | 2018 | - | 82.33% | 68.14 | 288.14 | - | - |
| 8 | C/o Bridge on R/F Gudur to Pothgal at Km 0/0 and ch 2/200 | 108.00/  04.12.2015 | 2016 | - | 99.04% | 46.86 | 106.96 | - | - |
| 9 | Const.of high level bridge across Local vagu on R/F NH44 to Patha Jangamaipally at 3/0 to 3/2 Km of Kothakota Mandal | 290.00/  04.12.2015 | 2021 | - | 56.99% | 461.06 | 701 | - | 1,230.00/  28.5.2021 |
| 10 | C/o High level bridge on Road from ZP Road to  Venkataratnapur Upto Abothpally of Toopran(M) | 950.00/  04.12.2015 | 2022 | - | 37.13% | 236.64 | 352.74 | - | - |
| 11 | Construction of Low Level Bridge @ 1/2 Km on r/F Mahibathpur ZP Road to Peepadpally | 100.00/  04.12.2015 | 2019 | - | 28.31% | 0 | 89.19 | - | 315.00/  18.7.2018 |
| 12 | Construction of Bridge on R/F PWD Road to Ghanapur via Mogiligundla | 126.00/  04.12.2015 | 2016 | - | 21.71% | 0 | 27.35 | - | - |
| 13 | C/o High Level Bridge Across Local Vagu on R/F Bhanjipet to Kundram, Lingalaghanpur (M). | 326.00/  04.12.2015 | 2016 | - | 38.27% | 30.19 | 124.75 | - | - |
| 14 | Balance work of C/o Casueway across Suddavagu at 2/600 on R/F Buttaigudem To Sarvai | 233.00/  04.12.2015 | 2022 | - | 48.46% | 47.39 | 112.91 | - | - |
|  | **BUILDINGS** |  |  |  |  |  |  |  |  |
| 1 | Construction of Integrated Dist. Office Complex at Newly formed district of Mulugu | 5,500.00/  23.03.2021 | 2022-23 | 31.10.2024 | 35% | 570.00 | 1,109.00 | 238.00 | - |
| 2 | Construction of Integrated Dist. Office Complex(IDOC) adjacent to exiting Collectorate at Karimnagar | 5100.00/  09.05.2018 | 2021-22 | 19.12.2022 | 65% | 48.90 | 2,208.90 | - | - |
| 3 | Construction of District Integrated Complex in district Head quarters of Adilabad dist. | 5,500.00/  15.06.2021 | 2023-24 | 09.08.2024 | 14% | - | - | 366.00 | - |
| 4 | Construction of District Integrated Complex and Residential Quarters at Warangal District. | 8,000.00/  31.03.2023 | 2023-24 | 15.09.2024 | 20% | - | 624.00 | 233.00 | - |
| 5 | Construction of Integrated Dist. Office Complex in newly formed district of Narayanpet | 5500.00/  23.03.2021 | 2023-24 | 30.03.2025 | 39% | 1,150.00 | 1,150.00 | - | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 6 | Construction of 6 suited (R&B) guest house near Clock tower, Nalgonda. | 625.00/  17.05.2022 | 2023-24 | 19.06.2024 | 50% | - | 48.00 | - | - |
| 7 | Construction of 6 suited (R&B) guest house at Adilabad District. | 220.00/  02.06.2017 | 2022-23 | 27.11.2023 | 25% | - | - | - | - |
| 8 | Construction of 4 suited IB at Vikarabad District. | 280.00/  02.06.2017 | 2018-19 | 09.06.2019 | 40% | - | 38.00 | - | - |
| 9 | Construction of 2 suited Inspection Bungalow at Mahabubabad Dist | 100.00/  02.06.2017 | 2021-22 | 26.02.2022 | 15% | - | - | 26.00 | - |
| 10 | C/o ZP Buiilding ZP premises at Karimnagar | 500.00/ 13.10.15 | 17.06.16 | … | … | 385.65 | … | 114.35 | … |
| 11 | C/o PR Division Office building at Sircilla | 200.00/  29.09.2015 | … | … | … | - | - | 200.00 | … |
| 12 | Construction of Guest House at Kollapur | 175.00/ 30.07.18 | 24.9.2019 | 23.09.2020 | … | - | … | 175.00 | … |
| 13 | Construction of new MPP Building at Sirpur T (V & M) | 100.00/ 13.10.15 | 21.03.2016 | 20.03.2017 | … | 75.11 | … | 24.89 | … |
| 14 | Balance work of C/o MPP Building at Kalluru | 100.00/ 13.10.15 | 20.02.2016 | 09.02.2017 | … | 82.71 | … | 17.29 | … |
| 15 | Construction of New MPP Building at Waddepally(V&M) | 100.00/ 13.10.15 | 18.4.2016 | 17.4.2017 | … | 21.80 | … | 78.20 | … |
| 16 | Construction of New MPP Building at Gadwal(V&M) | 100.00/ 13.10.15 | 2.4.2016 | 1.4.2017 | … | 90.97 | … | 9.03 | … |
| 17 | Construction of New MPP Building at Alair Village & Mandal | 100.00/ 13.10.15 | 02.03.16 | 01.03.17 | … | 73.11 | … | 26.89 | … |
| 18 | Constn.of New MPP Building at Mothkur | 100.00/ 13.10.15 | 12.05.16 | 11.05.17 | … | 68.49 | … | 31.51 | … |
| 19 | Const. of New MPP Buiding at Nakrekal | 100.00/ 13.10.15 | 27.05.16 | 26.05.17 | … | - | … | 100.00 | … |
| 20 | C/O New MPP Building at Chevella Mandal Ranga Reddy District | 100.00/ 13.10.15 | 30.04.16 | 29.04.17 | … | - | … | 100.00 | … |
| 21 | Construction of New MPP Building at Chityal (V&M) | 100.00/ 13.10.15 | 24.02.16 | 23.02.17 | … | 85.35 | 14.65 | - | … |
| 22 | Construction of New MPP Building at Mahadevpur (V) &(M) | 100.00/ 13.10.15 | 31.05.16 | 30.05.17 | … | 15.55 | … | 84.45 | … |
| 23 | Construction of New MPP Building at Mahamutharam  (V) &(M) | 100.00/ 13.10.15 | 06.08.16 | 05.08.17 | … | 55.10 | … | 44.90 | … |
| 24 | C/o MPP Building at Kothaguda | 100.00/ 13.10.15 | 17.03.2016 | 16.03.2017 | … | 72.40 | … | 27.60 | … |
| 25 | Construction of New MPP Building at Vikarabad | 100.00/ 13.10.15 | 10.02.16 | 09.02.17 | … | 81.69 | … | 18.31 | … |
| 26 | Construction of New MPP Building at Marpally | 100.00/ 13.10.15 | 11.03.16 | 10.03.17 | … | - | … | 100.00 | … |
| 27 | Construction of MPP office Building at Sadasivpet (V&M) | 100.00/ 13.10.15 | … | … | … | - | … | 100.00 | … |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 28 | Construction of New MPP Building at Jogipet | 100.00/ 13.10.15 | … | … | … | - | … | 100.00 | … |
| 29 | C/o New MPP Building at Cherial | 100.00/ 13.10.15 | 02.03.15 | 01.07.17 | … | 55.06 | … | 44.94 | … |
| 30 | C/o New MPP building at Thangallapally | 100.00/ 13.10.15 | 16.03.2020 | 15.03.2021 | … | 89.69 | … | 10.31 | … |
| 31 | C/o New MPP building at Vemulawada | 100.00/ 13.10.15 | … | … | … | 89.45 | 10.55 | - | … |
| 32 | C/o PR Guest house at Nizam Sagar | 100.00/  29.09.2015 | … | … | … | 26.91 | 44.55 | 52.43 | … |
|  | **OTHERS** |  |  |  |  |  |  |  |  |
| 1 | WSIS under Mission Bhageeratha (Urban) Balance Works Package-I (11 ULBs) - Bellampally, Bhainsa, Kagaznagar, Mancherial, Mandmarry, Nirmal, Jagtial,  Korutla, Metpally, Vemulawada, Peddapalli. | 47,843.00/12.05.2  020 | 2020 | 2021 | 100% | 12,348.56 | 57,407.84 | - | 61,102.00/  16.12.2022 |
| 2 | WSIS under Mission Bhageeratha (Urban) Balance works Package-II (09 ULBs) - Narsampet, Bhoopalpally, Parkal, Jangaon, Palvancha, Madhira, Sathupally, Yellandu & Mahabubabad | 37,415.00/12.05.2  020 | 2020 | 2021 | 81% | 10,670.06 | 28,823.65 | 4951.25 | 43,816.00/  16.12.2022 |
| 3 | WSIS under Mission Bhageeratha (Urban) Balance Works Package-III (18 ULBs) - Kamareddy, Bodhan, Zaheerabad, Sangareddy, Sadasivpet, Bhongir, Tandur, Vikarabad, Wanaparthy, Gadwal, Narayanpet, Kalwakurthy, Ieeja, Badepally, Nagarkurnool, Achampet,  Shadnagar, Ibrahimpatnam | 58,028.00/12.05.2  020 | 2020 | 2021 | 100% | 13,022.31 | 70,744.73 | - | 71,359.00/  16.12.2022 |
| 4 | Siricilla STP-Const. of STP,ID, Outfall Drain,etc including 5 year of O&M | 6,125.00/  06.08.2021 | 2022 | - | 87% | 850.00 | 2,307.20 | 1643.93 | - |
| 5 | Annuity Mode - Mission Bhageeratha (Urban) Huzurnagar, Kodad, Andol-jogipet, Husnabad, Devarakonda | 21,206.00/  01.07.2017 | 2018 | - | 100% | 6,100.31 | 21,623.61 | - | - |
| 6 | Warangal UIDSSMT | 17,866.00/  23.05.2007 | 2008 | 18 months | 100% | 3,182.57 | 19,535.57 | - | 19,656.44/  04.09.2017 |
| 7 | AMR SLBC Project | 5,81,143.00/  24.03.2005 | 1983 | 2023 | 71.33% | 16,258.00 | 7,70,209.00 | - | 8,09,000.00 |
| 8 | SRSP Stage-II | 83,075.00/  06.03.2005 | 1998 | 2023 | 97.52% | 322.00 | 1,22,183.00 | - | 1,22,041/  13.02.2017 |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 9 | J Chokka Rao Devadula LIS | 6,01,600.00/  08.01.2004 | 2003-04 | 2023 | 63.10% | 11,377.00 | 1383,672.00 | - | 13,44,544/  13.02.2017 |
| 10 | Tupakulagudem Barrage(PVNRKSSP) | 2,12,100.00/  12.09.2013 | 2013 | - | 97.32% | - | 199,022.00 | - | B |
| 11 | Pranahitha Project | 38,50,000.00/26.  05.2008 | 2008 | 2023 | 27.16% | 10,507.00 | 2,26,953.00 | - | 1,05,34,500.00 |
| 12 | Kaleswaram Project |  | 2023 | 64.11% | 1,54,306.00 | 94,38,081.00 | - |  |
| 13 | Indiramma Flood Flow Canal Project from SRSP | 2,46,600.00/ 2006 | 2006 | 2023 | 92.89% | 1,18,94.00 | 9,85,168.00 | - | 9,88,621/  02.08.2018 |
| 14 | Kaleswaram LIS | 44,300.00/  17.11.2008 | 2008 | 2023 | 39.54% | 16,125.00 | 575,154.00 | - | 63,200/  30.07.2008 |
| 15 | Sripada Yellampally LIS | 3,17,774.00/  17.02.2005 | 2005 | 2023 | 78.77% |  |  | - | 5,60,057.00 |
| 16 | Jawahar Nettempadu LIS | 1,42,800.00/22.06  .2005 | 2004-05 | 2023 | 91.94% | 2,651.00 | 2,41,045.00 | - | 2,75,399.00 |
| 17 | Rajiv Bhima LIS | 1,42,631.00/  30.10.2003 | 2004-06 | 2023 | 97.70% | 4,375.00 | 2,86,646.00 | - | 2,70,929.00 |
| 18 | Tumilla LIS (Phase-I) | 78,300.00/  01.09.2017 | 2017 | 2023 | 95.50% | - | 15,890.00 | - | B |
| 19 | Mahatma Gandhi Kalwakurthy LIS | 1,50,000.00/  02.03.2005 | 2005 | 2023 | 81.40% | 21,795.00 | 5,55,783.00 | - | 5,83,079.00 |
| 20 | Palamuru Rangareddy LIS | 35,20,000.00/  02.05.2016 | 2016 | 2023 | 75.68% | 6,07,559.00 | 29,22,960.00 | - | 49,59,500.00 |
| 21 | Dindi LIS | 6,19,000.00/  02.12.2016 | 2016 | 2024 | 37.48% | 55,532.00 | 3,34,500.00 | - | B |
| 22 | Chanaka-KorT Incl(Catering ayacut of Lower Penganaga) | 1,59,580.00/ | 2016 | 2023 | 66.92% | 9,573.00 | 1,04,062.00 | - | B |
| 23 | Sitarama LIS | 7,92,615.00/ | 2017 | 2024 | 69.51% | 1,09,354.00 | 821,633.00 | - | 13,05,798/  02.08.2018 |
| 24 | Palemvagu | 7,099.00/ | 2005 | 2023 | 91.50% | - | 20,326.00 | - | - |
| 25 | Peddavagu Jagannathpur Project | 12,464.00/  11.01.2005 | 2005 | 2023 | 81.50% | - | 17,662.00 | - | 24,466.00/  01.07.2017 |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 26 | Nilwai Project | 9,050.00/  17.03.2005 | 2011 | 2023 | 77.07% | - | 21,343.00 | - | 22,148.00/  03.03.2017 |
| 27 | Komarambheem Project | 27,414.00/  22.02.2005 | 2005 | 2023 | 82.00% | 1,816.00 | 77,970.00 | - | 88,236.00/  23.09.2016 |
| 28 | Lendi Project | 20,219.00/  26.03.2007 | 2005 | 2021-22 | 31.08% | - | 22,429.00 | - | 26,389.00/  16.06.2010 |
| 29 | Modikuntavagu Project | 12,460.00/  18.07.2005 | 2006 | 2021-22 | - | - | 6,032.00 | - | B |
| 30 | Sadarmatt Barrage | 52,829.00/  25.10.2016 | 2017 | 2023 | 94.00% | 25,930.00 | 53,715.00 | - | 52,039.00/  27.01.2018 |
| 31 | Intake arrangements at kollapur | 12,000.00/  02.04.2015 | 2015 | 2018 | 100% | - | 9,615.14 | - | - |
| 32 | Aug-Udayasamudram-NLG-Nakrekal | 13,500.00/  23.06.2015 | 2015 | 2023 | 100% | 1,200.00 | 31,637.00 | 15.87 | 25,400.00 |
| 33 | Aug-Suryapet | 5,400.00/  01.06.2015 | 2015 | 2021 | 100% |  |  |  | 5,900.00 |
| 34 | Aug-Tirumalgiri | 4,000.00/  01.06.2015 | 2015 | 2021 | 100% |  |  |  | - |
| 35 | Aug-Tungaturthy | 4,500.00/  01.06.2015 | 2015 | 2021 | 100% |  |  |  | 5,250.00 |
| 36 | Aug-Mothey | 1,500.00/  23.06.2015 | 2015 | 2021 | 100% |  |  |  | 1,950.00 |
| 37 | Godavari-kothagudem, Dummugudem (incl Pusur sub segment) | 2,08,200.00/  23.06.2015 | 2015 | 2020 | 100% | - | 1,60,159.78 | - | - |
| 38 | Yellampally Mancherial | 42,000.00/  23.06.2015 | 2015 | 2021 | 100% | 6.66 | 54,902.42 | - | 45,000.00 |
| 39 | Kadem Khanapur | 25,000.00/  01.06.2015 | 2015 | 2021 | 100% |  |  |  | 22,000.00 |
| 40 | AKBR-Kodandapur, Choutuppal, Bhongir | 2,10,600.00/  01.06.2015 | 2015 | 2023 | 100% | 1,116.00 | 1,51,288 | 506.94 | 1,80,500.00 |
| 41 | Intake @ Singur for Medak | 13,000.00/  07.02.2015 | 2015 | 2018 | 100% | - | 23,798.83 | - | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 42 | Intake@ Singur for sangareddy | 15,000.00/  07.02.2015 | 2015 | 2018 | 100% |  |  |  | - |
| 43 | Intake- Sircilla | 19,700.00/  07.02.2015 | 2015 | 2019 | 100% | 99.90 | 15,770.09 | 1,151.35 | - |
| 44 | Intake for Manthani- Bhupallpally | 5,500.00/  07.02.2015 | 2015 | 2018 | 100% |  |  |  | - |
| 45 | Intake arrangements for Manakondur-Husnabad- Huzurabad | 5,000.00/  07.02.2015 | 2015 | 2019 | 100% |  |  |  | - |
| 46 | Intake SRSP | 24,800.00/  07.02.2015 | 2015 | 2020 | 100% | 52.00 | 33,535.95 | 3,037.16 | - |
| 47 | intake at Yellampally | 4,750.00/  07.02.2015 | 2015 | 2021 | 100% |  |  |  | - |
| 48 | IntakeKaddam Segment | 3,000.00/  07.02.2015 | 2015 | 2019 | 100% |  |  |  | - |
| 49 | Intake Komrambheem | 11,500.00/  07.02.2015 | 2015 | 2019 | 100% |  |  |  | - |
| 50 | Intake arrangements at Mangapet | 1,300.00/  07.02.2015 | 2015 | 2019 | 100% | - | 1,062.67 | - | - |
| 51 | intake arrangements @ Pususru Godavari | 16,802.00/07.02.2  015 | 2015 | 2018 | 100% | - | 14,116.39 | - | - |
| 52 | intake @ Palair | 16,000.00/07.02.2  015 | 2015 | 2020 | 100% | - | 24,974.02 | - | - |
| 53 | intake @ Wyra | 15,500.00/07.02.2  015 | 2015 | 2020 | 100% |  |  |  | - |
| 54 | HMWSSB Warangal segment | 84,000.00/23.06.2  015 | 2015 | 2023 | 100% | 709.00 | 64,663.94 | 620.25 | - |
| 55 | NSP-Tailpond | 1,48,500.00/  01.06.2015 | 2015 | 2023 | 100% | 2,669.00 | 1,23,951.06 | 60.57 | 1,62,000.00 |
| 56 | Jurala segment | 70,000.00/  01.06.2015 | 2015 | 2018 | 100% | 31.00 | 47,515.13 | 583.57 | - |
| 57 | Singur-Sangareddy segment | 68,000.00/  01.06.2015 | 2015 | 2019 | 100% | - | 44,522.00 | - | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 58 | Singur-Narsapur segment | 44,500.00/  01.06.2015 | 2015 | 2019 | 100% | - | 24,528.00 | - | 34,500.00 |
| 59 | HMWSSB -Medchal segment | 16,000.00/  01.06.2015 | 2015 | 2019 | 100% | - | 15,487.00 | - | - |
| 60 | Singur - Jukkal, Bhodan, Bansawada and Yellareddy | 1,30,000.00/  01.06.2015 | 2015 | 2019 | 100% | - | 115,493.00 | - | - |
| 61 | Palair | 41,800.00/  23.06.2015 | 2015 | 2019 | 100% | - | 68,509.00 | 140.28 | - |
| 62 | Wyra | 57,500.00/  23.06.2015 | 2015 | 2019 | 100% |  |  |  | - |
| 63 | SRSP-Korutla, Jagtial, Dharmapuri Medarm cheruvu | 1,30,000.00/  23.06.2015 | 2015 | 2021 | 100% | 27.00 | 88,468.95 | 94.69 | - |
| 64 | C/o PM,RSF,PH near to Yellampally Reservior in PR Seg | 10,800.00/  02.04.2015 | 2015 | 2021 | 100% | - | 11,454.00 | - | 15,000.00 |
| 65 | MMD-Sircilla | 93,500.00/  01.06.2015 | 2015 | 2021 | 100% | 572.00 | 1,12,774.00 | 259.49 | - |
| 66 | Peddapally, Ramagundem | 65,000.00/  23.06.2015 | 2015 | 2021 | 100% |  |  |  | 60,800.00 |
| 67 | Manthani- Bhupalapally Seg (OVERALL) | 83,500.00/  23.06.2015 | 2015 | 2021 | 100% | 582.00 | 52,676.68 | 248.70 | - |
| 68 | LMD-Manakondur, Husnabad, Huzurabad | 1,80,000.00/  23.06.2015 | 2015 | 2022 | 100% | 770.00 | 94,092.00 | 722.03 | - |
| 69 | Karimnagar-Ramadugu | 24,000.00/  23.06.2015 | 2015 | 2022 | 100% | 7.00 | 14,931.00 | - | - |
| 70 | Godavari - Mangapet | 29,000.00/  23.06.2015 | 2015 | 2021 | 100% | 3.00 | 26,100.49 | 396.17 | 29,889.00 |
| 71 | Komarambheem-Asifabad segment | 1,65,000.00/  23.06.2015 | 2015 | 2021 | 100% | 25.00 | 1,26,878.00 | 2.73 | - |
| 72 | SRSP Balkonda -Nizamabad segment | 1,35,000.00/  23.06.2015 | 2015 | 2020 | 100% | - | 1,33,296.00 | - | - |
| 73 | SRSP-Adilabad segment | 1,53,000.00/  23.06.2015 | 2015 | 2021 | 100% | 208.00 | 1,23,674.53 | 3.95 | - |

|  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| **Sl.No**  **.** | **Name of the Project/Work** | **Estimated Cost of work and Date of sanction** | **Year of commence- ment** | **Target year of completion** | **Physical progress of work (in *per cent*)** | **Expenditure during the year**  **2023-24** | **Progressive Expenditure to the end of 31 March,**  **2024** | **Pending payments to the end of 31 March,**  **2024** | **Revised cost, if any and date of sanction** |
| **1** | **2** | **3** | **4** | **5** | **6** | **7** | **8** | **9** | **10** |
| ***(₹ in lakh)*** | | | | | | | | | |
| 74 | Palair -17 mdls in Wgl &1 mdl in Kmm | 1,70,000.00/  23.06.2015 | 2015 | 2023 | 100% | 424.00 | 1,26,972.00 | 42.12 | - |
| 75 | LMD -Manakondur extn -Parkal, Stn Ghanpur, warangal Segement | 1,33,500.00/  23.06.2015 | 2015 | 2021 | 100% | 356.00 | 1,08,117.84 | 144.06 | - |
| 76 | Srisailam segment | 1,80,000.00/  23.06.2015 | 2015 | 2021 | 100% | 18.00 | 1,46,589.13 | 618.02 | - |
| 77 | Srisailam - Gudipally | 5,95,300.00/  01.06.2015 | 2015 | 2021 | 100% | 102 | 500,100 | 9.18 | - |
| 78 | Alternate Source Arrangement to Yellore Segment from Anjanagiri Reservoir in Nagarkurnool District | 14,000.00/  22.01.2020 | 2020 | 2024 | 75% | 2,885.94 | 8,824.53 | 812.30 | - |
| 79 | Augumentation- Wanaparthy and Balakistapur from Yellore reservoir | 30,000.00/  22.01.2020 | 2020 | 2023 | 100% | 4,906.52 | 28,908.48 | 1,091.52 | - |
| 80 | HMWS segments (Janagaon, Gajwel, Alair-Bhongir and Medchal), with Mallanasagar as source | 67,400.00/  22.01.2020 | 2020 | 2024 | 91% | 14,748.66 | 94,588.23 | 5,200.00 | 1,21,200.00 |
| 81 | Drinking water to Nookapally Urban Colony (KCR Nagar) | 1,415.00/  19.07.2023 | 2023 | 2024 | 75% | - | - | - | - |